## Sheet2
Activity ID | Activity Name | Performance % Complete | Finish
MOC.REV.R06.U0200725.CON Construction |  | 45.06 | 2025-11-05
MOC.REV.R06.U0200725.CON.F1 First Floor |  | 65.73 | 2025-10-23
MOC.REV.R06.U0200725.CON.F1.Z1 Zone 01 |  | 54.36 | 2025-10-23
MOC.REV.R06.U0200725.CON.F1.Z1.FIN Finishes |  | 52.46 | 2025-10-23
MOC.REV.R06.U0200725.CON.F1.Z1.FIN.C&W Ceiling & Walls |  | 55.41 | 2025-10-23
MOC.CN.F1.Z1.04.1175 | Masonary works - First Floor Zone 01 | 100 | 10-Feb-25 A
MOC.CN.F1.Z1.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 01 | 100 | 10-Feb-25 A
MOC.CN.F1.Z1.09.1740 | Plaster First Stage - First Floor Zone 01 | 100 | 18-Feb-25 A
MOC.CN.F1.Z1.09.1745 | Plaster Second Stage - First Floor Zone 01 | 100 | 15-Apr-25 A
MOC.CN.F1.Z1.09.1685 | Wooden Cladding First Fix - First Floor Zone 01 | 100 | 21-Apr-25 A
MOC.CN.F1.Z1.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 01 | 100 | 22-Apr-25 A
MOC.CN.F1.Z1.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1680 | Wooden Ceiling First Fix - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1725 | Wooden Cladding Second Fix - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1455 | First and Second painting coats - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.10.1785 | GLASS partiton - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1735 | Acoustic wall panel Installation - First Floor Zone 01 | 100 | 21-Jun-25 A
MOC.CN.F1.Z1.09.1680[R] | Wooden Ceiling First Fix - First Floor Zone 01 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.F1.Z1.10.1795 | Curtain Installation - First Floor Zone 01 | 0 | 2025-07-31
MOC.CN.F1.Z1.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 01 [Remaining] | 30 | 2025-08-05
MOC.CN.F1.Z1.08.1430 | Doors Frame installation - First Floor Zone 01 | 0 | 2025-08-13
MOC.CN.F1.Z1.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 01 | 0 | 2025-08-23
MOC.CN.F1.Z1.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 01 | 0 | 2025-08-25
MOC.CN.F1.Z1.09.1455[R] | First and Second painting coats - First Floor Zone 01 [Remaining] | 30 | 2025-08-30
MOC.CN.F1.Z1.09.1725[R] | Wooden Cladding Second Fix - First Floor Zone 01 [Remaining] | 95 | 2025-08-31
MOC.CN.F1.Z1.08.1400 | Wooden Doors installation - First Floor Zone 01 | 0 | 2025-09-03
MOC.CN.F1.Z1.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 01 | 0 | 2025-09-10
MOC.CN.F1.Z1.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 01 | 0 | 2025-09-15
MOC.CN.F1.Z1.09.1765 | Cornice Installation - First Floor Zone 01 | 0 | 2025-09-16
MOC.CN.F1.Z1.10.1775 | Signage works - First Floor Zone 01 | 0 | 2025-09-16
MOC.CN.F1.Z1.10.2780 | Elevator Finishes - First Floor Zone 01 | 0 | 2025-09-24
MOC.CN.F1.Z1.09.1460 | Final painting coat - First Floor Zone 01 | 0 | 2025-10-04
MOC.CN.F1.Z1.10.1785[R] | GLASS partiton - First Floor Zone 01 [Remaining] | 55 | 2025-10-05
MOC.CN.F1.Z1.05.1220 | Metal Handles for stairs - First Floor Zone 01 | 0 | 2025-10-12
MOC.CN.F1.Z1.18.01 | Final Touch Up - First Floor Zone 01 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F1.Z1.FIN.FLR Flooring |  | 43.37 | 2025-10-23
MOC.CN.F1.Z1.09.1640 | Raised Floor First Fix - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1645 | Raised Floor Final fix installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 01 | 0 | 2025-09-06
MOC.CN.F1.Z1.09.1640[R] | Raised Floor First Fix - First Floor Zone 01 [Remaining] | 35 | 2025-09-17
MOC.CN.F1.Z1.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 01 [Remaining] | 35 | 2025-09-25
MOC.CN.F1.Z1.09.1595 | Carpet Installation - First Floor Zone 01 | 0 | 2025-10-12
MOC.CN.F1.Z1.09.1690 | Skirting Installation - First Floor Zone 01 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F1.Z1.MEP MEP |  | 55.72 | 2025-10-19
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.MEC Mechanical |  | 68.44 | 2025-09-24
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.MEC.PL Plumbing |  | 76.29 | 2025-09-21
MOC.CN.F1.Z1.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 01 | 100 | 16-Apr-25 A
MOC.CN.F1.Z1.15.2420 | Water Supply pipes insulation - First Floor Zone 01 | 100 | 16-Apr-25 A
MOC.CN.F1.Z1.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 01 | 100 | 17-Apr-25 A
MOC.CN.F1.Z1.15.2295 | Drainage pipes installation & Testing - First Floor Zone 01 | 100 | 01-May-25 A
MOC.CN.F1.Z1.15.2315 | Floor Drain Installation - First Floor Zone 01 | 0 | 2025-09-21
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.MEC.FF Fire Fightig |  | 54.76 | 2025-09-24
MOC.CN.F1.Z1.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.1970 | Fire Fighting valves and accessories - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.1975 | Fire-hose cabinets installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.1955[R] | Fire Fighting pipes installation & Testing - First Floor Zone 01 [Remaining] | 95 | 2025-07-21
MOC.CN.F1.Z1.15.1970[R] | Fire Fighting valves and accessories - First Floor Zone 01 [Remaining] | 0 | 2025-07-23
MOC.CN.F1.Z1.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 01 [Remaining] | 0 | 2025-07-27
MOC.CN.F1.Z1.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 01 [Remaining] | 0 | 2025-09-04
MOC.CN.F1.Z1.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 01 | 0 | 2025-09-14
MOC.CN.F1.Z1.15.1980 | Fire extinguishers installation - First Floor Zone 01 | 0 | 2025-09-15
MOC.CN.F1.Z1.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F1.Z1.15.1985 | Fire sprinklers installation - First Floor Zone 01 | 0 | 2025-09-24
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.MEC.HV HVAC |  | 72.34 | 2025-09-22
MOC.CN.F1.Z1.15.2340 | Fan Coil Units Installation - First Floor Zone 01 | 100 | 08-May-25 A
MOC.CN.F1.Z1.15.2275 | Thermostat Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2320 | Air Handling pipes installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2280 | Variable Air Volume (VAV) - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2380 | Duct Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2395 | HVAC Valves installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2385 | Duct Insulation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2375 | HVAC Pipes Insulation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2390 | Duct Lining - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2280[R] | Variable Air Volume (VAV) - First Floor Zone 01 [Remaining] | 100 | 31-May-25 A
MOC.CN.F1.Z1.15.2370[R] | HVAC Pipes Installation & Testing - First Floor Zone 01 [Remaining] | 95 | 2025-07-21
MOC.CN.F1.Z1.15.2375[R] | HVAC Pipes Insulation - First Floor Zone 01 [Remaining] | 0 | 2025-07-23
MOC.CN.F1.Z1.15.2380[R] | Duct Installation - First Floor Zone 01 [Remaining] | 95 | 2025-07-24
MOC.CN.F1.Z1.15.2385[R] | Duct Insulation - First Floor Zone 01 [Remaining] | 95 | 2025-07-27
MOC.CN.F1.Z1.15.2390[R] | Duct Lining - First Floor Zone 01 [Remaining] | 95 | 2025-07-29
MOC.CN.F1.Z1.15.2395[R] | HVAC Valves installation - First Floor Zone 01 [Remaining] | 0 | 2025-07-31
MOC.CN.F1.Z1.15.2320[R] | Air Handling pipes installation - First Floor Zone 01 [Remaining] | 0 | 2025-08-04
MOC.CN.F1.Z1.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 01 | 0 | 2025-08-20
MOC.CN.F1.Z1.15.2275[R] | Thermostat Installation - First Floor Zone 01 [Remaining] | 0 | 2025-09-08
MOC.CN.F1.Z1.15.2325 | Air Handling units installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F1.Z1.15.2100 | Air Diffusers Installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL Electrical |  | 51.46 | 2025-10-19
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.EP Electrical Power |  | 52.14 | 2025-10-19
MOC.CN.F1.Z1.16.2655 | Conduits and boxes installation - First Floor Zone 01 | 100 | 07-May-25 A
MOC.CN.F1.Z1.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 01 | 100 | 07-May-25 A
MOC.CN.F1.Z1.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2630 | Cables & Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2745 | Wiring Installation in floors - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 01 [Remaining] | 55 | 2025-07-26
MOC.CN.F1.Z1.16.2630[R] | Cables & Wiring Installation - First Floor Zone 01 [Remaining] | 35 | 2025-08-02
MOC.CN.F1.Z1.16.2745[R] | Wiring Installation in floors - First Floor Zone 01 [Remaining] | 0 | 2025-08-06
MOC.CN.F1.Z1.16.2625 | Earthing System installation - First Floor Zone 01 | 0 | 2025-08-23
MOC.CN.F1.Z1.16.2715 | Distribution board installation - First Floor Zone 01 | 0 | 2025-09-11
MOC.CN.F1.Z1.16.2495 | Sockets and Switches installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F1.Z1.16.2490 | Lighting fixtures installation - First Floor Zone 01 | 0 | 2025-09-28
MOC.CN.F1.Z1.16.2750 | Floor Sockets Installation - First Floor Zone 01 | 0 | 2025-10-19
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.AV Audio Visual |  | 52 | 2025-09-22
MOC.CN.F1.Z1.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 01 | 100 | 30-Apr-25 A
MOC.CN.F1.Z1.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 01 [Remaining] | 20 | 2025-07-28
MOC.CN.F1.Z1.16.2515 | Audiovisual system installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.LC Lighting Control |  | 63.74 | 2025-09-22
MOC.CN.F1.Z1.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 01 | 100 | 10-May-25 A
MOC.CN.F1.Z1.16.2710 | Lighting Control Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2710[R] | Lighting Control Wiring Installation - First Floor Zone 01 [Remaining] | 45 | 2025-07-24
MOC.CN.F1.Z1.16.2660 | Lighting Control System installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-22
MOC.CN.F1.Z1.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 01 | 100 | 06-May-25 A
MOC.CN.F1.Z1.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 01 [Remaining] | 0 | 2025-08-04
MOC.CN.F1.Z1.16.2505 | Telecommunication and Data system installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.SS Security System |  | 2.78 | 2025-09-22
MOC.CN.F1.Z1.16.2670 | Security System Conduits and boxes installation - First Floor Zone 01 | 100 | 06-May-25 A
MOC.CN.F1.Z1.16.2695 | Security System Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2695[R] | Security System Wiring Installation - First Floor Zone 01 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z1.16.2640 | Security System Installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.IPTV IPTV System |  | 40 | 2025-09-22
MOC.CN.F1.Z1.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 01 | 100 | 06-May-25 A
MOC.CN.F1.Z1.16.2700 | IPTV System Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2700[R] | IPTV System Wiring Installation - First Floor Zone 01 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z1.16.2645 | IPTV System installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.1 | 2025-09-22
MOC.CN.F1.Z1.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 01 | 100 | 08-Apr-25 A
MOC.CN.F1.Z1.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 01 [Remaining] | 40 | 2025-07-22
MOC.CN.F1.Z1.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.PA Public Address System |  | 40 | 2025-09-22
MOC.CN.F1.Z1.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.F1.Z1.16.2730 | Public Address System Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 01 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z1.16.2525 | Public Address System installation - First Floor Zone 01 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z1.MEP.EL.CBS Central Battery |  | 92.5 | 2025-07-23
MOC.CN.F1.Z1.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.F1.Z1.16.2690 | Central Battery System Wiring Installation - First Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F1.Z1.16.2690[R] | Central Battery System Wiring Installation - First Floor Zone 01 [Remaining] | 40 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z2 Zone 02 |  | 52.58 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z2.FIN Finishes |  | 52.17 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z2.FIN.C&W Ceiling & Walls |  | 55.67 | 2025-10-20
MOC.CN.F1.Z2.04.1175 | Masonary works - First Floor Zone 02 | 100 | 10-Feb-25 A
MOC.CN.F1.Z2.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 02 | 100 | 13-Feb-25 A
MOC.CN.F1.Z2.09.1740 | Plaster First Stage - First Floor Zone 02 | 100 | 15-Feb-25 A
MOC.CN.F1.Z2.09.1745 | Plaster Second Stage - First Floor Zone 02 | 100 | 15-Apr-25 A
MOC.CN.F1.Z2.09.1685 | Wooden Cladding First Fix - First Floor Zone 02 | 100 | 19-Apr-25 A
MOC.CN.F1.Z2.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 02 | 100 | 22-Apr-25 A
MOC.CN.F1.Z2.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.09.1680 | Wooden Ceiling First Fix - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.09.1455 | First and Second painting coats - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.10.1785 | GLASS partiton - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.09.1735 | Acoustic wall panel Installation - First Floor Zone 02 | 100 | 19-Jun-25 A
MOC.CN.F1.Z2.09.1680[R] | Wooden Ceiling First Fix - First Floor Zone 02 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.F1.Z2.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 02 [Remaining] | 35 | 2025-08-09
MOC.CN.F1.Z2.08.1430 | Doors Frame installation - First Floor Zone 02 | 0 | 2025-08-24
MOC.CN.F1.Z2.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 02 | 0 | 2025-08-25
MOC.CN.F1.Z2.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 02 | 0 | 2025-08-26
MOC.CN.F1.Z2.09.1455[R] | First and Second painting coats - First Floor Zone 02 [Remaining] | 35 | 2025-09-02
MOC.CN.F1.Z2.08.1400 | Wooden Doors installation - First Floor Zone 02 | 0 | 2025-09-03
MOC.CN.F1.Z2.09.1725 | Wooden Cladding Second Fix - First Floor Zone 02 | 95 | 2025-09-09
MOC.CN.F1.Z2.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 02 | 0 | 2025-09-10
MOC.CN.F1.Z2.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 02 | 0 | 2025-09-11
MOC.CN.F1.Z2.10.1775 | Signage works - First Floor Zone 02 | 0 | 2025-09-16
MOC.CN.F1.Z2.09.1765 | Cornice Installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.CN.F1.Z2.10.2780 | Elevator Finishes - First Floor Zone 02 | 0 | 2025-09-28
MOC.CN.F1.Z2.10.1785[R] | GLASS partiton - First Floor Zone 02 [Remaining] | 35 | 2025-09-30
MOC.CN.F1.Z2.09.1460 | Final painting coat - First Floor Zone 02 | 0 | 2025-10-07
MOC.CN.F1.Z2.05.1220 | Metal Handles for stairs - First Floor Zone 02 | 0 | 2025-10-19
MOC.CN.F1.Z2.10.1795 | Curtain Installation - First Floor Zone 02 | 0 | 2025-10-19
MOC.CN.F1.Z2.18.01 | Final Touch Up - First Floor Zone 02 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z2.FIN.FLR Flooring |  | 41.36 | 2025-10-20
MOC.CN.F1.Z2.09.1640 | Raised Floor First Fix - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.09.1645 | Raised Floor Final fix installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 02 | 0 | 2025-09-09
MOC.CN.F1.Z2.09.1640[R] | Raised Floor First Fix - First Floor Zone 02 [Remaining] | 35 | 2025-09-20
MOC.CN.F1.Z2.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 02 [Remaining] | 35 | 2025-09-22
MOC.CN.F1.Z2.09.1595 | Carpet Installation - First Floor Zone 02 | 0 | 2025-10-12
MOC.CN.F1.Z2.09.1690 | Skirting Installation - First Floor Zone 02 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z2.MEP MEP |  | 52.87 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.MEC Mechanical |  | 66.05 | 2025-10-01
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.MEC.PL Plumbing |  | 75.64 | 2025-09-30
MOC.CN.F1.Z2.15.2420 | Water Supply pipes insulation - First Floor Zone 02 | 100 | 19-Apr-25 A
MOC.CN.F1.Z2.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 02 | 100 | 20-Apr-25 A
MOC.CN.F1.Z2.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 02 | 100 | 21-Apr-25 A
MOC.CN.F1.Z2.15.2295 | Drainage pipes installation & Testing - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2295[R] | Drainage pipes installation & Testing - First Floor Zone 02 [Remaining] | 70 | 2025-07-21
MOC.CN.F1.Z2.15.2315 | Floor Drain Installation - First Floor Zone 02 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.MEC.FF Fire Fightig |  | 56.97 | 2025-10-01
MOC.CN.F1.Z2.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.1970 | Fire Fighting valves and accessories - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.1975 | Fire-hose cabinets installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 02 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F1.Z2.15.1955[R] | Fire Fighting pipes installation & Testing - First Floor Zone 02 [Remaining] | 80 | 2025-07-24
MOC.CN.F1.Z2.15.1970[R] | Fire Fighting valves and accessories - First Floor Zone 02 [Remaining] | 35 | 2025-07-30
MOC.CN.F1.Z2.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 02 [Remaining] | 0 | 2025-09-08
MOC.CN.F1.Z2.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 02 | 0 | 2025-09-13
MOC.CN.F1.Z2.15.1980 | Fire extinguishers installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.CN.F1.Z2.15.1985 | Fire sprinklers installation - First Floor Zone 02 | 0 | 2025-09-20
MOC.CN.F1.Z2.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 02 | 0 | 2025-10-01
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.MEC.HV HVAC |  | 68.32 | 2025-09-18
MOC.CN.F1.Z2.15.2340 | Fan Coil Units Installation - First Floor Zone 02 | 100 | 11-May-25 A
MOC.CN.F1.Z2.15.2275 | Thermostat Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2320 | Air Handling pipes installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2280 | Variable Air Volume (VAV) - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2380 | Duct Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2395 | HVAC Valves installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2385 | Duct Insulation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2375 | HVAC Pipes Insulation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2390 | Duct Lining - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.15.2380[R] | Duct Installation - First Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.F1.Z2.15.2385[R] | Duct Insulation - First Floor Zone 02 [Remaining] | 95 | 2025-07-23
MOC.CN.F1.Z2.15.2370[R] | HVAC Pipes Installation & Testing - First Floor Zone 02 [Remaining] | 80 | 2025-07-24
MOC.CN.F1.Z2.15.2320[R] | Air Handling pipes installation - First Floor Zone 02 [Remaining] | 0 | 2025-07-24
MOC.CN.F1.Z2.15.2390[R] | Duct Lining - First Floor Zone 02 [Remaining] | 0 | 2025-07-31
MOC.CN.F1.Z2.15.2375[R] | HVAC Pipes Insulation - First Floor Zone 02 [Remaining] | 25 | 2025-08-02
MOC.CN.F1.Z2.15.2280[R] | Variable Air Volume (VAV) - First Floor Zone 02 [Remaining] | 30 | 2025-08-03
MOC.CN.F1.Z2.15.2395[R] | HVAC Valves installation - First Floor Zone 02 [Remaining] | 0 | 2025-08-03
MOC.CN.F1.Z2.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 02 | 0 | 2025-08-11
MOC.CN.F1.Z2.15.2275[R] | Thermostat Installation - First Floor Zone 02 [Remaining] | 0 | 2025-09-08
MOC.CN.F1.Z2.15.2325 | Air Handling units installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.CN.F1.Z2.15.2100 | Air Diffusers Installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL Electrical |  | 48.32 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.EP Electrical Power |  | 50.12 | 2025-10-18
MOC.CN.F1.Z2.16.2655 | Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2630 | Cables & Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2745 | Wiring Installation in floors - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 02 [Remaining] | 77.99 | 2025-07-21
MOC.CN.F1.Z2.16.2630[R] | Cables & Wiring Installation - First Floor Zone 02 [Remaining] | 55 | 2025-07-21
MOC.CN.F1.Z2.16.2745[R] | Wiring Installation in floors - First Floor Zone 02 [Remaining] | 0 | 2025-07-28
MOC.CN.F1.Z2.16.2625 | Earthing System installation - First Floor Zone 02 | 0 | 2025-08-13
MOC.CN.F1.Z2.16.2715 | Distribution board installation - First Floor Zone 02 | 0 | 2025-09-13
MOC.CN.F1.Z2.16.2495 | Sockets and Switches installation - First Floor Zone 02 | 0 | 2025-09-20
MOC.CN.F1.Z2.16.2490 | Lighting fixtures installation - First Floor Zone 02 | 0 | 2025-09-27
MOC.CN.F1.Z2.16.2750 | Floor Sockets Installation - First Floor Zone 02 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.AV Audio Visual |  | 45 | 2025-09-20
MOC.CN.F1.Z2.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 02 [Remaining] | 0 | 2025-07-30
MOC.CN.F1.Z2.16.2515 | Audiovisual system installation - First Floor Zone 02 | 0 | 2025-09-20
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.LC Lighting Control |  | 69.1 | 2025-09-18
MOC.CN.F1.Z2.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2710 | Lighting Control Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2710[R] | Lighting Control Wiring Installation - First Floor Zone 02 [Remaining] | 80 | 2025-07-22
MOC.CN.F1.Z2.16.2660 | Lighting Control System installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-22
MOC.CN.F1.Z2.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 02 [Remaining] | 0 | 2025-08-04
MOC.CN.F1.Z2.16.2505 | Telecommunication and Data system installation - First Floor Zone 02 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.SS Security System |  | 2.78 | 2025-09-18
MOC.CN.F1.Z2.16.2670 | Security System Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2695 | Security System Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2695[R] | Security System Wiring Installation - First Floor Zone 02 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z2.16.2640 | Security System Installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.IPTV IPTV System |  | 40 | 2025-09-18
MOC.CN.F1.Z2.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2700 | IPTV System Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2700[R] | IPTV System Wiring Installation - First Floor Zone 02 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z2.16.2645 | IPTV System installation - First Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.1 | 2025-09-22
MOC.CN.F1.Z2.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.F1.Z2.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 02 [Remaining] | 70 | 2025-07-21
MOC.CN.F1.Z2.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 02 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.PA Public Address System |  | 40 | 2025-09-22
MOC.CN.F1.Z2.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 02 | 100 | 04-May-25 A
MOC.CN.F1.Z2.16.2730 | Public Address System Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 02 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z2.16.2525 | Public Address System installation - First Floor Zone 02 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.F1.Z2.MEP.EL.CBS Central Battery |  | 75 | 2025-07-28
MOC.CN.F1.Z2.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 02 | 100 | 04-May-25 A
MOC.CN.F1.Z2.16.2690 | Central Battery System Wiring Installation - First Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F1.Z2.16.2690[R] | Central Battery System Wiring Installation - First Floor Zone 02 [Remaining] | 0 | 2025-07-28
MOC.REV.R06.U0200725.CON.F1.Z3 Zone 03 |  | 55.2 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z3.FIN Finishes |  | 50.29 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z3.FIN.C&W Ceiling & Walls |  | 54.22 | 2025-10-20
MOC.CN.F1.Z3.04.1175 | Masonary works - First Floor Zone 03 | 100 | 10-Feb-25 A
MOC.CN.F1.Z3.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 03 | 100 | 13-Feb-25 A
MOC.CN.F1.Z3.09.1740 | Plaster First Stage - First Floor Zone 03 | 100 | 15-Feb-25 A
MOC.CN.F1.Z3.09.1745 | Plaster Second Stage - First Floor Zone 03 | 100 | 15-Apr-25 A
MOC.CN.F1.Z3.09.1685 | Wooden Cladding First Fix - First Floor Zone 03 | 100 | 20-Apr-25 A
MOC.CN.F1.Z3.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 03 | 100 | 22-Apr-25 A
MOC.CN.F1.Z3.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.09.1680 | Wooden Ceiling First Fix - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.09.1455 | First and Second painting coats - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.09.1735 | Acoustic wall panel Installation - First Floor Zone 03 | 100 | 21-Jun-25 A
MOC.CN.F1.Z3.09.1680[R] | Wooden Ceiling First Fix - First Floor Zone 03 [Remaining] | 100 | 23-Jun-25 A
MOC.CN.F1.Z3.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 03 [Remaining] | 40 | 2025-08-10
MOC.CN.F1.Z3.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 03 | 0 | 2025-08-21
MOC.CN.F1.Z3.09.1455[R] | First and Second painting coats - First Floor Zone 03 [Remaining] | 35 | 2025-08-28
MOC.CN.F1.Z3.08.1430 | Doors Frame installation - First Floor Zone 03 | 0 | 2025-09-04
MOC.CN.F1.Z3.09.1725 | Wooden Cladding Second Fix - First Floor Zone 03 | 95 | 2025-09-04
MOC.CN.F1.Z3.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 03 | 0 | 2025-09-06
MOC.CN.F1.Z3.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 03 | 0 | 2025-09-07
MOC.CN.F1.Z3.08.1400 | Wooden Doors installation - First Floor Zone 03 | 0 | 2025-09-11
MOC.CN.F1.Z3.09.1765 | Cornice Installation - First Floor Zone 03 | 0 | 2025-09-15
MOC.CN.F1.Z3.10.1775 | Signage works - First Floor Zone 03 | 0 | 2025-09-17
MOC.CN.F1.Z3.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 03 | 0 | 2025-09-20
MOC.CN.F1.Z3.10.2780 | Elevator Finishes - First Floor Zone 03 | 0 | 2025-09-22
MOC.CN.F1.Z3.10.1785 | GLASS partiton - First Floor Zone 03 | 50 | 2025-10-06
MOC.CN.F1.Z3.09.1460 | Final painting coat - First Floor Zone 03 | 0 | 2025-10-11
MOC.CN.F1.Z3.10.1795 | Curtain Installation - First Floor Zone 03 | 0 | 2025-10-12
MOC.CN.F1.Z3.05.1220 | Metal Handles for stairs - First Floor Zone 03 | 0 | 2025-10-15
MOC.CN.F1.Z3.18.01 | Final Touch Up - First Floor Zone 03 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z3.FIN.FLR Flooring |  | 38.85 | 2025-10-20
MOC.CN.F1.Z3.09.1640 | Raised Floor First Fix - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.09.1645 | Raised Floor Final fix installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.09.1515 | Porcelain tiles for Flooring - First Floor Zone 03 | 0 | 2025-09-09
MOC.CN.F1.Z3.09.1640[R] | Raised Floor First Fix - First Floor Zone 03 [Remaining] | 35 | 2025-09-27
MOC.CN.F1.Z3.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 03 | 0 | 2025-09-29
MOC.CN.F1.Z3.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 03 [Remaining] | 35 | 2025-10-04
MOC.CN.F1.Z3.09.1595 | Carpet Installation - First Floor Zone 03 | 0 | 2025-10-15
MOC.CN.F1.Z3.09.1690 | Skirting Installation - First Floor Zone 03 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z3.MEP MEP |  | 58.65 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.MEC Mechanical |  | 66.01 | 2025-10-15
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.MEC.PL Plumbing |  | 74.12 | 2025-10-15
MOC.CN.F1.Z3.15.2420 | Water Supply pipes insulation - First Floor Zone 03 | 100 | 19-Apr-25 A
MOC.CN.F1.Z3.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 03 | 100 | 20-Apr-25 A
MOC.CN.F1.Z3.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 03 | 100 | 20-Apr-25 A
MOC.CN.F1.Z3.15.2295 | Drainage pipes installation & Testing - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2295[R] | Drainage pipes installation & Testing - First Floor Zone 03 [Remaining] | 0 | 2025-07-22
MOC.CN.F1.Z3.15.2315 | Floor Drain Installation - First Floor Zone 03 | 0 | 2025-10-15
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.MEC.FF Fire Fightig |  | 53.92 | 2025-10-02
MOC.CN.F1.Z3.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.1970 | Fire Fighting valves and accessories - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.1975 | Fire-hose cabinets installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.1955[R] | Fire Fighting pipes installation & Testing - First Floor Zone 03 [Remaining] | 75 | 2025-07-28
MOC.CN.F1.Z3.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 03 [Remaining] | 0 | 2025-07-31
MOC.CN.F1.Z3.15.1970[R] | Fire Fighting valves and accessories - First Floor Zone 03 [Remaining] | 0 | 2025-08-03
MOC.CN.F1.Z3.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 03 [Remaining] | 0 | 2025-08-17
MOC.CN.F1.Z3.15.1980 | Fire extinguishers installation - First Floor Zone 03 | 0 | 2025-09-14
MOC.CN.F1.Z3.15.1985 | Fire sprinklers installation - First Floor Zone 03 | 0 | 2025-09-14
MOC.CN.F1.Z3.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 03 | 0 | 2025-09-16
MOC.CN.F1.Z3.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 03 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.MEC.HV HVAC |  | 69.08 | 2025-09-21
MOC.CN.F1.Z3.15.2340 | Fan Coil Units Installation - First Floor Zone 03 | 100 | 11-May-25 A
MOC.CN.F1.Z3.15.2275 | Thermostat Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2320 | Air Handling pipes installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2280 | Variable Air Volume (VAV) - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2380 | Duct Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2385 | Duct Insulation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2375 | HVAC Pipes Insulation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2390 | Duct Lining - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.15.2370[R] | HVAC Pipes Installation & Testing - First Floor Zone 03 [Remaining] | 85 | 2025-07-23
MOC.CN.F1.Z3.15.2380[R] | Duct Installation - First Floor Zone 03 [Remaining] | 85 | 2025-07-24
MOC.CN.F1.Z3.15.2375[R] | HVAC Pipes Insulation - First Floor Zone 03 [Remaining] | 0 | 2025-07-30
MOC.CN.F1.Z3.15.2385[R] | Duct Insulation - First Floor Zone 03 [Remaining] | 40 | 2025-07-31
MOC.CN.F1.Z3.15.2395 | HVAC Valves installation - First Floor Zone 03 | 0 | 2025-08-06
MOC.CN.F1.Z3.15.2390[R] | Duct Lining - First Floor Zone 03 [Remaining] | 40 | 2025-08-07
MOC.CN.F1.Z3.15.2320[R] | Air Handling pipes installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-09
MOC.CN.F1.Z3.15.2280[R] | Variable Air Volume (VAV) - First Floor Zone 03 [Remaining] | 0 | 2025-08-14
MOC.CN.F1.Z3.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 03 | 0 | 2025-08-28
MOC.CN.F1.Z3.15.2100 | Air Diffusers Installation - First Floor Zone 03 | 0 | 2025-09-16
MOC.CN.F1.Z3.15.2275[R] | Thermostat Installation - First Floor Zone 03 [Remaining] | 0 | 2025-09-16
MOC.CN.F1.Z3.15.2325 | Air Handling units installation - First Floor Zone 03 | 0 | 2025-09-21
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL Electrical |  | 56.05 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.EP Electrical Power |  | 68.54 | 2025-10-18
MOC.CN.F1.Z3.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 03 | 100 | 05-May-25 A
MOC.CN.F1.Z3.16.2655 | Conduits and boxes installation - First Floor Zone 03 | 100 | 08-May-25 A
MOC.CN.F1.Z3.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2630 | Cables & Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2745 | Wiring Installation in floors - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 03 [Remaining] | 60 | 2025-07-28
MOC.CN.F1.Z3.16.2630[R] | Cables & Wiring Installation - First Floor Zone 03 [Remaining] | 80 | 2025-07-30
MOC.CN.F1.Z3.16.2745[R] | Wiring Installation in floors - First Floor Zone 03 [Remaining] | 0 | 2025-08-11
MOC.CN.F1.Z3.16.2625 | Earthing System installation - First Floor Zone 03 | 0 | 2025-08-27
MOC.CN.F1.Z3.16.2495 | Sockets and Switches installation - First Floor Zone 03 | 0 | 2025-09-21
MOC.CN.F1.Z3.16.2715 | Distribution board installation - First Floor Zone 03 | 100 | 25-Sep-25 A
MOC.CN.F1.Z3.16.2490 | Lighting fixtures installation - First Floor Zone 03 | 0 | 2025-10-06
MOC.CN.F1.Z3.16.2750 | Floor Sockets Installation - First Floor Zone 03 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.AV Audio Visual |  | 40 | 2025-09-17
MOC.CN.F1.Z3.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 03 | 100 | 05-May-25 A
MOC.CN.F1.Z3.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-18
MOC.CN.F1.Z3.16.2515 | Audiovisual system installation - First Floor Zone 03 | 0 | 2025-09-17
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.LC Lighting Control |  | 49.1 | 2025-09-21
MOC.CN.F1.Z3.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 03 | 100 | 05-May-25 A
MOC.CN.F1.Z3.16.2710 | Lighting Control Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2710[R] | Lighting Control Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-14
MOC.CN.F1.Z3.16.2660 | Lighting Control System installation - First Floor Zone 03 | 0 | 2025-09-21
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.T&D Telecommunication & Data System |  | 65.86 | 2025-09-17
MOC.CN.F1.Z3.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 03 | 100 | 07-May-25 A
MOC.CN.F1.Z3.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 03 [Remaining] | 60 | 2025-08-13
MOC.CN.F1.Z3.16.2505 | Telecommunication and Data system installation - First Floor Zone 03 | 0 | 2025-09-17
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.SS Security System |  | 2.78 | 2025-09-18
MOC.CN.F1.Z3.16.2670 | Security System Conduits and boxes installation - First Floor Zone 03 | 100 | 07-May-25 A
MOC.CN.F1.Z3.16.2695 | Security System Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2695[R] | Security System Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-18
MOC.CN.F1.Z3.16.2640 | Security System Installation - First Floor Zone 03 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.IPTV IPTV System |  | 40 | 2025-09-17
MOC.CN.F1.Z3.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 03 | 100 | 07-May-25 A
MOC.CN.F1.Z3.16.2700 | IPTV System Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2700[R] | IPTV System Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-20
MOC.CN.F1.Z3.16.2645 | IPTV System installation - First Floor Zone 03 | 0 | 2025-09-17
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 57.51 | 2025-09-21
MOC.CN.F1.Z3.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 03 | 100 | 08-Apr-25 A
MOC.CN.F1.Z3.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-06
MOC.CN.F1.Z3.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 03 | 0 | 2025-09-21
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.PA Public Address System |  | 38.33 | 2025-09-20
MOC.CN.F1.Z3.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 03 | 100 | 07-May-25 A
MOC.CN.F1.Z3.16.2730 | Public Address System Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-08-18
MOC.CN.F1.Z3.16.2525 | Public Address System installation - First Floor Zone 03 | 0 | 2025-09-20
MOC.REV.R06.U0200725.CON.F1.Z3.MEP.EL.CBS Central Battery |  | 72.5 | 2025-07-29
MOC.CN.F1.Z3.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 03 | 100 | 07-May-25 A
MOC.CN.F1.Z3.16.2690 | Central Battery System Wiring Installation - First Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F1.Z3.16.2690[R] | Central Battery System Wiring Installation - First Floor Zone 03 [Remaining] | 0 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z4 Zone 04 |  | 58.44 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z4.FIN Finishes |  | 61.18 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z4.FIN.C&W Ceiling & Walls |  | 60.25 | 2025-10-20
MOC.CN.F1.Z4.04.1175 | Masonary works - First Floor Zone 04 | 100 | 10-Feb-25 A
MOC.CN.F1.Z4.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 04 | 100 | 15-Feb-25 A
MOC.CN.F1.Z4.09.1740 | Plaster First Stage - First Floor Zone 04 | 100 | 15-Feb-25 A
MOC.CN.F1.Z4.09.1685 | Wooden Cladding First Fix - First Floor Zone 04 | 100 | 20-Apr-25 A
MOC.CN.F1.Z4.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 04 | 100 | 22-Apr-25 A
MOC.CN.F1.Z4.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1680 | Wooden Ceiling First Fix - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1745 | Plaster Second Stage - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1455 | First and Second painting coats - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.10.1785 | GLASS partiton - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1745[R] | Plaster Second Stage - First Floor Zone 04 [Remaining] | 100 | 14-Jun-25 A
MOC.CN.F1.Z4.09.1735 | Acoustic wall panel Installation - First Floor Zone 04 | 100 | 19-Jun-25 A
MOC.CN.F1.Z4.09.1680[R] | Wooden Ceiling First Fix - First Floor Zone 04 [Remaining] | 100 | 06-Jul-25 A
MOC.CN.F1.Z4.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 04 [Remaining] | 50 | 2025-08-12
MOC.CN.F1.Z4.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 04 | 0 | 2025-08-21
MOC.CN.F1.Z4.09.1455[R] | First and Second painting coats - First Floor Zone 04 [Remaining] | 45 | 2025-08-28
MOC.CN.F1.Z4.09.1725 | Wooden Cladding Second Fix - First Floor Zone 04 | 95 | 2025-09-01
MOC.CN.F1.Z4.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 04 | 20 | 2025-09-04
MOC.CN.F1.Z4.10.1785[R] | GLASS partiton - First Floor Zone 04 [Remaining] | 65 | 2025-09-04
MOC.CN.F1.Z4.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 04 | 0 | 2025-09-09
MOC.CN.F1.Z4.08.1430 | Doors Frame installation - First Floor Zone 04 | 0 | 2025-09-14
MOC.CN.F1.Z4.08.1400 | Wooden Doors installation - First Floor Zone 04 | 0 | 2025-09-21
MOC.CN.F1.Z4.10.2780 | Elevator Finishes - First Floor Zone 04 | 0 | 2025-09-22
MOC.CN.F1.Z4.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 04 | 0 | 2025-09-27
MOC.CN.F1.Z4.10.1775 | Signage works - First Floor Zone 04 | 0 | 2025-09-28
MOC.CN.F1.Z4.09.1460 | Final painting coat - First Floor Zone 04 | 0 | 2025-10-08
MOC.CN.F1.Z4.10.1795 | Curtain Installation - First Floor Zone 04 | 0 | 2025-10-15
MOC.CN.F1.Z4.05.1220 | Metal Handles for stairs - First Floor Zone 04 | 0 | 2025-10-20
MOC.CN.F1.Z4.09.1765 | Cornice Installation - First Floor Zone 04 | 0 | 2025-10-20
MOC.CN.F1.Z4.18.01 | Final Touch Up - First Floor Zone 04 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F1.Z4.FIN.FLR Flooring |  | 63.87 | 2025-10-16
MOC.CN.F1.Z4.09.1640 | Raised Floor First Fix - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1645 | Raised Floor Final fix installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.09.1640[R] | Raised Floor First Fix - First Floor Zone 04 [Remaining] | 60 | 2025-08-28
MOC.CN.F1.Z4.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 04 [Remaining] | 60 | 2025-09-01
MOC.CN.F1.Z4.09.1515 | Porcelain tiles for Flooring - First Floor Zone 04 | 0 | 2025-09-09
MOC.CN.F1.Z4.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 04 | 0 | 2025-09-29
MOC.CN.F1.Z4.09.1595 | Carpet Installation - First Floor Zone 04 | 60 | 2025-10-12
MOC.CN.F1.Z4.09.1690 | Skirting Installation - First Floor Zone 04 | 0 | 2025-10-16
MOC.REV.R06.U0200725.CON.F1.Z4.MEP MEP |  | 56.41 | 2025-10-13
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.MEC Mechanical |  | 69.83 | 2025-10-08
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.MEC.PL Plumbing |  | 74.99 | 2025-10-08
MOC.CN.F1.Z4.15.2420 | Water Supply pipes insulation - First Floor Zone 04 | 100 | 18-Apr-25 A
MOC.CN.F1.Z4.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 04 | 100 | 19-Apr-25 A
MOC.CN.F1.Z4.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 04 | 100 | 19-Apr-25 A
MOC.CN.F1.Z4.15.2295 | Drainage pipes installation & Testing - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2295[R] | Drainage pipes installation & Testing - First Floor Zone 04 [Remaining] | 80 | 2025-07-22
MOC.CN.F1.Z4.15.2315 | Floor Drain Installation - First Floor Zone 04 | 0 | 2025-10-08
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.MEC.FF Fire Fightig |  | 52.55 | 2025-09-25
MOC.CN.F1.Z4.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.1970 | Fire Fighting valves and accessories - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.1975 | Fire-hose cabinets installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.1955[R] | Fire Fighting pipes installation & Testing - First Floor Zone 04 [Remaining] | 80 | 2025-07-26
MOC.CN.F1.Z4.15.1970[R] | Fire Fighting valves and accessories - First Floor Zone 04 [Remaining] | 45 | 2025-07-31
MOC.CN.F1.Z4.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 04 [Remaining] | 0 | 2025-08-12
MOC.CN.F1.Z4.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 04 [Remaining] | 0 | 2025-09-03
MOC.CN.F1.Z4.15.1980 | Fire extinguishers installation - First Floor Zone 04 | 0 | 2025-09-14
MOC.CN.F1.Z4.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 04 | 0 | 2025-09-17
MOC.CN.F1.Z4.15.1985 | Fire sprinklers installation - First Floor Zone 04 | 0 | 2025-09-22
MOC.CN.F1.Z4.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 04 | 0 | 2025-09-25
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.MEC.HV HVAC |  | 75.3 | 2025-09-27
MOC.CN.F1.Z4.15.2340 | Fan Coil Units Installation - First Floor Zone 04 | 100 | 11-May-25 A
MOC.CN.F1.Z4.15.2275 | Thermostat Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2320 | Air Handling pipes installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2280 | Variable Air Volume (VAV) - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2380 | Duct Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2385 | Duct Insulation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2375 | HVAC Pipes Insulation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2390 | Duct Lining - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2280[R] | Variable Air Volume (VAV) - First Floor Zone 04 [Remaining] | 100 | 31-May-25 A
MOC.CN.F1.Z4.15.2370[R] | HVAC Pipes Installation & Testing - First Floor Zone 04 [Remaining] | 85 | 2025-07-21
MOC.CN.F1.Z4.15.2380[R] | Duct Installation - First Floor Zone 04 [Remaining] | 85 | 2025-07-23
MOC.CN.F1.Z4.15.2375[R] | HVAC Pipes Insulation - First Floor Zone 04 [Remaining] | 40 | 2025-07-26
MOC.CN.F1.Z4.15.2385[R] | Duct Insulation - First Floor Zone 04 [Remaining] | 40 | 2025-07-30
MOC.CN.F1.Z4.15.2390[R] | Duct Lining - First Floor Zone 04 [Remaining] | 40 | 2025-08-04
MOC.CN.F1.Z4.15.2395 | HVAC Valves installation - First Floor Zone 04 | 0 | 2025-08-06
MOC.CN.F1.Z4.15.2320[R] | Air Handling pipes installation - First Floor Zone 04 [Remaining] | 0 | 2025-08-09
MOC.CN.F1.Z4.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 04 | 0 | 2025-08-26
MOC.CN.F1.Z4.15.2325 | Air Handling units installation - First Floor Zone 04 | 0 | 2025-09-27
MOC.CN.F1.Z4.15.2100 | Air Diffusers Installation - First Floor Zone 04 | 0 | 2025-09-27
MOC.CN.F1.Z4.15.2275[R] | Thermostat Installation - First Floor Zone 04 [Remaining] | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL Electrical |  | 52.05 | 2025-10-13
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.EP Electrical Power |  | 53.04 | 2025-10-13
MOC.CN.F1.Z4.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2655 | Conduits and boxes installation - First Floor Zone 04 | 100 | 10-May-25 A
MOC.CN.F1.Z4.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2630 | Cables & Wiring Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2745 | Wiring Installation in floors - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 04 [Remaining] | 75 | 2025-07-24
MOC.CN.F1.Z4.16.2630[R] | Cables & Wiring Installation - First Floor Zone 04 [Remaining] | 50 | 2025-07-30
MOC.CN.F1.Z4.16.2745[R] | Wiring Installation in floors - First Floor Zone 04 [Remaining] | 40 | 2025-08-06
MOC.CN.F1.Z4.16.2625 | Earthing System installation - First Floor Zone 04 | 0 | 2025-08-23
MOC.CN.F1.Z4.16.2715 | Distribution board installation - First Floor Zone 04 | 0 | 2025-09-15
MOC.CN.F1.Z4.16.2495 | Sockets and Switches installation - First Floor Zone 04 | 0 | 2025-09-27
MOC.CN.F1.Z4.16.2490 | Lighting fixtures installation - First Floor Zone 04 | 0 | 2025-09-28
MOC.CN.F1.Z4.16.2750 | Floor Sockets Installation - First Floor Zone 04 | 0 | 2025-10-13
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.AV Audio Visual |  | 51.5 | 2025-09-28
MOC.CN.F1.Z4.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 04 [Remaining] | 30 | 2025-08-17
MOC.CN.F1.Z4.16.2515 | Audiovisual system installation - First Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.LC Lighting Control |  | 72.74 | 2025-09-27
MOC.CN.F1.Z4.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2710 | Lighting Control Wiring Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2710[R] | Lighting Control Wiring Installation - First Floor Zone 04 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.F1.Z4.16.2660 | Lighting Control System installation - First Floor Zone 04 | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.T&D Telecommunication & Data System |  | 66.08 | 2025-09-28
MOC.CN.F1.Z4.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 04 [Remaining] | 65 | 2025-08-21
MOC.CN.F1.Z4.16.2505 | Telecommunication and Data system installation - First Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.SS Security System |  | 3.7 | 2025-09-29
MOC.CN.F1.Z4.16.2670 | Security System Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2695 | Security System Wiring Installation - First Floor Zone 04 | 60 | 2025-07-27
MOC.CN.F1.Z4.16.2640 | Security System Installation - First Floor Zone 04 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-27
MOC.CN.F1.Z4.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2700 | IPTV System Wiring Installation - First Floor Zone 04 | 0 | 2025-08-05
MOC.CN.F1.Z4.16.2645 | IPTV System installation - First Floor Zone 04 | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.98 | 2025-09-30
MOC.CN.F1.Z4.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 04 [Remaining] | 100 | 23-Jun-25 A
MOC.CN.F1.Z4.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 04 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.PA Public Address System |  | 40 | 2025-09-30
MOC.CN.F1.Z4.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2730 | Public Address System Wiring Installation - First Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F1.Z4.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 04 [Remaining] | 0 | 2025-08-19
MOC.CN.F1.Z4.16.2525 | Public Address System installation - First Floor Zone 04 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F1.Z4.MEP.EL.CBS Central Battery |  | 100 | 25-Jun-25 A
MOC.CN.F1.Z4.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 04 | 100 | 04-May-25 A
MOC.CN.F1.Z4.16.2690 | Central Battery System Wiring Installation - First Floor Zone 04 | 100 | 25-Jun-25 A
MOC.REV.R06.U0200725.CON.F1.Z5 Zone 05 |  | 84.64 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z5.FIN Finishes |  | 96.75 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z5.FIN.C&W Ceiling & Walls |  | 95.67 | 2025-07-23
MOC.CN.F1.Z5.04.1175 | Masonary works - First Floor Zone 05 | 100 | 10-Feb-25 A
MOC.CN.F1.Z5.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 05 | 100 | 15-Feb-25 A
MOC.CN.F1.Z5.09.1740 | Plaster First Stage - First Floor Zone 05 | 100 | 18-Feb-25 A
MOC.CN.F1.Z5.09.1745 | Plaster Second Stage - First Floor Zone 05 | 100 | 08-Apr-25 A
MOC.CN.F1.Z5.09.1685 | Wooden Cladding First Fix - First Floor Zone 05 | 100 | 19-Apr-25 A
MOC.CN.F1.Z5.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 05 | 100 | 22-Apr-25 A
MOC.CN.F1.Z5.09.1680 | Wooden Ceiling First Fix - First Floor Zone 05 | 100 | 19-May-25 A
MOC.CN.F1.Z5.09.1725 | Wooden Cladding Second Fix - First Floor Zone 05 | 100 | 21-May-25 A
MOC.CN.F1.Z5.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1455 | First and Second painting coats - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.10.1785 | GLASS partiton - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1670[R] | Acoustic Ceiling First Fix - First Floor Zone 05 [Remaining] | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 05 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.F1.Z5.09.1735 | Acoustic wall panel Installation - First Floor Zone 05 | 100 | 19-Jun-25 A
MOC.CN.F1.Z5.09.1455[R] | First and Second painting coats - First Floor Zone 05 [Remaining] | 100 | 25-Jun-25 A
MOC.CN.F1.Z5.09.1720[R] | Wooden Ceiling Second Fix - First Floor Zone 05 [Remaining] | 100 | 26-Jun-25 A
MOC.CN.F1.Z5.10.1785[R] | GLASS partiton - First Floor Zone 05 [Remaining] | 100 | 26-Jun-25 A
MOC.CN.F1.Z5.09.1705[R] | Gypsum Board Ceiling Second Fix - First Floor Zone 05 [Remaining] | 100 | 29-Jun-25 A
MOC.CN.F1.Z5.09.1765 | Cornice Installation - First Floor Zone 05 | 100 | 01-Jul-25 A
MOC.CN.F1.Z5.10.1775 | Signage works - First Floor Zone 05 | 100 | 01-Jul-25 A
MOC.CN.F1.Z5.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 05 | 100 | 03-Jul-25 A
MOC.CN.F1.Z5.08.1430 | Doors Frame installation - First Floor Zone 05 | 95 | 2025-07-21
MOC.CN.F1.Z5.08.1400 | Wooden Doors installation - First Floor Zone 05 | 95 | 2025-07-21
MOC.CN.F1.Z5.09.1460 | Final painting coat - First Floor Zone 05 | 90 | 2025-07-21
MOC.CN.F1.Z5.05.1220 | Metal Handles for stairs - First Floor Zone 05 | 0 | 2025-07-22
MOC.CN.F1.Z5.10.1795 | Curtain Installation - First Floor Zone 05 | 50 | 2025-07-22
MOC.CN.F1.Z5.18.01 | Final Touch Up - First Floor Zone 05 | 40 | 2025-07-22
MOC.CN.F1.Z5.10.2780 | Elevator Finishes - First Floor Zone 05 | 25 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z5.FIN.FLR Flooring |  | 100 | 02-Jul-25 A
MOC.CN.F1.Z5.09.1640 | Raised Floor First Fix - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1645 | Raised Floor Final fix installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.09.1640[R] | Raised Floor First Fix - First Floor Zone 05 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.F1.Z5.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 05 [Remaining] | 100 | 25-Jun-25 A
MOC.CN.F1.Z5.09.1515 | Porcelain tiles for Flooring - First Floor Zone 05 | 100 | 26-Jun-25 A
MOC.CN.F1.Z5.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 05 | 100 | 26-Jun-25 A
MOC.CN.F1.Z5.09.1595 | Carpet Installation - First Floor Zone 05 | 100 | 01-Jul-25 A
MOC.CN.F1.Z5.09.1690 | Skirting Installation - First Floor Zone 05 | 100 | 02-Jul-25 A
MOC.REV.R06.U0200725.CON.F1.Z5.MEP MEP |  | 75.77 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.MEC Mechanical |  | 99.7 | 2025-07-22
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.MEC.PL Plumbing |  | 100 | 13-Jun-25 A
MOC.CN.F1.Z5.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 05 | 100 | 16-Apr-25 A
MOC.CN.F1.Z5.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 05 | 100 | 17-Apr-25 A
MOC.CN.F1.Z5.15.2420 | Water Supply pipes insulation - First Floor Zone 05 | 100 | 17-Apr-25 A
MOC.CN.F1.Z5.15.2295 | Drainage pipes installation & Testing - First Floor Zone 05 | 100 | 26-May-25 A
MOC.CN.F1.Z5.15.2315 | Floor Drain Installation - First Floor Zone 05 | 100 | 13-Jun-25 A
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.MEC.FF Fire Fightig |  | 98.72 | 2025-07-22
MOC.CN.F1.Z5.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.F1.Z5.15.1970 | Fire Fighting valves and accessories - First Floor Zone 05 | 100 | 04-May-25 A
MOC.CN.F1.Z5.15.1975 | Fire-hose cabinets installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 05 [Remaining] | 100 | 09-Jun-25 A
MOC.CN.F1.Z5.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 05 | 100 | 15-Jun-25 A
MOC.CN.F1.Z5.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 05 | 100 | 30-Jun-25 A
MOC.CN.F1.Z5.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 05 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F1.Z5.15.1985 | Fire sprinklers installation - First Floor Zone 05 | 100 | 05-Jul-25 A
MOC.CN.F1.Z5.15.1980 | Fire extinguishers installation - First Floor Zone 05 | 0 | 2025-07-22
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.MEC.HV HVAC |  | 100 | 06-Jul-25 A
MOC.CN.F1.Z5.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.F1.Z5.15.2375 | HVAC Pipes Insulation - First Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.F1.Z5.15.2395 | HVAC Valves installation - First Floor Zone 05 | 100 | 02-May-25 A
MOC.CN.F1.Z5.15.2340 | Fan Coil Units Installation - First Floor Zone 05 | 100 | 03-May-25 A
MOC.CN.F1.Z5.15.2380 | Duct Installation - First Floor Zone 05 | 100 | 04-May-25 A
MOC.CN.F1.Z5.15.2385 | Duct Insulation - First Floor Zone 05 | 100 | 04-May-25 A
MOC.CN.F1.Z5.15.2390 | Duct Lining - First Floor Zone 05 | 100 | 04-May-25 A
MOC.CN.F1.Z5.15.2280 | Variable Air Volume (VAV) - First Floor Zone 05 | 100 | 13-May-25 A
MOC.CN.F1.Z5.15.2275 | Thermostat Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.15.2320 | Air Handling pipes installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.15.2320[R] | Air Handling pipes installation - First Floor Zone 05 [Remaining] | 100 | 02-Jul-25 A
MOC.CN.F1.Z5.15.2100 | Air Diffusers Installation - First Floor Zone 05 | 100 | 02-Jul-25 A
MOC.CN.F1.Z5.15.2275[R] | Thermostat Installation - First Floor Zone 05 [Remaining] | 100 | 02-Jul-25 A
MOC.CN.F1.Z5.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 05 | 100 | 03-Jul-25 A
MOC.CN.F1.Z5.15.2325 | Air Handling units installation - First Floor Zone 05 | 100 | 06-Jul-25 A
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL Electrical |  | 67.96 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.EP Electrical Power |  | 68.98 | 2025-07-22
MOC.CN.F1.Z5.16.2655 | Conduits and boxes installation - First Floor Zone 05 | 100 | 21-Apr-25 A
MOC.CN.F1.Z5.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 05 | 100 | 21-Apr-25 A
MOC.CN.F1.Z5.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2630 | Cables & Wiring Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2745 | Wiring Installation in floors - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 05 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.F1.Z5.16.2630[R] | Cables & Wiring Installation - First Floor Zone 05 [Remaining] | 100 | 21-Jun-25 A
MOC.CN.F1.Z5.16.2745[R] | Wiring Installation in floors - First Floor Zone 05 [Remaining] | 100 | 21-Jun-25 A
MOC.CN.F1.Z5.16.2715 | Distribution board installation - First Floor Zone 05 | 100 | 28-Jun-25 A
MOC.CN.F1.Z5.16.2495 | Sockets and Switches installation - First Floor Zone 05 | 100 | 01-Jul-25 A
MOC.CN.F1.Z5.16.2490 | Lighting fixtures installation - First Floor Zone 05 | 0 | 2025-07-22
MOC.CN.F1.Z5.16.2750 | Floor Sockets Installation - First Floor Zone 05 | 0 | 2025-07-22
MOC.CN.F1.Z5.16.2625 | Earthing System installation - First Floor Zone 05 | 0 | 2025-07-22
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.AV Audio Visual |  | 66.08 | 2025-07-28
MOC.CN.F1.Z5.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 05 | 100 | 19-Apr-25 A
MOC.CN.F1.Z5.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 05 [Remaining] | 95 | 2025-07-21
MOC.CN.F1.Z5.16.2515 | Audiovisual system installation - First Floor Zone 05 | 0 | 2025-07-28
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.LC Lighting Control |  | 72.74 | 2025-07-29
MOC.CN.F1.Z5.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 05 | 100 | 20-Apr-25 A
MOC.CN.F1.Z5.16.2710 | Lighting Control Wiring Installation - First Floor Zone 05 | 100 | 20-Apr-25 A
MOC.CN.F1.Z5.16.2660 | Lighting Control System installation - First Floor Zone 05 | 0 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.T&D Telecommunication & Data System |  | 67.65 | 2025-07-27
MOC.CN.F1.Z5.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 05 | 100 | 19-Apr-25 A
MOC.CN.F1.Z5.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 05 [Remaining] | 100 | 24-Jun-25 A
MOC.CN.F1.Z5.16.2505 | Telecommunication and Data system installation - First Floor Zone 05 | 0 | 2025-07-27
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.SS Security System |  | 4.63 | 2025-07-27
MOC.CN.F1.Z5.16.2670 | Security System Conduits and boxes installation - First Floor Zone 05 | 100 | 20-Apr-25 A
MOC.CN.F1.Z5.16.2695 | Security System Wiring Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2695[R] | Security System Wiring Installation - First Floor Zone 05 [Remaining] | 100 | 19-Jun-25 A
MOC.CN.F1.Z5.16.2640 | Security System Installation - First Floor Zone 05 | 0 | 2025-07-27
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.IPTV IPTV System |  | 66.67 | 2025-07-28
MOC.CN.F1.Z5.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 05 | 100 | 21-Apr-25 A
MOC.CN.F1.Z5.16.2700 | IPTV System Wiring Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2700[R] | IPTV System Wiring Installation - First Floor Zone 05 [Remaining] | 100 | 18-Jun-25 A
MOC.CN.F1.Z5.16.2645 | IPTV System installation - First Floor Zone 05 | 0 | 2025-07-28
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 100 | 02-Jul-25 A
MOC.CN.F1.Z5.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 05 | 100 | 08-Apr-25 A
MOC.CN.F1.Z5.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 05 | 100 | 13-Apr-25 A
MOC.CN.F1.Z5.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 05 | 100 | 02-Jul-25 A
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.PA Public Address System |  | 66.67 | 2025-07-27
MOC.CN.F1.Z5.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 05 | 100 | 20-Apr-25 A
MOC.CN.F1.Z5.16.2730 | Public Address System Wiring Installation - First Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F1.Z5.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 05 [Remaining] | 100 | 18-Jun-25 A
MOC.CN.F1.Z5.16.2525 | Public Address System installation - First Floor Zone 05 | 0 | 2025-07-27
MOC.REV.R06.U0200725.CON.F1.Z5.MEP.EL.CBS Central Battery |  | 100 | 21-Apr-25 A
MOC.CN.F1.Z5.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 05 | 100 | 19-Apr-25 A
MOC.CN.F1.Z5.16.2690 | Central Battery System Wiring Installation - First Floor Zone 05 | 100 | 21-Apr-25 A
MOC.REV.R06.U0200725.CON.F1.Z6 Zone 06 |  | 77.59 | 2025-08-09
MOC.REV.R06.U0200725.CON.F1.Z6.FIN Finishes |  | 84.91 | 2025-07-24
MOC.REV.R06.U0200725.CON.F1.Z6.FIN.C&W Ceiling & Walls |  | 85.79 | 2025-07-24
MOC.CN.F1.Z6.04.1175 | Masonary works - First Floor Zone 06 | 100 | 10-Feb-25 A
MOC.CN.F1.Z6.09.1750 | Gypsum Board Partitions First Fix - First Floor Zone 06 | 100 | 16-Feb-25 A
MOC.CN.F1.Z6.09.1740 | Plaster First Stage - First Floor Zone 06 | 100 | 18-Feb-25 A
MOC.CN.F1.Z6.09.1745 | Plaster Second Stage - First Floor Zone 06 | 100 | 08-Apr-25 A
MOC.CN.F1.Z6.09.1685 | Wooden Cladding First Fix - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.09.1755 | Gypsum Board Partitions Second Fix - First Floor Zone 06 | 100 | 22-Apr-25 A
MOC.CN.F1.Z6.09.1680 | Wooden Ceiling First Fix - First Floor Zone 06 | 100 | 19-May-25 A
MOC.CN.F1.Z6.09.1725 | Wooden Cladding Second Fix - First Floor Zone 06 | 100 | 26-May-25 A
MOC.CN.F1.Z6.09.1700 | Gypsum Board Ceiling First Fix - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1670 | Acoustic Ceiling First Fix - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1720 | Wooden Ceiling Second Fix - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1455 | First and Second painting coats - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.10.1785 | GLASS partiton - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1670[R] | Acoustic Ceiling First Fix - First Floor Zone 06 [Remaining] | 100 | 07-Jun-25 A
MOC.CN.F1.Z6.09.1735 | Acoustic wall panel Installation - First Floor Zone 06 | 100 | 21-Jun-25 A
MOC.CN.F1.Z6.09.1455[R] | First and Second painting coats - First Floor Zone 06 [Remaining] | 100 | 29-Jun-25 A
MOC.CN.F1.Z6.09.1700[R] | Gypsum Board Ceiling First Fix - First Floor Zone 06 [Remaining] | 100 | 03-Jul-25 A
MOC.CN.F1.Z6.09.1705[R] | Gypsum Board Ceiling Second Fix - First Floor Zone 06 [Remaining] | 100 | 06-Jul-25 A
MOC.CN.F1.Z6.09.1720[R] | Wooden Ceiling Second Fix - First Floor Zone 06 [Remaining] | 100 | 08-Jul-25 A
MOC.CN.F1.Z6.10.1785[R] | GLASS partiton - First Floor Zone 06 [Remaining] | 100 | 10-Jul-25 A
MOC.CN.F1.Z6.08.1430 | Doors Frame installation - First Floor Zone 06 | 75 | 2025-07-21
MOC.CN.F1.Z6.08.1400 | Wooden Doors installation - First Floor Zone 06 | 75 | 2025-07-21
MOC.CN.F1.Z6.09.1460 | Final painting coat - First Floor Zone 06 | 25 | 2025-07-22
MOC.CN.F1.Z6.09.1765 | Cornice Installation - First Floor Zone 06 | 35 | 2025-07-22
MOC.CN.F1.Z6.09.1730 | Acoustic Ceiling Second Fix - First Floor Zone 06 | 0 | 2025-07-22
MOC.CN.F1.Z6.10.2780 | Elevator Finishes - First Floor Zone 06 | 0 | 2025-07-22
MOC.CN.F1.Z6.10.1775 | Signage works - First Floor Zone 06 | 20 | 2025-07-23
MOC.CN.F1.Z6.10.1795 | Curtain Installation - First Floor Zone 06 | 0 | 2025-07-23
MOC.CN.F1.Z6.05.1220 | Metal Handles for stairs - First Floor Zone 06 | 0 | 2025-07-24
MOC.CN.F1.Z6.18.01 | Final Touch Up - First Floor Zone 06 | 0 | 2025-07-24
MOC.REV.R06.U0200725.CON.F1.Z6.FIN.FLR Flooring |  | 82.39 | 2025-07-22
MOC.CN.F1.Z6.09.1640 | Raised Floor First Fix - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1645 | Raised Floor Final fix installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.09.1640[R] | Raised Floor First Fix - First Floor Zone 06 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.F1.Z6.09.1645[R] | Raised Floor Final fix installation - First Floor Zone 06 [Remaining] | 100 | 25-Jun-25 A
MOC.CN.F1.Z6.09.1515 | Porcelain tiles for Flooring - First Floor Zone 06 | 100 | 28-Jun-25 A
MOC.CN.F1.Z6.09.1490 | Ceramic tiles for Flooring works - First Floor Zone 06 | 100 | 28-Jun-25 A
MOC.CN.F1.Z6.09.1595 | Carpet Installation - First Floor Zone 06 | 85 | 2025-07-22
MOC.CN.F1.Z6.09.1690 | Skirting Installation - First Floor Zone 06 | 0 | 2025-07-22
MOC.REV.R06.U0200725.CON.F1.Z6.MEP MEP |  | 72.14 | 2025-08-09
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.MEC Mechanical |  | 95.61 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.MEC.PL Plumbing |  | 100 | 02-Jul-25 A
MOC.CN.F1.Z6.15.2305 | Water Supply pipes installation & Testing - First Floor Zone 06 | 100 | 16-Apr-25 A
MOC.CN.F1.Z6.15.2420 | Water Supply pipes insulation - First Floor Zone 06 | 100 | 17-Apr-25 A
MOC.CN.F1.Z6.15.1915 | Valves and accessories for Water Supply System - First Floor Zone 06 | 100 | 18-Apr-25 A
MOC.CN.F1.Z6.15.2295 | Drainage pipes installation & Testing - First Floor Zone 06 | 100 | 24-May-25 A
MOC.CN.F1.Z6.15.2315 | Floor Drain Installation - First Floor Zone 06 | 100 | 02-Jul-25 A
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.MEC.FF Fire Fightig |  | 95.93 | 2025-07-22
MOC.CN.F1.Z6.15.1955 | Fire Fighting pipes installation & Testing - First Floor Zone 06 | 100 | 01-May-25 A
MOC.CN.F1.Z6.15.1970 | Fire Fighting valves and accessories - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.1975 | Fire-hose cabinets installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.15.2245 | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - First Floor Zone 06 [Remaining] | 100 | 19-Jun-25 A
MOC.CN.F1.Z6.15.2250 | NOVEC 1230 - Cylinders installation - First Floor Zone 06 | 100 | 22-Jun-25 A
MOC.CN.F1.Z6.15.2255 | NOVEC 1230 - Nozzles installation - First Floor Zone 06 | 100 | 07-Jul-25 A
MOC.CN.F1.Z6.15.1975[R] | Fire-hose cabinets installation - First Floor Zone 06 [Remaining] | 100 | 07-Jul-25 A
MOC.CN.F1.Z6.15.1985 | Fire sprinklers installation - First Floor Zone 06 | 75 | 2025-07-21
MOC.CN.F1.Z6.15.1980 | Fire extinguishers installation - First Floor Zone 06 | 0 | 2025-07-22
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.MEC.HV HVAC |  | 95.31 | 2025-07-23
MOC.CN.F1.Z6.15.2370 | HVAC Pipes Installation & Testing - First Floor Zone 06 | 100 | 01-May-25 A
MOC.CN.F1.Z6.15.2375 | HVAC Pipes Insulation - First Floor Zone 06 | 100 | 03-May-25 A
MOC.CN.F1.Z6.15.2340 | Fan Coil Units Installation - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.2380 | Duct Installation - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.2395 | HVAC Valves installation - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.2385 | Duct Insulation - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.2390 | Duct Lining - First Floor Zone 06 | 100 | 04-May-25 A
MOC.CN.F1.Z6.15.2280 | Variable Air Volume (VAV) - First Floor Zone 06 | 100 | 13-May-25 A
MOC.CN.F1.Z6.15.2275 | Thermostat Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.15.2320 | Air Handling pipes installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.15.2275[R] | Thermostat Installation - First Floor Zone 06 [Remaining] | 100 | 23-Jun-25 A
MOC.CN.F1.Z6.15.2755 | Air Handling Unit Valves Installation - First Floor Zone 06 | 100 | 07-Jul-25 A
MOC.CN.F1.Z6.15.2320[R] | Air Handling pipes installation - First Floor Zone 06 [Remaining] | 100 | 07-Jul-25 A
MOC.CN.F1.Z6.15.2100 | Air Diffusers Installation - First Floor Zone 06 | 60 | 2025-07-21
MOC.CN.F1.Z6.15.2325 | Air Handling units installation - First Floor Zone 06 | 65 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL Electrical |  | 64.56 | 2025-08-09
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.EP Electrical Power |  | 68.36 | 2025-07-23
MOC.CN.F1.Z6.16.2460 | Installing electrical conduits and boxes in floors - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2655 | Conduits and boxes installation - First Floor Zone 06 | 100 | 21-Apr-25 A
MOC.CN.F1.Z6.16.2610 | Cable Trays & Trunks Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2630 | Cables & Wiring Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2745 | Wiring Installation in floors - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2610[R] | Cable Trays & Trunks Installation - First Floor Zone 06 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.F1.Z6.16.2630[R] | Cables & Wiring Installation - First Floor Zone 06 [Remaining] | 100 | 17-Jun-25 A
MOC.CN.F1.Z6.16.2745[R] | Wiring Installation in floors - First Floor Zone 06 [Remaining] | 100 | 18-Jun-25 A
MOC.CN.F1.Z6.16.2715 | Distribution board installation - First Floor Zone 06 | 100 | 26-Jun-25 A
MOC.CN.F1.Z6.16.2495 | Sockets and Switches installation - First Floor Zone 06 | 50 | 2025-07-21
MOC.CN.F1.Z6.16.2625 | Earthing System installation - First Floor Zone 06 | 0 | 2025-07-22
MOC.CN.F1.Z6.16.2750 | Floor Sockets Installation - First Floor Zone 06 | 0 | 2025-07-23
MOC.CN.F1.Z6.16.2490 | Lighting fixtures installation - First Floor Zone 06 | 0 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.AV Audio Visual |  | 66.67 | 2025-07-28
MOC.CN.F1.Z6.16.2735 | Audiovisual system Conduits and boxes installation - First Floor Zone 06 | 100 | 19-Apr-25 A
MOC.CN.F1.Z6.16.2740 | Audiovisual system Wiring Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2740[R] | Audiovisual system Wiring Installation - First Floor Zone 06 [Remaining] | 100 | 30-Jun-25 A
MOC.CN.F1.Z6.16.2515 | Audiovisual system installation - First Floor Zone 06 | 0 | 2025-07-28
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.LC Lighting Control |  | 72.74 | 2025-07-29
MOC.CN.F1.Z6.16.2685 | Lighting Control Conduits and boxes installation - First Floor Zone 06 | 100 | 17-Apr-25 A
MOC.CN.F1.Z6.16.2710 | Lighting Control Wiring Installation - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2660 | Lighting Control System installation - First Floor Zone 06 | 0 | 2025-07-29
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-08-09
MOC.CN.F1.Z6.16.2720 | Telecommunication & Data System Conduits and boxes installation - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2200 | Telecommunication and Data Cables installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2200[R] | Telecommunication and Data Cables installation - First Floor Zone 06 [Remaining] | 0 | 2025-08-02
MOC.CN.F1.Z6.16.2505 | Telecommunication and Data system installation - First Floor Zone 06 | 0 | 2025-08-09
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.SS Security System |  | 3.01 | 2025-08-07
MOC.CN.F1.Z6.16.2670 | Security System Conduits and boxes installation - First Floor Zone 06 | 100 | 19-Apr-25 A
MOC.CN.F1.Z6.16.2695 | Security System Wiring Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2695[R] | Security System Wiring Installation - First Floor Zone 06 [Remaining] | 0 | 2025-07-31
MOC.CN.F1.Z6.16.2640 | Security System Installation - First Floor Zone 06 | 0 | 2025-08-07
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.IPTV IPTV System |  | 66.67 | 2025-08-03
MOC.CN.F1.Z6.16.2675 | IPTV System Conduits and boxes installation - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2700 | IPTV System Wiring Installation - First Floor Zone 06 | 100 | 12-May-25 A
MOC.CN.F1.Z6.16.2645 | IPTV System installation - First Floor Zone 06 | 0 | 2025-08-03
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.98 | 2025-07-23
MOC.CN.F1.Z6.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - First Floor Zone 06 | 100 | 08-Apr-25 A
MOC.CN.F1.Z6.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - First Floor Zone 06 | 100 | 13-Apr-25 A
MOC.CN.F1.Z6.16.2650 | Fire Alarm & Voice Evacuation System Installation - First Floor Zone 06 | 0 | 2025-07-23
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.PA Public Address System |  | 43.33 | 2025-08-07
MOC.CN.F1.Z6.16.2725 | Public Address System Conduits and boxes installation - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2730 | Public Address System Wiring Installation - First Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F1.Z6.16.2730[R] | Public Address System Wiring Installation - First Floor Zone 06 [Remaining] | 0 | 2025-07-31
MOC.CN.F1.Z6.16.2525 | Public Address System installation - First Floor Zone 06 | 0 | 2025-08-07
MOC.REV.R06.U0200725.CON.F1.Z6.MEP.EL.CBS Central Battery |  | 100 | 21-Apr-25 A
MOC.CN.F1.Z6.16.2665 | Central Battery System Conduits and boxes installation - First Floor Zone 06 | 100 | 20-Apr-25 A
MOC.CN.F1.Z6.16.2690 | Central Battery System Wiring Installation - First Floor Zone 06 | 100 | 21-Apr-25 A
MOC.REV.R06.U0200725.CON.F1.WT Wet Areas |  | 63.79 | 2025-09-15
MOC.REV.R06.U0200725.CON.F1.WT.FIN Finishes |  | 63.64 | 2025-09-13
MOC.REV.R06.U0200725.CON.F1.WT.FIN.C&W Ceiling & Walls |  | 75.72 | 2025-09-13
MOC.CN.F1.WT.04.1175 | Masonary works - First Floor Wet Areas | 100 | 10-Feb-25 A
MOC.CN.F1.WT.09.1740 | Plaster First Stage - First Floor Wet Areas | 100 | 09-Mar-25 A
MOC.CN.F1.WT.09.1745 | Plaster Second Stage - First Floor Wet Areas | 100 | 08-Apr-25 A
MOC.CN.F1.WT.09.1455 | First and Second painting coats - First Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F1.WT.09.1665 | Porcelain tiles for walls - First Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F1.WT.08.1430 | Doors Frame installation - First Floor Wet Areas | 30 | 2025-07-28
MOC.CN.F1.WT.09.1700 | Gypsum Board Ceiling First Fix - First Floor Wet Areas | 0 | 2025-07-31
MOC.CN.F1.WT.09.1665[R] | Porcelain tiles for walls - First Floor Wet Areas [Remaining] | 85 | 2025-08-07
MOC.CN.F1.WT.09.1705 | Gypsum Board Ceiling Second Fix - First Floor Wet Areas | 0 | 2025-08-21
MOC.CN.F1.WT.09.1455[R] | First and Second painting coats - First Floor Wet Areas [Remaining] | 0 | 2025-08-27
MOC.CN.F1.WT.10.1790 | HPL partition installation - First Floor Wet Areas | 30 | 2025-08-28
MOC.CN.F1.WT.08.1400 | Wooden Doors installation - First Floor Wet Areas | 30 | 2025-09-03
MOC.CN.F1.WT.10.1775 | Signage works - First Floor Wet Areas | 0 | 2025-09-09
MOC.CN.F1.WT.09.1460 | Final painting coat - First Floor Wet Areas | 0 | 2025-09-13
MOC.REV.R06.U0200725.CON.F1.WT.FIN.FLR Flooring |  | 27.41 | 2025-09-10
MOC.CN.F1.WT.07.1330 | Water proofing for wet areas - First Floor Wet Areas | 100 | 19-May-25 A
MOC.CN.F1.WT.09.1515 | Porcelain tiles for Flooring - First Floor Wet Areas | 30 | 2025-08-14
MOC.CN.F1.WT.10.1770 | Toilet Accessories and Fixtures Installation - First Floor Wet Areas | 0 | 2025-09-10
MOC.REV.R06.U0200725.CON.F1.WT.MEP MEP |  | 63.88 | 2025-09-15
MOC.REV.R06.U0200725.CON.F1.WT.MEP.PL Plumbing |  | 63.67 | 2025-09-15
MOC.CN.F1.WT.15.2305 | Water Supply pipes installation & Testing - First Floor Wet Areas | 100 | 01-Apr-25 A
MOC.CN.F1.WT.15.2420 | Water Supply pipes insulation - First Floor Wet Areas | 100 | 10-Apr-25 A
MOC.CN.F1.WT.15.2295 | Drainage pipes installation & Testing - First Floor Wet Areas | 100 | 11-May-25 A
MOC.CN.F1.WT.15.1915 | Valves and accessories for Water Supply System - First Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F1.WT.15.1945 | Plumbing Fixtures Installations - First Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F1.WT.15.1915[R] | Valves and accessories for Water Supply System - First Floor Wet Areas [Remaining] | 100 | 09-Jun-25 A
MOC.CN.F1.WT.15.1925 | Electrical water heater - First Floor Wet Areas | 100 | 03-Jul-25 A
MOC.CN.F1.WT.15.2315 | Floor Drain Installation - First Floor Wet Areas | 30 | 2025-08-23
MOC.CN.F1.WT.15.1945[R] | Plumbing Fixtures Installations - First Floor Wet Areas [Remaining] | 30 | 2025-09-15
MOC.REV.R06.U0200725.CON.F1.WT.MEP.EL Electrical |  | 67.29 | 2025-09-10
MOC.REV.R06.U0200725.CON.F1.WT.MEP.EL.EP Electrical Power |  | 67.29 | 2025-09-10
MOC.CN.F1.WT.16.2655 | Conduits and boxes installation - First Floor Wet Areas | 100 | 20-Apr-25 A
MOC.CN.F1.WT.16.2630 | Cables & Wiring Installation - First Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F1.WT.16.2630[R] | Cables & Wiring Installation - First Floor Wet Areas [Remaining] | 85 | 2025-07-21
MOC.CN.F1.WT.16.2490 | Lighting fixtures installation - First Floor Wet Areas | 0 | 2025-09-10
MOC.REV.R06.U0200725.CON.F2 Second Floor |  | 36.65 | 2025-11-05
MOC.REV.R06.U0200725.CON.F2.Z1 Zone 01 |  | 39.92 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z1.FIN Finishes |  | 25.59 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z1.FIN.C&W Ceiling & Walls |  | 22.4 | 2025-10-23
MOC.CN.F2.Z1.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 01 | 100 | 27-Mar-25 A
MOC.CN.F2.Z1.04.1175 | Masonary works - Second Floor Zone 01 | 100 | 31-Mar-25 A
MOC.CN.F2.Z1.09.1740 | Plaster First Stage - Second Floor Zone 01 | 100 | 09-Apr-25 A
MOC.CN.F2.Z1.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.09.1745 | Plaster Second Stage - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.09.1455 | First and Second painting coats - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z1.09.1745[R] | Plaster Second Stage - Second Floor Zone 01 [Remaining] | 90 | 2025-07-24
MOC.CN.F2.Z1.09.1685 | Wooden Cladding First Fix - Second Floor Zone 01 | 75 | 2025-08-12
MOC.CN.F2.Z1.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 01 | 0 | 2025-08-17
MOC.CN.F2.Z1.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 01 | 10 | 2025-08-21
MOC.CN.F2.Z1.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 01 | 0 | 2025-08-28
MOC.CN.F2.Z1.08.1430 | Doors Frame installation - Second Floor Zone 01 | 0 | 2025-09-04
MOC.CN.F2.Z1.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 01 | 0 | 2025-09-09
MOC.CN.F2.Z1.08.1400 | Wooden Doors installation - Second Floor Zone 01 | 0 | 2025-09-11
MOC.CN.F2.Z1.09.1455[R] | First and Second painting coats - Second Floor Zone 01 [Remaining] | 45 | 2025-09-13
MOC.CN.F2.Z1.09.1765 | Cornice Installation - Second Floor Zone 01 | 0 | 2025-09-21
MOC.CN.F2.Z1.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F2.Z1.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F2.Z1.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 01 | 0 | 2025-09-25
MOC.CN.F2.Z1.10.1775 | Signage works - Second Floor Zone 01 | 0 | 2025-09-28
MOC.CN.F2.Z1.10.2780 | Elevator Finishes - Second Floor Zone 01 | 0 | 2025-09-28
MOC.CN.F2.Z1.10.1785 | GLASS partiton - Second Floor Zone 01 | 0 | 2025-10-15
MOC.CN.F2.Z1.09.1460 | Final painting coat - Second Floor Zone 01 | 0 | 2025-10-15
MOC.CN.F2.Z1.10.1795 | Curtain Installation - Second Floor Zone 01 | 0 | 2025-10-19
MOC.CN.F2.Z1.05.1220 | Metal Handles for stairs - Second Floor Zone 01 | 0 | 2025-10-20
MOC.CN.F2.Z1.09.1735 | Acoustic wall panel Installation - Second Floor Zone 01 | 15 | 2025-10-23
MOC.CN.F2.Z1.18.01 | Final Touch Up - Second Floor Zone 01 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z1.FIN.FLR Flooring |  | 35.62 | 2025-10-23
MOC.CN.F2.Z1.09.1640 | Raised Floor First Fix - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 01 | 0 | 2025-09-28
MOC.CN.F2.Z1.09.1640[R] | Raised Floor First Fix - Second Floor Zone 01 [Remaining] | 50 | 2025-09-30
MOC.CN.F2.Z1.09.1645 | Raised Floor Final fix installation - Second Floor Zone 01 | 50 | 2025-10-07
MOC.CN.F2.Z1.09.1595 | Carpet Installation - Second Floor Zone 01 | 0 | 2025-10-19
MOC.CN.F2.Z1.09.1690 | Skirting Installation - Second Floor Zone 01 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z1.MEP MEP |  | 50.31 | 2025-10-21
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.MEC Mechanical |  | 70.73 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.MEC.PL Plumbing |  | 67.42 | 2025-10-07
MOC.CN.F2.Z1.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2420 | Water Supply pipes insulation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2305[R] | Water Supply pipes installation & Testing - Second Floor Zone 01 [Remaining] | 80 | 2025-07-23
MOC.CN.F2.Z1.15.1915[R] | Valves and accessories for Water Supply System - Second Floor Zone 01 [Remaining] | 50 | 2025-07-24
MOC.CN.F2.Z1.15.2420[R] | Water Supply pipes insulation - Second Floor Zone 01 [Remaining] | 0 | 2025-07-27
MOC.CN.F2.Z1.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 01 [Remaining] | 45 | 2025-07-28
MOC.CN.F2.Z1.15.2315 | Floor Drain Installation - Second Floor Zone 01 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.MEC.FF Fire Fightig |  | 58.22 | 2025-10-09
MOC.CN.F2.Z1.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 01 | 100 | 10-May-25 A
MOC.CN.F2.Z1.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 01 | 100 | 11-May-25 A
MOC.CN.F2.Z1.15.1975 | Fire-hose cabinets installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 01 | 100 | 15-Jun-25 A
MOC.CN.F2.Z1.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 01 [Remaining] | 0 | 2025-09-17
MOC.CN.F2.Z1.15.1980 | Fire extinguishers installation - Second Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F2.Z1.15.1985 | Fire sprinklers installation - Second Floor Zone 01 | 0 | 2025-10-01
MOC.CN.F2.Z1.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 01 | 0 | 2025-10-02
MOC.CN.F2.Z1.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 01 | 0 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.MEC.HV HVAC |  | 75.44 | 2025-10-06
MOC.CN.F2.Z1.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 01 | 100 | 03-May-25 A
MOC.CN.F2.Z1.15.2380 | Duct Installation - Second Floor Zone 01 | 100 | 12-May-25 A
MOC.CN.F2.Z1.15.2385 | Duct Insulation - Second Floor Zone 01 | 100 | 18-May-25 A
MOC.CN.F2.Z1.15.2390 | Duct Lining - Second Floor Zone 01 | 100 | 18-May-25 A
MOC.CN.F2.Z1.15.2275 | Thermostat Installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2320 | Air Handling pipes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.15.2375 | HVAC Pipes Insulation - Second Floor Zone 01 | 30 | 2025-07-31
MOC.CN.F2.Z1.15.2395 | HVAC Valves installation - Second Floor Zone 01 | 30 | 2025-08-07
MOC.CN.F2.Z1.15.2340 | Fan Coil Units Installation - Second Floor Zone 01 | 0 | 2025-08-31
MOC.CN.F2.Z1.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 01 | 0 | 2025-08-31
MOC.CN.F2.Z1.15.2320[R] | Air Handling pipes installation - Second Floor Zone 01 [Remaining] | 0 | 2025-09-06
MOC.CN.F2.Z1.15.2275[R] | Thermostat Installation - Second Floor Zone 01 [Remaining] | 0 | 2025-09-16
MOC.CN.F2.Z1.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 01 | 0 | 2025-09-22
MOC.CN.F2.Z1.15.2100 | Air Diffusers Installation - Second Floor Zone 01 | 0 | 2025-10-02
MOC.CN.F2.Z1.15.2325 | Air Handling units installation - Second Floor Zone 01 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL Electrical |  | 44.33 | 2025-10-21
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.EP Electrical Power |  | 49.72 | 2025-10-21
MOC.CN.F2.Z1.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2630 | Cables & Wiring Installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2655 | Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2745 | Wiring Installation in floors - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2610[R] | Cable Trays & Trunks Installation - Second Floor Zone 01 [Remaining] | 80 | 2025-07-23
MOC.CN.F2.Z1.16.2655[R] | Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 80 | 2025-07-27
MOC.CN.F2.Z1.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 01 [Remaining] | 50 | 2025-07-27
MOC.CN.F2.Z1.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 01 [Remaining] | 80 | 2025-08-25
MOC.CN.F2.Z1.16.2745[R] | Wiring Installation in floors - Second Floor Zone 01 [Remaining] | 40 | 2025-09-01
MOC.CN.F2.Z1.16.2625 | Earthing System installation - Second Floor Zone 01 | 0 | 2025-09-15
MOC.CN.F2.Z1.16.2715 | Distribution board installation - Second Floor Zone 01 | 0 | 2025-09-28
MOC.CN.F2.Z1.16.2495 | Sockets and Switches installation - Second Floor Zone 01 | 0 | 2025-10-01
MOC.CN.F2.Z1.16.2490 | Lighting fixtures installation - Second Floor Zone 01 | 0 | 2025-10-06
MOC.CN.F2.Z1.16.2750 | Floor Sockets Installation - Second Floor Zone 01 | 0 | 2025-10-21
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-02
MOC.CN.F2.Z1.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.F2.Z1.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 01 | 0 | 2025-08-03
MOC.CN.F2.Z1.16.2515 | Audiovisual system installation - Second Floor Zone 01 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.LC Lighting Control |  | 69.83 | 2025-10-06
MOC.CN.F2.Z1.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2685[R] | Lighting Control Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z1.16.2710[R] | Lighting Control Wiring Installation - Second Floor Zone 01 [Remaining] | 85 | 2025-07-23
MOC.CN.F2.Z1.16.2660 | Lighting Control System installation - Second Floor Zone 01 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.T&D Telecommunication & Data System |  | 54.31 | 2025-09-30
MOC.CN.F2.Z1.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 70 | 2025-07-23
MOC.CN.F2.Z1.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 01 | 0 | 2025-08-10
MOC.CN.F2.Z1.16.2505 | Telecommunication and Data system installation - Second Floor Zone 01 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.SS Security System |  | 2.26 | 2025-09-30
MOC.CN.F2.Z1.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z1.16.2695 | Security System Wiring Installation - Second Floor Zone 01 | 0 | 2025-08-14
MOC.CN.F2.Z1.16.2640 | Security System Installation - Second Floor Zone 01 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-10-02
MOC.CN.F2.Z1.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2675[R] | IPTV System Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 100 | 30-Jun-25 A
MOC.CN.F2.Z1.16.2700 | IPTV System Wiring Installation - Second Floor Zone 01 | 0 | 2025-08-13
MOC.CN.F2.Z1.16.2645 | IPTV System installation - Second Floor Zone 01 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.98 | 2025-09-30
MOC.CN.F2.Z1.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 01 | 100 | 06-May-25 A
MOC.CN.F2.Z1.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 01 | 100 | 17-May-25 A
MOC.CN.F2.Z1.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 01 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.PA Public Address System |  | 32.5 | 2025-10-04
MOC.CN.F2.Z1.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2725[R] | Public Address System Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z1.16.2730 | Public Address System Wiring Installation - Second Floor Zone 01 | 0 | 2025-08-07
MOC.CN.F2.Z1.16.2525 | Public Address System installation - Second Floor Zone 01 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z1.MEP.EL.CBS Central Battery |  | 95 | 2025-07-22
MOC.CN.F2.Z1.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.F2.Z1.16.2665[R] | Central Battery System Conduits and boxes installation - Second Floor Zone 01 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.F2.Z1.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 01 | 90 | 2025-07-22
MOC.REV.R06.U0200725.CON.F2.Z2 Zone 02 |  | 44.79 | 2025-11-05
MOC.REV.R06.U0200725.CON.F2.Z2.FIN Finishes |  | 31.26 | 2025-11-05
MOC.REV.R06.U0200725.CON.F2.Z2.FIN.C&W Ceiling & Walls |  | 29.47 | 2025-11-05
MOC.CN.F2.Z2.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 02 | 100 | 26-Mar-25 A
MOC.CN.F2.Z2.04.1175 | Masonary works - Second Floor Zone 02 | 100 | 05-Apr-25 A
MOC.CN.F2.Z2.09.1740 | Plaster First Stage - Second Floor Zone 02 | 100 | 07-Apr-25 A
MOC.CN.F2.Z2.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.09.1745 | Plaster Second Stage - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.09.1455 | First and Second painting coats - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.09.1745[R] | Plaster Second Stage - Second Floor Zone 02 [Remaining] | 100 | 29-Jun-25 A
MOC.CN.F2.Z2.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 02 [Remaining] | 100 | 30-Jun-25 A
MOC.CN.F2.Z2.09.1685 | Wooden Cladding First Fix - Second Floor Zone 02 | 100 | 01-Jul-25 A
MOC.CN.F2.Z2.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 02 | 20 | 2025-08-20
MOC.CN.F2.Z2.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 02 | 0 | 2025-08-27
MOC.CN.F2.Z2.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 02 | 0 | 2025-08-27
MOC.CN.F2.Z2.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 02 | 0 | 2025-09-07
MOC.CN.F2.Z2.08.1430 | Doors Frame installation - Second Floor Zone 02 | 0 | 2025-09-10
MOC.CN.F2.Z2.09.1455[R] | First and Second painting coats - Second Floor Zone 02 [Remaining] | 45 | 2025-09-14
MOC.CN.F2.Z2.08.1400 | Wooden Doors installation - Second Floor Zone 02 | 0 | 2025-09-17
MOC.CN.F2.Z2.09.1765 | Cornice Installation - Second Floor Zone 02 | 0 | 2025-09-18
MOC.CN.F2.Z2.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 02 | 0 | 2025-09-21
MOC.CN.F2.Z2.10.1775 | Signage works - Second Floor Zone 02 | 0 | 2025-09-22
MOC.CN.F2.Z2.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 02 | 0 | 2025-09-25
MOC.CN.F2.Z2.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 02 | 0 | 2025-09-25
MOC.CN.F2.Z2.10.2780 | Elevator Finishes - Second Floor Zone 02 | 0 | 2025-09-29
MOC.CN.F2.Z2.10.1795 | Curtain Installation - Second Floor Zone 02 | 0 | 2025-10-07
MOC.CN.F2.Z2.10.1785 | GLASS partiton - Second Floor Zone 02 | 35 | 2025-10-12
MOC.CN.F2.Z2.09.1460 | Final painting coat - Second Floor Zone 02 | 0 | 2025-10-18
MOC.CN.F2.Z2.05.1220 | Metal Handles for stairs - Second Floor Zone 02 | 0 | 2025-10-22
MOC.CN.F2.Z2.09.1735 | Acoustic wall panel Installation - Second Floor Zone 02 | 15 | 2025-10-25
MOC.CN.F2.Z2.18.01 | Final Touch Up - Second Floor Zone 02 | 0 | 2025-11-05
MOC.REV.R06.U0200725.CON.F2.Z2.FIN.FLR Flooring |  | 36.42 | 2025-10-27
MOC.CN.F2.Z2.09.1640 | Raised Floor First Fix - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.09.1515 | Porcelain tiles for Flooring - Second Floor Zone 02 | 0 | 2025-08-12
MOC.CN.F2.Z2.09.1640[R] | Raised Floor First Fix - Second Floor Zone 02 [Remaining] | 60 | 2025-09-28
MOC.CN.F2.Z2.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 02 | 0 | 2025-09-30
MOC.CN.F2.Z2.09.1645 | Raised Floor Final fix installation - Second Floor Zone 02 | 60 | 2025-10-05
MOC.CN.F2.Z2.09.1595 | Carpet Installation - Second Floor Zone 02 | 0 | 2025-10-22
MOC.CN.F2.Z2.09.1690 | Skirting Installation - Second Floor Zone 02 | 0 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z2.MEP MEP |  | 53.47 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.MEC Mechanical |  | 75.08 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.MEC.PL Plumbing |  | 88.52 | 2025-10-12
MOC.CN.F2.Z2.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 02 | 100 | 05-May-25 A
MOC.CN.F2.Z2.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2420 | Water Supply pipes insulation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2220 | Stainless Steel water tanks - Second Floor Zone 02 | 100 | 22-Jun-25 A
MOC.CN.F2.Z2.15.1915[R] | Valves and accessories for Water Supply System - Second Floor Zone 02 [Remaining] | 60 | 2025-07-22
MOC.CN.F2.Z2.15.2420[R] | Water Supply pipes insulation - Second Floor Zone 02 [Remaining] | 60 | 2025-07-24
MOC.CN.F2.Z2.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 02 [Remaining] | 70 | 2025-07-27
MOC.CN.F2.Z2.15.2315 | Floor Drain Installation - Second Floor Zone 02 | 0 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.MEC.FF Fire Fightig |  | 83.84 | 2025-10-12
MOC.CN.F2.Z2.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2260 | Hood fire protection system - Pipes Installation & Testing - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2265 | Hood fire protection system - Cylinders installation - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2270 | Hood fire protection system - Nozzles installation - Second Floor Zone 02 | 100 | 17-May-25 A
MOC.CN.F2.Z2.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.1975 | Fire-hose cabinets installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 02 | 100 | 15-Jun-25 A
MOC.CN.F2.Z2.15.1970[R] | Fire Fighting valves and accessories - Second Floor Zone 02 [Remaining] | 0 | 2025-08-05
MOC.CN.F2.Z2.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 02 [Remaining] | 0 | 2025-09-21
MOC.CN.F2.Z2.15.1980 | Fire extinguishers installation - Second Floor Zone 02 | 0 | 2025-10-01
MOC.CN.F2.Z2.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 02 | 0 | 2025-10-05
MOC.CN.F2.Z2.15.1985 | Fire sprinklers installation - Second Floor Zone 02 | 0 | 2025-10-11
MOC.CN.F2.Z2.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 02 | 0 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.MEC.HV HVAC |  | 66.37 | 2025-10-04
MOC.CN.F2.Z2.15.2380 | Duct Installation - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2385 | Duct Insulation - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2390 | Duct Lining - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.CN.F2.Z2.15.2275 | Thermostat Installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2320 | Air Handling pipes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.15.2370[R] | HVAC Pipes Installation & Testing - Second Floor Zone 02 [Remaining] | 75 | 2025-07-21
MOC.CN.F2.Z2.15.2375 | HVAC Pipes Insulation - Second Floor Zone 02 | 0 | 2025-08-06
MOC.CN.F2.Z2.15.2395 | HVAC Valves installation - Second Floor Zone 02 | 0 | 2025-08-13
MOC.CN.F2.Z2.15.2340 | Fan Coil Units Installation - Second Floor Zone 02 | 30 | 2025-08-31
MOC.CN.F2.Z2.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 02 | 0 | 2025-09-03
MOC.CN.F2.Z2.15.2320[R] | Air Handling pipes installation - Second Floor Zone 02 [Remaining] | 0 | 2025-09-06
MOC.CN.F2.Z2.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 02 | 0 | 2025-09-18
MOC.CN.F2.Z2.15.2275[R] | Thermostat Installation - Second Floor Zone 02 [Remaining] | 0 | 2025-09-22
MOC.CN.F2.Z2.15.2100 | Air Diffusers Installation - Second Floor Zone 02 | 0 | 2025-10-01
MOC.CN.F2.Z2.15.2325 | Air Handling units installation - Second Floor Zone 02 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL Electrical |  | 43.43 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.EP Electrical Power |  | 48.39 | 2025-10-27
MOC.CN.F2.Z2.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2630 | Cables & Wiring Installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2655 | Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2655[R] | Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 100 | 05-Jun-25 A
MOC.CN.F2.Z2.16.2610[R] | Cable Trays & Trunks Installation - Second Floor Zone 02 [Remaining] | 50 | 2025-07-29
MOC.CN.F2.Z2.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 02 [Remaining] | 50 | 2025-07-30
MOC.CN.F2.Z2.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 02 [Remaining] | 80 | 2025-08-31
MOC.CN.F2.Z2.16.2745 | Wiring Installation in floors - Second Floor Zone 02 | 80 | 2025-09-06
MOC.CN.F2.Z2.16.2625 | Earthing System installation - Second Floor Zone 02 | 0 | 2025-09-20
MOC.CN.F2.Z2.16.2715 | Distribution board installation - Second Floor Zone 02 | 0 | 2025-09-29
MOC.CN.F2.Z2.16.2490 | Lighting fixtures installation - Second Floor Zone 02 | 0 | 2025-10-07
MOC.CN.F2.Z2.16.2495 | Sockets and Switches installation - Second Floor Zone 02 | 0 | 2025-10-09
MOC.CN.F2.Z2.16.2750 | Floor Sockets Installation - Second Floor Zone 02 | 0 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-21
MOC.CN.F2.Z2.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 02 | 100 | 05-May-25 A
MOC.CN.F2.Z2.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 02 | 0 | 2025-08-13
MOC.CN.F2.Z2.16.2515 | Audiovisual system installation - Second Floor Zone 02 | 0 | 2025-10-21
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.LC Lighting Control |  | 68.92 | 2025-10-07
MOC.CN.F2.Z2.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2685[R] | Lighting Control Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.F2.Z2.16.2710[R] | Lighting Control Wiring Installation - Second Floor Zone 02 [Remaining] | 85 | 2025-07-22
MOC.CN.F2.Z2.16.2660 | Lighting Control System installation - Second Floor Zone 02 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.T&D Telecommunication & Data System |  | 54.31 | 2025-10-02
MOC.CN.F2.Z2.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 70 | 2025-07-22
MOC.CN.F2.Z2.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 02 | 0 | 2025-08-20
MOC.CN.F2.Z2.16.2505 | Telecommunication and Data system installation - Second Floor Zone 02 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.SS Security System |  | 2.24 | 2025-10-02
MOC.CN.F2.Z2.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z2.16.2695 | Security System Wiring Installation - Second Floor Zone 02 | 0 | 2025-08-14
MOC.CN.F2.Z2.16.2640 | Security System Installation - Second Floor Zone 02 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.IPTV IPTV System |  | 23.33 | 2025-10-02
MOC.CN.F2.Z2.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2675[R] | IPTV System Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 0 | 2025-07-26
MOC.CN.F2.Z2.16.2700 | IPTV System Wiring Installation - Second Floor Zone 02 | 0 | 2025-08-12
MOC.CN.F2.Z2.16.2645 | IPTV System installation - Second Floor Zone 02 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 55.96 | 2025-10-11
MOC.CN.F2.Z2.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2680[R] | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.F2.Z2.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 02 [Remaining] | 80 | 2025-07-23
MOC.CN.F2.Z2.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 02 | 0 | 2025-10-11
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.PA Public Address System |  | 32.33 | 2025-10-12
MOC.CN.F2.Z2.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.F2.Z2.16.2725[R] | Public Address System Conduits and boxes installation - Second Floor Zone 02 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z2.16.2730 | Public Address System Wiring Installation - Second Floor Zone 02 | 0 | 2025-08-14
MOC.CN.F2.Z2.16.2525 | Public Address System installation - Second Floor Zone 02 | 0 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z2.MEP.EL.CBS Central Battery |  | 100 | 10-May-25 A
MOC.CN.F2.Z2.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 02 | 100 | 01-May-25 A
MOC.CN.F2.Z2.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 02 | 100 | 10-May-25 A
MOC.REV.R06.U0200725.CON.F2.Z3 Zone 03 |  | 41.4 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z3.FIN Finishes |  | 29.66 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z3.FIN.C&W Ceiling & Walls |  | 28.37 | 2025-10-23
MOC.CN.F2.Z3.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 03 | 100 | 27-Mar-25 A
MOC.CN.F2.Z3.04.1175 | Masonary works - Second Floor Zone 03 | 100 | 02-Apr-25 A
MOC.CN.F2.Z3.09.1740 | Plaster First Stage - Second Floor Zone 03 | 100 | 08-Apr-25 A
MOC.CN.F2.Z3.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.09.1745 | Plaster Second Stage - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.09.1745[R] | Plaster Second Stage - Second Floor Zone 03 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F2.Z3.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 03 [Remaining] | 90 | 2025-07-22
MOC.CN.F2.Z3.09.1685 | Wooden Cladding First Fix - Second Floor Zone 03 | 90 | 2025-08-14
MOC.CN.F2.Z3.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 03 | 10 | 2025-08-16
MOC.CN.F2.Z3.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 03 | 0 | 2025-08-16
MOC.CN.F2.Z3.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 03 | 0 | 2025-08-23
MOC.CN.F2.Z3.08.1430 | Doors Frame installation - Second Floor Zone 03 | 0 | 2025-09-03
MOC.CN.F2.Z3.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 03 | 0 | 2025-09-09
MOC.CN.F2.Z3.08.1400 | Wooden Doors installation - Second Floor Zone 03 | 0 | 2025-09-10
MOC.CN.F2.Z3.10.1775 | Signage works - Second Floor Zone 03 | 0 | 2025-09-15
MOC.CN.F2.Z3.09.1455 | First and Second painting coats - Second Floor Zone 03 | 40 | 2025-09-16
MOC.CN.F2.Z3.09.1765 | Cornice Installation - Second Floor Zone 03 | 0 | 2025-09-21
MOC.CN.F2.Z3.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 03 | 0 | 2025-09-22
MOC.CN.F2.Z3.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 03 | 0 | 2025-09-24
MOC.CN.F2.Z3.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 03 | 0 | 2025-09-24
MOC.CN.F2.Z3.10.2780 | Elevator Finishes - Second Floor Zone 03 | 0 | 2025-10-01
MOC.CN.F2.Z3.10.1795 | Curtain Installation - Second Floor Zone 03 | 0 | 2025-10-06
MOC.CN.F2.Z3.10.1785 | GLASS partiton - Second Floor Zone 03 | 25 | 2025-10-12
MOC.CN.F2.Z3.09.1460 | Final painting coat - Second Floor Zone 03 | 0 | 2025-10-13
MOC.CN.F2.Z3.05.1220 | Metal Handles for stairs - Second Floor Zone 03 | 0 | 2025-10-18
MOC.CN.F2.Z3.09.1735 | Acoustic wall panel Installation - Second Floor Zone 03 | 75 | 2025-10-21
MOC.CN.F2.Z3.18.01 | Final Touch Up - Second Floor Zone 03 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z3.FIN.FLR Flooring |  | 33.45 | 2025-10-23
MOC.CN.F2.Z3.09.1640 | Raised Floor First Fix - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.09.1515 | Porcelain tiles for Flooring - Second Floor Zone 03 | 0 | 2025-08-24
MOC.CN.F2.Z3.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 03 | 0 | 2025-09-28
MOC.CN.F2.Z3.09.1640[R] | Raised Floor First Fix - Second Floor Zone 03 [Remaining] | 50 | 2025-09-29
MOC.CN.F2.Z3.09.1645 | Raised Floor Final fix installation - Second Floor Zone 03 | 50 | 2025-10-06
MOC.CN.F2.Z3.09.1595 | Carpet Installation - Second Floor Zone 03 | 0 | 2025-10-19
MOC.CN.F2.Z3.09.1690 | Skirting Installation - Second Floor Zone 03 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z3.MEP MEP |  | 50.11 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.MEC Mechanical |  | 68.12 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.MEC.PL Plumbing |  | 70.9 | 2025-10-07
MOC.CN.F2.Z3.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2420 | Water Supply pipes insulation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2305[R] | Water Supply pipes installation & Testing - Second Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z3.15.1915[R] | Valves and accessories for Water Supply System - Second Floor Zone 03 [Remaining] | 65 | 2025-07-23
MOC.CN.F2.Z3.15.2420[R] | Water Supply pipes insulation - Second Floor Zone 03 [Remaining] | 0 | 2025-07-29
MOC.CN.F2.Z3.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 03 [Remaining] | 70 | 2025-07-30
MOC.CN.F2.Z3.15.2315 | Floor Drain Installation - Second Floor Zone 03 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.MEC.FF Fire Fightig |  | 55.3 | 2025-10-07
MOC.CN.F2.Z3.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 03 | 100 | 10-May-25 A
MOC.CN.F2.Z3.15.1975 | Fire-hose cabinets installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 03 | 100 | 15-Jun-25 A
MOC.CN.F2.Z3.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 03 | 50 | 2025-07-26
MOC.CN.F2.Z3.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 03 [Remaining] | 0 | 2025-09-24
MOC.CN.F2.Z3.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 03 | 0 | 2025-10-02
MOC.CN.F2.Z3.15.1980 | Fire extinguishers installation - Second Floor Zone 03 | 0 | 2025-10-04
MOC.CN.F2.Z3.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 03 | 0 | 2025-10-06
MOC.CN.F2.Z3.15.1985 | Fire sprinklers installation - Second Floor Zone 03 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.MEC.HV HVAC |  | 72.71 | 2025-09-30
MOC.CN.F2.Z3.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 03 | 100 | 01-May-25 A
MOC.CN.F2.Z3.15.2275 | Thermostat Installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2380 | Duct Installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2385 | Duct Insulation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2390 | Duct Lining - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.15.2380[R] | Duct Installation - Second Floor Zone 03 [Remaining] | 70 | 2025-07-27
MOC.CN.F2.Z3.15.2385[R] | Duct Insulation - Second Floor Zone 03 [Remaining] | 70 | 2025-08-02
MOC.CN.F2.Z3.15.2390[R] | Duct Lining - Second Floor Zone 03 [Remaining] | 70 | 2025-08-05
MOC.CN.F2.Z3.15.2375 | HVAC Pipes Insulation - Second Floor Zone 03 | 0 | 2025-08-05
MOC.CN.F2.Z3.15.2395 | HVAC Valves installation - Second Floor Zone 03 | 0 | 2025-08-12
MOC.CN.F2.Z3.15.2340 | Fan Coil Units Installation - Second Floor Zone 03 | 0 | 2025-08-27
MOC.CN.F2.Z3.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 03 | 0 | 2025-08-27
MOC.CN.F2.Z3.15.2320 | Air Handling pipes installation - Second Floor Zone 03 | 0 | 2025-09-08
MOC.CN.F2.Z3.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 03 | 0 | 2025-09-13
MOC.CN.F2.Z3.15.2275[R] | Thermostat Installation - Second Floor Zone 03 [Remaining] | 0 | 2025-09-24
MOC.CN.F2.Z3.15.2100 | Air Diffusers Installation - Second Floor Zone 03 | 0 | 2025-09-27
MOC.CN.F2.Z3.15.2325 | Air Handling units installation - Second Floor Zone 03 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL Electrical |  | 44.85 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.EP Electrical Power |  | 51.25 | 2025-10-22
MOC.CN.F2.Z3.16.2630 | Cables & Wiring Installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2655 | Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2655[R] | Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 100 | 05-Jun-25 A
MOC.CN.F2.Z3.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 03 | 50 | 2025-07-28
MOC.CN.F2.Z3.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 03 [Remaining] | 50 | 2025-07-29
MOC.CN.F2.Z3.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 03 [Remaining] | 80 | 2025-08-24
MOC.CN.F2.Z3.16.2745 | Wiring Installation in floors - Second Floor Zone 03 | 65 | 2025-08-31
MOC.CN.F2.Z3.16.2625 | Earthing System installation - Second Floor Zone 03 | 0 | 2025-09-14
MOC.CN.F2.Z3.16.2715 | Distribution board installation - Second Floor Zone 03 | 0 | 2025-09-25
MOC.CN.F2.Z3.16.2495 | Sockets and Switches installation - Second Floor Zone 03 | 0 | 2025-10-02
MOC.CN.F2.Z3.16.2490 | Lighting fixtures installation - Second Floor Zone 03 | 0 | 2025-10-05
MOC.CN.F2.Z3.16.2750 | Floor Sockets Installation - Second Floor Zone 03 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-16
MOC.CN.F2.Z3.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 03 | 100 | 05-May-25 A
MOC.CN.F2.Z3.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 03 | 0 | 2025-08-05
MOC.CN.F2.Z3.16.2515 | Audiovisual system installation - Second Floor Zone 03 | 0 | 2025-10-16
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.LC Lighting Control |  | 67.1 | 2025-09-30
MOC.CN.F2.Z3.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2710[R] | Lighting Control Wiring Installation - Second Floor Zone 03 [Remaining] | 85 | 2025-07-22
MOC.CN.F2.Z3.16.2685[R] | Lighting Control Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 0 | 2025-07-22
MOC.CN.F2.Z3.16.2660 | Lighting Control System installation - Second Floor Zone 03 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.T&D Telecommunication & Data System |  | 54.31 | 2025-09-30
MOC.CN.F2.Z3.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 70 | 2025-07-22
MOC.CN.F2.Z3.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 03 | 0 | 2025-08-07
MOC.CN.F2.Z3.16.2505 | Telecommunication and Data system installation - Second Floor Zone 03 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.SS Security System |  | 2.24 | 2025-10-04
MOC.CN.F2.Z3.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z3.16.2695 | Security System Wiring Installation - Second Floor Zone 03 | 0 | 2025-08-06
MOC.CN.F2.Z3.16.2640 | Security System Installation - Second Floor Zone 03 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.IPTV IPTV System |  | 23.33 | 2025-09-30
MOC.CN.F2.Z3.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2675[R] | IPTV System Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 0 | 2025-07-26
MOC.CN.F2.Z3.16.2700 | IPTV System Wiring Installation - Second Floor Zone 03 | 0 | 2025-08-04
MOC.CN.F2.Z3.16.2645 | IPTV System installation - Second Floor Zone 03 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.98 | 2025-10-04
MOC.CN.F2.Z3.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 03 | 100 | 01-May-25 A
MOC.CN.F2.Z3.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 03 | 100 | 10-May-25 A
MOC.CN.F2.Z3.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 03 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.PA Public Address System |  | 32.33 | 2025-09-30
MOC.CN.F2.Z3.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.F2.Z3.16.2725[R] | Public Address System Conduits and boxes installation - Second Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z3.16.2730 | Public Address System Wiring Installation - Second Floor Zone 03 | 0 | 2025-08-06
MOC.CN.F2.Z3.16.2525 | Public Address System installation - Second Floor Zone 03 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.F2.Z3.MEP.EL.CBS Central Battery |  | 100 | 10-May-25 A
MOC.CN.F2.Z3.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 03 | 100 | 01-May-25 A
MOC.CN.F2.Z3.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 03 | 100 | 10-May-25 A
MOC.REV.R06.U0200725.CON.F2.Z4 Zone 04 |  | 39.73 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z4.FIN Finishes |  | 27.43 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z4.FIN.C&W Ceiling & Walls |  | 25.17 | 2025-10-26
MOC.CN.F2.Z4.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 04 | 100 | 26-Mar-25 A
MOC.CN.F2.Z4.04.1175 | Masonary works - Second Floor Zone 04 | 100 | 02-Apr-25 A
MOC.CN.F2.Z4.09.1740 | Plaster First Stage - Second Floor Zone 04 | 100 | 08-Apr-25 A
MOC.CN.F2.Z4.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.09.1745 | Plaster Second Stage - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.09.1455 | First and Second painting coats - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.09.1745[R] | Plaster Second Stage - Second Floor Zone 04 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F2.Z4.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 04 [Remaining] | 100 | 13-Jul-25 A
MOC.CN.F2.Z4.09.1685 | Wooden Cladding First Fix - Second Floor Zone 04 | 100 | 14-Jul-25 A
MOC.CN.F2.Z4.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 04 | 10 | 2025-08-23
MOC.CN.F2.Z4.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 04 | 0 | 2025-08-24
MOC.CN.F2.Z4.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 04 | 0 | 2025-08-30
MOC.CN.F2.Z4.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 04 | 0 | 2025-09-09
MOC.CN.F2.Z4.08.1430 | Doors Frame installation - Second Floor Zone 04 | 0 | 2025-09-11
MOC.CN.F2.Z4.09.1455[R] | First and Second painting coats - Second Floor Zone 04 [Remaining] | 25 | 2025-09-13
MOC.CN.F2.Z4.08.1400 | Wooden Doors installation - Second Floor Zone 04 | 0 | 2025-09-16
MOC.CN.F2.Z4.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 04 | 0 | 2025-09-21
MOC.CN.F2.Z4.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 04 | 0 | 2025-09-21
MOC.CN.F2.Z4.10.1775 | Signage works - Second Floor Zone 04 | 0 | 2025-09-22
MOC.CN.F2.Z4.10.2780 | Elevator Finishes - Second Floor Zone 04 | 0 | 2025-09-22
MOC.CN.F2.Z4.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 04 | 0 | 2025-09-24
MOC.CN.F2.Z4.10.1795 | Curtain Installation - Second Floor Zone 04 | 0 | 2025-10-06
MOC.CN.F2.Z4.10.1785 | GLASS partiton - Second Floor Zone 04 | 20 | 2025-10-08
MOC.CN.F2.Z4.09.1460 | Final painting coat - Second Floor Zone 04 | 0 | 2025-10-09
MOC.CN.F2.Z4.05.1220 | Metal Handles for stairs - Second Floor Zone 04 | 0 | 2025-10-14
MOC.CN.F2.Z4.09.1735 | Acoustic wall panel Installation - Second Floor Zone 04 | 0 | 2025-10-19
MOC.CN.F2.Z4.09.1765 | Cornice Installation - Second Floor Zone 04 | 0 | 2025-10-21
MOC.CN.F2.Z4.18.01 | Final Touch Up - Second Floor Zone 04 | 0 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z4.FIN.FLR Flooring |  | 34.24 | 2025-10-19
MOC.CN.F2.Z4.09.1640 | Raised Floor First Fix - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.09.1515 | Porcelain tiles for Flooring - Second Floor Zone 04 | 0 | 2025-08-17
MOC.CN.F2.Z4.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 04 | 0 | 2025-09-27
MOC.CN.F2.Z4.09.1640[R] | Raised Floor First Fix - Second Floor Zone 04 [Remaining] | 50 | 2025-09-27
MOC.CN.F2.Z4.09.1645 | Raised Floor Final fix installation - Second Floor Zone 04 | 50 | 2025-10-02
MOC.CN.F2.Z4.09.1595 | Carpet Installation - Second Floor Zone 04 | 0 | 2025-10-15
MOC.CN.F2.Z4.09.1690 | Skirting Installation - Second Floor Zone 04 | 0 | 2025-10-19
MOC.REV.R06.U0200725.CON.F2.Z4.MEP MEP |  | 49.02 | 2025-10-14
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.MEC Mechanical |  | 65.84 | 2025-10-06
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.MEC.PL Plumbing |  | 66.01 | 2025-10-04
MOC.CN.F2.Z4.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 04 | 100 | 30-Apr-25 A
MOC.CN.F2.Z4.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 04 | 100 | 05-May-25 A
MOC.CN.F2.Z4.15.2420 | Water Supply pipes insulation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2420[R] | Water Supply pipes insulation - Second Floor Zone 04 [Remaining] | 0 | 2025-08-05
MOC.CN.F2.Z4.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 04 [Remaining] | 30 | 2025-08-17
MOC.CN.F2.Z4.15.2315 | Floor Drain Installation - Second Floor Zone 04 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.MEC.FF Fire Fightig |  | 48.31 | 2025-10-06
MOC.CN.F2.Z4.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.1975 | Fire-hose cabinets installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 04 | 100 | 15-Jun-25 A
MOC.CN.F2.Z4.15.1955[R] | Fire Fighting pipes installation & Testing - Second Floor Zone 04 [Remaining] | 60 | 2025-07-29
MOC.CN.F2.Z4.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 04 | 0 | 2025-08-09
MOC.CN.F2.Z4.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 04 [Remaining] | 0 | 2025-09-20
MOC.CN.F2.Z4.15.1980 | Fire extinguishers installation - Second Floor Zone 04 | 0 | 2025-09-30
MOC.CN.F2.Z4.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 04 | 0 | 2025-10-01
MOC.CN.F2.Z4.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 04 | 0 | 2025-10-05
MOC.CN.F2.Z4.15.1985 | Fire sprinklers installation - Second Floor Zone 04 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.MEC.HV HVAC |  | 72.56 | 2025-10-04
MOC.CN.F2.Z4.15.2380 | Duct Installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2385 | Duct Insulation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2390 | Duct Lining - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.15.2370[R] | HVAC Pipes Installation & Testing - Second Floor Zone 04 [Remaining] | 85 | 2025-07-22
MOC.CN.F2.Z4.15.2380[R] | Duct Installation - Second Floor Zone 04 [Remaining] | 75 | 2025-07-24
MOC.CN.F2.Z4.15.2375 | HVAC Pipes Insulation - Second Floor Zone 04 | 0 | 2025-07-31
MOC.CN.F2.Z4.15.2385[R] | Duct Insulation - Second Floor Zone 04 [Remaining] | 0 | 2025-07-31
MOC.CN.F2.Z4.15.2390[R] | Duct Lining - Second Floor Zone 04 [Remaining] | 0 | 2025-08-05
MOC.CN.F2.Z4.15.2395 | HVAC Valves installation - Second Floor Zone 04 | 0 | 2025-08-10
MOC.CN.F2.Z4.15.2340 | Fan Coil Units Installation - Second Floor Zone 04 | 30 | 2025-08-31
MOC.CN.F2.Z4.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 04 | 0 | 2025-09-03
MOC.CN.F2.Z4.15.2320 | Air Handling pipes installation - Second Floor Zone 04 | 0 | 2025-09-11
MOC.CN.F2.Z4.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 04 | 0 | 2025-09-17
MOC.CN.F2.Z4.15.2275 | Thermostat Installation - Second Floor Zone 04 | 0 | 2025-09-29
MOC.CN.F2.Z4.15.2325 | Air Handling units installation - Second Floor Zone 04 | 0 | 2025-10-04
MOC.CN.F2.Z4.15.2100 | Air Diffusers Installation - Second Floor Zone 04 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL Electrical |  | 44.11 | 2025-10-14
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.EP Electrical Power |  | 53.28 | 2025-10-08
MOC.CN.F2.Z4.16.2630 | Cables & Wiring Installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2655 | Conduits and boxes installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2655[R] | Conduits and boxes installation - Second Floor Zone 04 [Remaining] | 100 | 05-Jun-25 A
MOC.CN.F2.Z4.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 04 | 30 | 2025-08-03
MOC.CN.F2.Z4.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 04 [Remaining] | 35 | 2025-08-07
MOC.CN.F2.Z4.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 04 [Remaining] | 90 | 2025-08-31
MOC.CN.F2.Z4.16.2745 | Wiring Installation in floors - Second Floor Zone 04 | 55 | 2025-09-07
MOC.CN.F2.Z4.16.2715 | Distribution board installation - Second Floor Zone 04 | 0 | 2025-09-16
MOC.CN.F2.Z4.16.2625 | Earthing System installation - Second Floor Zone 04 | 0 | 2025-09-21
MOC.CN.F2.Z4.16.2490 | Lighting fixtures installation - Second Floor Zone 04 | 0 | 2025-09-29
MOC.CN.F2.Z4.16.2495 | Sockets and Switches installation - Second Floor Zone 04 | 0 | 2025-09-30
MOC.CN.F2.Z4.16.2750 | Floor Sockets Installation - Second Floor Zone 04 | 0 | 2025-10-08
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-09
MOC.CN.F2.Z4.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 04 | 100 | 05-May-25 A
MOC.CN.F2.Z4.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 04 | 0 | 2025-08-05
MOC.CN.F2.Z4.16.2515 | Audiovisual system installation - Second Floor Zone 04 | 0 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.LC Lighting Control |  | 67.28 | 2025-10-02
MOC.CN.F2.Z4.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2685[R] | Lighting Control Conduits and boxes installation - Second Floor Zone 04 [Remaining] | 100 | 23-Jun-25 A
MOC.CN.F2.Z4.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 04 | 85 | 2025-07-28
MOC.CN.F2.Z4.16.2660 | Lighting Control System installation - Second Floor Zone 04 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.T&D Telecommunication & Data System |  | 32.29 | 2025-10-02
MOC.CN.F2.Z4.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 04 [Remaining] | 40 | 2025-07-28
MOC.CN.F2.Z4.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 04 | 0 | 2025-08-13
MOC.CN.F2.Z4.16.2505 | Telecommunication and Data system installation - Second Floor Zone 04 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.SS Security System |  | 2.2 | 2025-10-14
MOC.CN.F2.Z4.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 04 [Remaining] | 90 | 2025-07-22
MOC.CN.F2.Z4.16.2695 | Security System Wiring Installation - Second Floor Zone 04 | 0 | 2025-08-13
MOC.CN.F2.Z4.16.2640 | Security System Installation - Second Floor Zone 04 | 0 | 2025-10-14
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-29
MOC.CN.F2.Z4.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 04 | 100 | 24-Jun-25 A
MOC.CN.F2.Z4.16.2700 | IPTV System Wiring Installation - Second Floor Zone 04 | 0 | 2025-08-13
MOC.CN.F2.Z4.16.2645 | IPTV System installation - Second Floor Zone 04 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 52.64 | 2025-09-29
MOC.CN.F2.Z4.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.F2.Z4.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 04 [Remaining] | 90 | 2025-07-29
MOC.CN.F2.Z4.16.2680[R] | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 04 [Remaining] | 0 | 2025-08-06
MOC.CN.F2.Z4.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 04 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.PA Public Address System |  | 30 | 2025-09-29
MOC.CN.F2.Z4.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 04 | 90 | 2025-07-21
MOC.CN.F2.Z4.16.2730 | Public Address System Wiring Installation - Second Floor Zone 04 | 0 | 2025-08-13
MOC.CN.F2.Z4.16.2525 | Public Address System installation - Second Floor Zone 04 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.F2.Z4.MEP.EL.CBS Central Battery |  | 90 | 2025-07-31
MOC.CN.F2.Z4.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 04 | 100 | 18-Jun-25 A
MOC.CN.F2.Z4.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 04 | 80 | 2025-07-31
MOC.REV.R06.U0200725.CON.F2.Z5 Zone 05 |  | 38.09 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z5.FIN Finishes |  | 26.96 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z5.FIN.C&W Ceiling & Walls |  | 24.63 | 2025-10-27
MOC.CN.F2.Z5.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 05 | 100 | 31-Mar-25 A
MOC.CN.F2.Z5.04.1175 | Masonary works - Second Floor Zone 05 | 100 | 02-Apr-25 A
MOC.CN.F2.Z5.09.1740 | Plaster First Stage - Second Floor Zone 05 | 100 | 12-Apr-25 A
MOC.CN.F2.Z5.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.09.1745 | Plaster Second Stage - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.09.1455 | First and Second painting coats - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.09.1745[R] | Plaster Second Stage - Second Floor Zone 05 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F2.Z5.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 05 [Remaining] | 90 | 2025-07-22
MOC.CN.F2.Z5.09.1685 | Wooden Cladding First Fix - Second Floor Zone 05 | 90 | 2025-08-21
MOC.CN.F2.Z5.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 05 | 10 | 2025-08-30
MOC.CN.F2.Z5.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 05 | 0 | 2025-09-01
MOC.CN.F2.Z5.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 05 | 0 | 2025-09-06
MOC.CN.F2.Z5.08.1430 | Doors Frame installation - Second Floor Zone 05 | 0 | 2025-09-16
MOC.CN.F2.Z5.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 05 | 0 | 2025-09-17
MOC.CN.F2.Z5.09.1455[R] | First and Second painting coats - Second Floor Zone 05 [Remaining] | 25 | 2025-09-22
MOC.CN.F2.Z5.08.1400 | Wooden Doors installation - Second Floor Zone 05 | 0 | 2025-09-24
MOC.CN.F2.Z5.10.1775 | Signage works - Second Floor Zone 05 | 0 | 2025-09-29
MOC.CN.F2.Z5.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 05 | 0 | 2025-09-30
MOC.CN.F2.Z5.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 05 | 0 | 2025-09-30
MOC.CN.F2.Z5.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 05 | 0 | 2025-09-30
MOC.CN.F2.Z5.09.1765 | Cornice Installation - Second Floor Zone 05 | 0 | 2025-09-30
MOC.CN.F2.Z5.10.1785 | GLASS partiton - Second Floor Zone 05 | 25 | 2025-10-07
MOC.CN.F2.Z5.10.2780 | Elevator Finishes - Second Floor Zone 05 | 0 | 2025-10-07
MOC.CN.F2.Z5.10.1795 | Curtain Installation - Second Floor Zone 05 | 0 | 2025-10-12
MOC.CN.F2.Z5.09.1460 | Final painting coat - Second Floor Zone 05 | 0 | 2025-10-18
MOC.CN.F2.Z5.05.1220 | Metal Handles for stairs - Second Floor Zone 05 | 0 | 2025-10-22
MOC.CN.F2.Z5.09.1735 | Acoustic wall panel Installation - Second Floor Zone 05 | 0 | 2025-10-27
MOC.CN.F2.Z5.18.01 | Final Touch Up - Second Floor Zone 05 | 0 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z5.FIN.FLR Flooring |  | 33.91 | 2025-10-27
MOC.CN.F2.Z5.09.1640 | Raised Floor First Fix - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.09.1515 | Porcelain tiles for Flooring - Second Floor Zone 05 | 0 | 2025-08-17
MOC.CN.F2.Z5.09.1640[R] | Raised Floor First Fix - Second Floor Zone 05 [Remaining] | 50 | 2025-09-25
MOC.CN.F2.Z5.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 05 | 0 | 2025-10-04
MOC.CN.F2.Z5.09.1645 | Raised Floor Final fix installation - Second Floor Zone 05 | 50 | 2025-10-04
MOC.CN.F2.Z5.09.1595 | Carpet Installation - Second Floor Zone 05 | 0 | 2025-10-22
MOC.CN.F2.Z5.09.1690 | Skirting Installation - Second Floor Zone 05 | 0 | 2025-10-27
MOC.REV.R06.U0200725.CON.F2.Z5.MEP MEP |  | 46.45 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.MEC Mechanical |  | 63.5 | 2025-10-13
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.MEC.PL Plumbing |  | 58.95 | 2025-10-13
MOC.CN.F2.Z5.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 05 | 100 | 06-May-25 A
MOC.CN.F2.Z5.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2420 | Water Supply pipes insulation - Second Floor Zone 05 | 0 | 2025-07-31
MOC.CN.F2.Z5.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 05 [Remaining] | 75 | 2025-08-04
MOC.CN.F2.Z5.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 05 | 0 | 2025-08-17
MOC.CN.F2.Z5.15.2315 | Floor Drain Installation - Second Floor Zone 05 | 0 | 2025-10-13
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.MEC.FF Fire Fightig |  | 47.81 | 2025-10-07
MOC.CN.F2.Z5.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.1975 | Fire-hose cabinets installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 05 | 100 | 15-Jun-25 A
MOC.CN.F2.Z5.15.1955[R] | Fire Fighting pipes installation & Testing - Second Floor Zone 05 [Remaining] | 70 | 2025-07-26
MOC.CN.F2.Z5.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 05 | 0 | 2025-08-09
MOC.CN.F2.Z5.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 05 [Remaining] | 0 | 2025-09-25
MOC.CN.F2.Z5.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 05 | 0 | 2025-10-01
MOC.CN.F2.Z5.15.1980 | Fire extinguishers installation - Second Floor Zone 05 | 0 | 2025-10-02
MOC.CN.F2.Z5.15.1985 | Fire sprinklers installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.CN.F2.Z5.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.MEC.HV HVAC |  | 69.65 | 2025-10-09
MOC.CN.F2.Z5.15.2380 | Duct Installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2385 | Duct Insulation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2390 | Duct Lining - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.15.2370[R] | HVAC Pipes Installation & Testing - Second Floor Zone 05 [Remaining] | 70 | 2025-07-23
MOC.CN.F2.Z5.15.2380[R] | Duct Installation - Second Floor Zone 05 [Remaining] | 70 | 2025-07-24
MOC.CN.F2.Z5.15.2385[R] | Duct Insulation - Second Floor Zone 05 [Remaining] | 50 | 2025-07-29
MOC.CN.F2.Z5.15.2390[R] | Duct Lining - Second Floor Zone 05 [Remaining] | 50 | 2025-08-03
MOC.CN.F2.Z5.15.2375 | HVAC Pipes Insulation - Second Floor Zone 05 | 0 | 2025-08-09
MOC.CN.F2.Z5.15.2395 | HVAC Valves installation - Second Floor Zone 05 | 0 | 2025-08-18
MOC.CN.F2.Z5.15.2340 | Fan Coil Units Installation - Second Floor Zone 05 | 0 | 2025-09-10
MOC.CN.F2.Z5.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 05 | 0 | 2025-09-10
MOC.CN.F2.Z5.15.2320 | Air Handling pipes installation - Second Floor Zone 05 | 0 | 2025-09-18
MOC.CN.F2.Z5.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 05 | 0 | 2025-09-22
MOC.CN.F2.Z5.15.2275 | Thermostat Installation - Second Floor Zone 05 | 0 | 2025-10-06
MOC.CN.F2.Z5.15.2325 | Air Handling units installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.CN.F2.Z5.15.2100 | Air Diffusers Installation - Second Floor Zone 05 | 0 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL Electrical |  | 41.47 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.EP Electrical Power |  | 45.44 | 2025-10-23
MOC.CN.F2.Z5.16.2630 | Cables & Wiring Installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2655 | Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2655[R] | Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 100 | 05-Jun-25 A
MOC.CN.F2.Z5.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 05 | 20 | 2025-08-05
MOC.CN.F2.Z5.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 05 [Remaining] | 40 | 2025-08-09
MOC.CN.F2.Z5.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 05 [Remaining] | 85 | 2025-09-04
MOC.CN.F2.Z5.16.2745 | Wiring Installation in floors - Second Floor Zone 05 | 40 | 2025-09-13
MOC.CN.F2.Z5.16.2625 | Earthing System installation - Second Floor Zone 05 | 0 | 2025-09-28
MOC.CN.F2.Z5.16.2715 | Distribution board installation - Second Floor Zone 05 | 0 | 2025-09-29
MOC.CN.F2.Z5.16.2495 | Sockets and Switches installation - Second Floor Zone 05 | 0 | 2025-10-11
MOC.CN.F2.Z5.16.2490 | Lighting fixtures installation - Second Floor Zone 05 | 0 | 2025-10-14
MOC.CN.F2.Z5.16.2750 | Floor Sockets Installation - Second Floor Zone 05 | 0 | 2025-10-23
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-22
MOC.CN.F2.Z5.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 05 | 100 | 05-May-25 A
MOC.CN.F2.Z5.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 05 | 0 | 2025-08-13
MOC.CN.F2.Z5.16.2515 | Audiovisual system installation - Second Floor Zone 05 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.LC Lighting Control |  | 36.37 | 2025-10-12
MOC.CN.F2.Z5.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 05 | 100 | 10-May-25 A
MOC.CN.F2.Z5.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 05 | 0 | 2025-08-12
MOC.CN.F2.Z5.16.2660 | Lighting Control System installation - Second Floor Zone 05 | 0 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.T&D Telecommunication & Data System |  | 55.78 | 2025-10-07
MOC.CN.F2.Z5.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 0 | 2025-07-27
MOC.CN.F2.Z5.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 05 | 0 | 2025-08-13
MOC.CN.F2.Z5.16.2505 | Telecommunication and Data system installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.SS Security System |  | 2.2 | 2025-10-14
MOC.CN.F2.Z5.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 0 | 2025-07-27
MOC.CN.F2.Z5.16.2695 | Security System Wiring Installation - Second Floor Zone 05 | 0 | 2025-08-13
MOC.CN.F2.Z5.16.2640 | Security System Installation - Second Floor Zone 05 | 0 | 2025-10-14
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.IPTV IPTV System |  | 31.67 | 2025-10-07
MOC.CN.F2.Z5.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2675[R] | IPTV System Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 0 | 2025-07-27
MOC.CN.F2.Z5.16.2700 | IPTV System Wiring Installation - Second Floor Zone 05 | 0 | 2025-08-13
MOC.CN.F2.Z5.16.2645 | IPTV System installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 56.03 | 2025-10-12
MOC.CN.F2.Z5.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2680[R] | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 100 | 04-Jun-25 A
MOC.CN.F2.Z5.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 05 | 90 | 2025-07-30
MOC.CN.F2.Z5.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 05 | 0 | 2025-10-12
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.PA Public Address System |  | 33.17 | 2025-10-07
MOC.CN.F2.Z5.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2725[R] | Public Address System Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z5.16.2730 | Public Address System Wiring Installation - Second Floor Zone 05 | 0 | 2025-08-14
MOC.CN.F2.Z5.16.2525 | Public Address System installation - Second Floor Zone 05 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.F2.Z5.MEP.EL.CBS Central Battery |  | 92.5 | 2025-07-26
MOC.CN.F2.Z5.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.F2.Z5.16.2665[R] | Central Battery System Conduits and boxes installation - Second Floor Zone 05 [Remaining] | 100 | 03-Jun-25 A
MOC.CN.F2.Z5.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 05 | 85 | 2025-07-26
MOC.REV.R06.U0200725.CON.F2.Z6 Zone 06 |  | 33.57 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z6.FIN Finishes |  | 19.31 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z6.FIN.C&W Ceiling & Walls |  | 22.72 | 2025-10-26
MOC.CN.F2.Z6.09.1750 | Gypsum Board Partitions First Fix - Second Floor Zone 06 | 100 | 31-Mar-25 A
MOC.CN.F2.Z6.04.1175 | Masonary works - Second Floor Zone 06 | 100 | 02-Apr-25 A
MOC.CN.F2.Z6.09.1740 | Plaster First Stage - Second Floor Zone 06 | 100 | 12-Apr-25 A
MOC.CN.F2.Z6.09.1755 | Gypsum Board Partitions Second Fix - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.09.1745 | Plaster Second Stage - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.09.1455 | First and Second painting coats - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.09.1745[R] | Plaster Second Stage - Second Floor Zone 06 [Remaining] | 100 | 01-Jul-25 A
MOC.CN.F2.Z6.09.1755[R] | Gypsum Board Partitions Second Fix - Second Floor Zone 06 [Remaining] | 90 | 2025-07-22
MOC.CN.F2.Z6.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Zone 06 | 10 | 2025-08-18
MOC.CN.F2.Z6.09.1685 | Wooden Cladding First Fix - Second Floor Zone 06 | 75 | 2025-08-21
MOC.CN.F2.Z6.09.1680 | Wooden Ceiling First Fix - Second Floor Zone 06 | 0 | 2025-08-23
MOC.CN.F2.Z6.09.1670 | Acoustic Ceiling First Fix - Second Floor Zone 06 | 0 | 2025-08-25
MOC.CN.F2.Z6.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Zone 06 | 0 | 2025-09-03
MOC.CN.F2.Z6.09.1455[R] | First and Second painting coats - Second Floor Zone 06 [Remaining] | 30 | 2025-09-07
MOC.CN.F2.Z6.08.1430 | Doors Frame installation - Second Floor Zone 06 | 0 | 2025-09-10
MOC.CN.F2.Z6.08.1400 | Wooden Doors installation - Second Floor Zone 06 | 0 | 2025-09-14
MOC.CN.F2.Z6.09.1730 | Acoustic Ceiling Second Fix - Second Floor Zone 06 | 0 | 2025-09-15
MOC.CN.F2.Z6.09.1725 | Wooden Cladding Second Fix - Second Floor Zone 06 | 0 | 2025-09-15
MOC.CN.F2.Z6.09.1720 | Wooden Ceiling Second Fix - Second Floor Zone 06 | 0 | 2025-09-16
MOC.CN.F2.Z6.10.2780 | Elevator Finishes - Second Floor Zone 06 | 0 | 2025-09-18
MOC.CN.F2.Z6.10.1775 | Signage works - Second Floor Zone 06 | 0 | 2025-09-29
MOC.CN.F2.Z6.10.1785 | GLASS partiton - Second Floor Zone 06 | 25 | 2025-09-29
MOC.CN.F2.Z6.09.1460 | Final painting coat - Second Floor Zone 06 | 0 | 2025-10-13
MOC.CN.F2.Z6.05.1220 | Metal Handles for stairs - Second Floor Zone 06 | 0 | 2025-10-18
MOC.CN.F2.Z6.09.1765 | Cornice Installation - Second Floor Zone 06 | 0 | 2025-10-20
MOC.CN.F2.Z6.10.1795 | Curtain Installation - Second Floor Zone 06 | 0 | 2025-10-21
MOC.CN.F2.Z6.09.1735 | Acoustic wall panel Installation - Second Floor Zone 06 | 0 | 2025-10-22
MOC.CN.F2.Z6.18.01 | Final Touch Up - Second Floor Zone 06 | 0 | 2025-10-26
MOC.REV.R06.U0200725.CON.F2.Z6.FIN.FLR Flooring |  | 14.95 | 2025-10-22
MOC.CN.F2.Z6.09.1640 | Raised Floor First Fix - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.09.1515 | Porcelain tiles for Flooring - Second Floor Zone 06 | 0 | 2025-08-05
MOC.CN.F2.Z6.09.1525 | Marble tiles works - Second Floor Zone 06 | 0 | 2025-08-09
MOC.CN.F2.Z6.09.1640[R] | Raised Floor First Fix - Second Floor Zone 06 [Remaining] | 60 | 2025-09-10
MOC.CN.F2.Z6.09.1490 | Ceramic tiles for Flooring works - Second Floor Zone 06 | 0 | 2025-09-20
MOC.CN.F2.Z6.09.1645 | Raised Floor Final fix installation - Second Floor Zone 06 | 60 | 2025-09-21
MOC.CN.F2.Z6.09.1595 | Carpet Installation - Second Floor Zone 06 | 0 | 2025-10-18
MOC.CN.F2.Z6.09.1690 | Skirting Installation - Second Floor Zone 06 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z6.MEP MEP |  | 45.11 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.MEC Mechanical |  | 65.15 | 2025-10-11
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.MEC.PL Plumbing |  | 56.96 | 2025-10-11
MOC.CN.F2.Z6.15.2305 | Water Supply pipes installation & Testing - Second Floor Zone 06 | 100 | 05-May-25 A
MOC.CN.F2.Z6.15.1915 | Valves and accessories for Water Supply System - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2295 | Drainage pipes installation & Testing - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2420 | Water Supply pipes insulation - Second Floor Zone 06 | 0 | 2025-07-31
MOC.CN.F2.Z6.15.2295[R] | Drainage pipes installation & Testing - Second Floor Zone 06 [Remaining] | 65 | 2025-08-04
MOC.CN.F2.Z6.15.1915[R] | Valves and accessories for Water Supply System - Second Floor Zone 06 [Remaining] | 0 | 2025-08-14
MOC.CN.F2.Z6.15.2315 | Floor Drain Installation - Second Floor Zone 06 | 0 | 2025-10-11
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.MEC.FF Fire Fightig |  | 50.26 | 2025-10-05
MOC.CN.F2.Z6.15.1955 | Fire Fighting pipes installation & Testing - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.1975 | Fire-hose cabinets installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Second Floor Zone 06 | 100 | 15-Jun-25 A
MOC.CN.F2.Z6.15.1955[R] | Fire Fighting pipes installation & Testing - Second Floor Zone 06 [Remaining] | 75 | 2025-07-26
MOC.CN.F2.Z6.15.1970 | Fire Fighting valves and accessories - Second Floor Zone 06 | 0 | 2025-08-02
MOC.CN.F2.Z6.15.1975[R] | Fire-hose cabinets installation - Second Floor Zone 06 [Remaining] | 0 | 2025-09-14
MOC.CN.F2.Z6.15.1980 | Fire extinguishers installation - Second Floor Zone 06 | 0 | 2025-09-24
MOC.CN.F2.Z6.15.2250 | NOVEC 1230 - Cylinders installation - Second Floor Zone 06 | 0 | 2025-09-25
MOC.CN.F2.Z6.15.2255 | NOVEC 1230 - Nozzles installation - Second Floor Zone 06 | 0 | 2025-10-02
MOC.CN.F2.Z6.15.1985 | Fire sprinklers installation - Second Floor Zone 06 | 0 | 2025-10-05
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.MEC.HV HVAC |  | 71.25 | 2025-10-08
MOC.CN.F2.Z6.15.2380 | Duct Installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2370 | HVAC Pipes Installation & Testing - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2385 | Duct Insulation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2390 | Duct Lining - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.15.2370[R] | HVAC Pipes Installation & Testing - Second Floor Zone 06 [Remaining] | 65 | 2025-07-23
MOC.CN.F2.Z6.15.2380[R] | Duct Installation - Second Floor Zone 06 [Remaining] | 65 | 2025-07-26
MOC.CN.F2.Z6.15.2385[R] | Duct Insulation - Second Floor Zone 06 [Remaining] | 40 | 2025-07-30
MOC.CN.F2.Z6.15.2375 | HVAC Pipes Insulation - Second Floor Zone 06 | 0 | 2025-08-04
MOC.CN.F2.Z6.15.2390[R] | Duct Lining - Second Floor Zone 06 [Remaining] | 40 | 2025-08-06
MOC.CN.F2.Z6.15.2395 | HVAC Valves installation - Second Floor Zone 06 | 0 | 2025-08-09
MOC.CN.F2.Z6.15.2340 | Fan Coil Units Installation - Second Floor Zone 06 | 0 | 2025-08-27
MOC.CN.F2.Z6.15.2280 | Variable Air Volume (VAV) - Second Floor Zone 06 | 0 | 2025-08-30
MOC.CN.F2.Z6.15.2320 | Air Handling pipes installation - Second Floor Zone 06 | 0 | 2025-09-06
MOC.CN.F2.Z6.15.2755 | Air Handling Unit Valves Installation - Second Floor Zone 06 | 0 | 2025-09-18
MOC.CN.F2.Z6.15.2275 | Thermostat Installation - Second Floor Zone 06 | 0 | 2025-09-27
MOC.CN.F2.Z6.15.2100 | Air Diffusers Installation - Second Floor Zone 06 | 0 | 2025-09-27
MOC.CN.F2.Z6.15.2325 | Air Handling units installation - Second Floor Zone 06 | 0 | 2025-10-08
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL Electrical |  | 41.1 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.EP Electrical Power |  | 47.36 | 2025-10-20
MOC.CN.F2.Z6.16.2630 | Cables & Wiring Installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2655 | Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2460 | Installing electrical conduits and boxes in floors - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2610 | Cable Trays & Trunks Installation - Second Floor Zone 06 | 20 | 2025-08-04
MOC.CN.F2.Z6.16.2655[R] | Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 90 | 2025-08-06
MOC.CN.F2.Z6.16.2630[R] | Cables & Wiring Installation - Second Floor Zone 06 [Remaining] | 45 | 2025-08-07
MOC.CN.F2.Z6.16.2460[R] | Installing electrical conduits and boxes in floors - Second Floor Zone 06 [Remaining] | 80 | 2025-08-30
MOC.CN.F2.Z6.16.2745 | Wiring Installation in floors - Second Floor Zone 06 | 40 | 2025-09-07
MOC.CN.F2.Z6.16.2715 | Distribution board installation - Second Floor Zone 06 | 0 | 2025-09-15
MOC.CN.F2.Z6.16.2625 | Earthing System installation - Second Floor Zone 06 | 0 | 2025-09-21
MOC.CN.F2.Z6.16.2495 | Sockets and Switches installation - Second Floor Zone 06 | 0 | 2025-10-01
MOC.CN.F2.Z6.16.2490 | Lighting fixtures installation - Second Floor Zone 06 | 0 | 2025-10-04
MOC.CN.F2.Z6.16.2750 | Floor Sockets Installation - Second Floor Zone 06 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-22
MOC.CN.F2.Z6.16.2735 | Audiovisual system Conduits and boxes installation - Second Floor Zone 06 | 100 | 05-May-25 A
MOC.CN.F2.Z6.16.2740 | Audiovisual system Wiring Installation - Second Floor Zone 06 | 0 | 2025-08-13
MOC.CN.F2.Z6.16.2515 | Audiovisual system installation - Second Floor Zone 06 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.LC Lighting Control |  | 66.92 | 2025-10-02
MOC.CN.F2.Z6.16.2685 | Lighting Control Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2685[R] | Lighting Control Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z6.16.2710 | Lighting Control Wiring Installation - Second Floor Zone 06 | 85 | 2025-07-26
MOC.CN.F2.Z6.16.2660 | Lighting Control System installation - Second Floor Zone 06 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.T&D Telecommunication & Data System |  | 56.95 | 2025-10-01
MOC.CN.F2.Z6.16.2720 | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2720[R] | Telecommunication & Data System Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 70 | 2025-07-21
MOC.CN.F2.Z6.16.2200 | Telecommunication and Data Cables installation - Second Floor Zone 06 | 0 | 2025-08-14
MOC.CN.F2.Z6.16.2505 | Telecommunication and Data system installation - Second Floor Zone 06 | 0 | 2025-10-01
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.SS Security System |  | 2.29 | 2025-10-22
MOC.CN.F2.Z6.16.2670 | Security System Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2670[R] | Security System Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z6.16.2695 | Security System Wiring Installation - Second Floor Zone 06 | 0 | 2025-08-14
MOC.CN.F2.Z6.16.2640 | Security System Installation - Second Floor Zone 06 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.IPTV IPTV System |  | 32.33 | 2025-09-24
MOC.CN.F2.Z6.16.2675 | IPTV System Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2675[R] | IPTV System Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 70 | 2025-07-21
MOC.CN.F2.Z6.16.2700 | IPTV System Wiring Installation - Second Floor Zone 06 | 0 | 2025-08-14
MOC.CN.F2.Z6.16.2645 | IPTV System installation - Second Floor Zone 06 | 0 | 2025-09-24
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 84.75 | 2025-09-24
MOC.CN.F2.Z6.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Second Floor Zone 06 [Remaining] | 100 | 04-Jun-25 A
MOC.CN.F2.Z6.16.2680[R] | Fire Alarm & Voice Evacuation Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 0 | 2025-07-22
MOC.CN.F2.Z6.16.2650 | Fire Alarm & Voice Evacuation System Installation - Second Floor Zone 06 | 70 | 2025-09-24
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.PA Public Address System |  | 33 | 2025-10-04
MOC.CN.F2.Z6.16.2725 | Public Address System Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2725[R] | Public Address System Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 90 | 2025-07-21
MOC.CN.F2.Z6.16.2730 | Public Address System Wiring Installation - Second Floor Zone 06 | 0 | 2025-08-14
MOC.CN.F2.Z6.16.2525 | Public Address System installation - Second Floor Zone 06 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.CBS Central Battery |  | 92.5 | 2025-07-26
MOC.CN.F2.Z6.16.2665 | Central Battery System Conduits and boxes installation - Second Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.F2.Z6.16.2665[R] | Central Battery System Conduits and boxes installation - Second Floor Zone 06 [Remaining] | 100 | 04-Jun-25 A
MOC.CN.F2.Z6.16.2690 | Central Battery System Wiring Installation - Second Floor Zone 06 | 85 | 2025-07-26
MOC.REV.R06.U0200725.CON.F2.Z6.MEP.EL.MR.SS Ministers Meeting Room Smart Systems |  | 33.33 | 2025-09-24
MOC.CN.F2.Z6.16.2775 | Audiovisual system installation for Ministers MR - Second Floor Zone 06 | 100 | 25-Jun-25 A
MOC.CN.F2.Z6.16.2765 | Audiovisual system Conduits installation for Ministers MR - Second Floor Zone 06 | 0 | 2025-08-31
MOC.CN.F2.Z6.16.2770 | Audiovisual system Wiring Installation for Ministers MR - Second Floor Zone 06 | 0 | 2025-09-24
MOC.REV.R06.U0200725.CON.F2.WT Wet Areas |  | 13.57 | 2025-10-13
MOC.REV.R06.U0200725.CON.F2.WT.FIN Finishes |  | 5.9 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.WT.FIN.C&W Ceiling & Walls |  | 7.02 | 2025-10-04
MOC.CN.F2.WT.04.1175 | Masonary works - Second Floor Wet Areas | 100 | 02-Apr-25 A
MOC.CN.F2.WT.09.1740 | Plaster First Stage - Second Floor Wet Areas | 100 | 20-Apr-25 A
MOC.CN.F2.WT.09.1745 | Plaster Second Stage - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.09.1745[R] | Plaster Second Stage - Second Floor Wet Areas [Remaining] | 60 | 2025-08-04
MOC.CN.F2.WT.09.1700 | Gypsum Board Ceiling First Fix - Second Floor Wet Areas | 0 | 2025-08-18
MOC.CN.F2.WT.08.1430 | Doors Frame installation - Second Floor Wet Areas | 0 | 2025-08-18
MOC.CN.F2.WT.09.1555 | Marble cladding works - Second Floor Wet Areas | 0 | 2025-08-26
MOC.CN.F2.WT.09.1665 | Porcelain tiles for walls - Second Floor Wet Areas | 15 | 2025-08-30
MOC.CN.F2.WT.09.1705 | Gypsum Board Ceiling Second Fix - Second Floor Wet Areas | 0 | 2025-09-14
MOC.CN.F2.WT.09.1455 | First and Second painting coats - Second Floor Wet Areas | 0 | 2025-09-20
MOC.CN.F2.WT.08.1400 | Wooden Doors installation - Second Floor Wet Areas | 0 | 2025-09-24
MOC.CN.F2.WT.10.1790 | HPL partition installation - Second Floor Wet Areas | 0 | 2025-10-01
MOC.CN.F2.WT.10.1775 | Signage works - Second Floor Wet Areas | 0 | 2025-10-01
MOC.CN.F2.WT.09.1460 | Final painting coat - Second Floor Wet Areas | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.F2.WT.FIN.FLR Flooring |  | 1.74 | 2025-10-09
MOC.CN.F2.WT.07.1330 | Water proofing for wet areas - Second Floor Wet Areas | 40 | 2025-07-27
MOC.CN.F2.WT.09.1525 | Marble tiles works - Second Floor Wet Areas | 0 | 2025-08-30
MOC.CN.F2.WT.09.1515 | Porcelain tiles for Flooring - Second Floor Wet Areas | 0 | 2025-09-02
MOC.CN.F2.WT.09.1690 | Skirting Installation - Second Floor Wet Areas | 0 | 2025-09-13
MOC.CN.F2.WT.10.1770 | Toilet Accessories and Fixtures Installation - Second Floor Wet Areas | 0 | 2025-10-09
MOC.REV.R06.U0200725.CON.F2.WT.MEP MEP |  | 45.85 | 2025-10-13
MOC.REV.R06.U0200725.CON.F2.WT.MEP.PL Plumbing |  | 45.65 | 2025-10-13
MOC.CN.F2.WT.15.2305 | Water Supply pipes installation & Testing - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.15.1915 | Valves and accessories for Water Supply System - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.15.2420 | Water Supply pipes insulation - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.15.2295 | Drainage pipes installation & Testing - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.15.1945 | Plumbing Fixtures Installations - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.15.1915[R] | Valves and accessories for Water Supply System - Second Floor Wet Areas [Remaining] | 0 | 2025-07-22
MOC.CN.F2.WT.15.2420[R] | Water Supply pipes insulation - Second Floor Wet Areas [Remaining] | 0 | 2025-07-22
MOC.CN.F2.WT.15.2305[R] | Water Supply pipes installation & Testing - Second Floor Wet Areas [Remaining] | 0 | 2025-07-29
MOC.CN.F2.WT.15.2295[R] | Drainage pipes installation & Testing - Second Floor Wet Areas [Remaining] | 0 | 2025-07-31
MOC.CN.F2.WT.15.1925 | Electrical water heater - Second Floor Wet Areas | 0 | 2025-09-02
MOC.CN.F2.WT.15.2315 | Floor Drain Installation - Second Floor Wet Areas | 0 | 2025-09-10
MOC.CN.F2.WT.15.1945[R] | Plumbing Fixtures Installations - Second Floor Wet Areas [Remaining] | 0 | 2025-10-13
MOC.REV.R06.U0200725.CON.F2.WT.MEP.EL Electrical |  | 49.48 | 2025-09-27
MOC.REV.R06.U0200725.CON.F2.WT.MEP.EL.EP Electrical Power |  | 49.48 | 2025-09-27
MOC.CN.F2.WT.16.2655 | Conduits and boxes installation - Second Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.F2.WT.16.2655[R] | Conduits and boxes installation - Second Floor Wet Areas [Remaining] | 75 | 2025-07-22
MOC.CN.F2.WT.16.2630 | Cables & Wiring Installation - Second Floor Wet Areas | 50 | 2025-07-30
MOC.CN.F2.WT.16.2490 | Lighting fixtures installation - Second Floor Wet Areas | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.GF Ground Floor |  | 51.65 | 2025-10-25
MOC.REV.R06.U0200725.CON.GF.Z1 Zone 01 |  | 44.41 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.FIN Finishes |  | 42.78 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.FIN.C&W Ceiling & Walls |  | 48.1 | 2025-10-20
MOC.CN.GF.Z1.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 01 | 100 | 25-Feb-25 A
MOC.CN.GF.Z1.04.1175 | Masonary works - Ground Floor Zone 01 | 100 | 31-Mar-25 A
MOC.CN.GF.Z1.09.1740 | Plaster First Stage - Ground Floor Zone 01 | 100 | 01-Apr-25 A
MOC.CN.GF.Z1.09.1745 | Plaster Second Stage - Ground Floor Zone 01 | 100 | 08-Apr-25 A
MOC.CN.GF.Z1.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 01 | 100 | 23-Apr-25 A
MOC.CN.GF.Z1.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 01 | 100 | 03-May-25 A
MOC.CN.GF.Z1.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.09.1455 | First and Second painting coats - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.10.1785 | GLASS partiton - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 01 | 100 | 18-Jun-25 A
MOC.CN.GF.Z1.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 01 | 85 | 2025-08-11
MOC.CN.GF.Z1.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 01 | 0 | 2025-08-30
MOC.CN.GF.Z1.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 01 | 50 | 2025-09-06
MOC.CN.GF.Z1.09.1455[R] | First and Second painting coats - Ground Floor Zone 01 [Remaining] | 45 | 2025-09-06
MOC.CN.GF.Z1.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 01 [Remaining] | 25 | 2025-09-09
MOC.CN.GF.Z1.08.1430 | Doors Frame installation - Ground Floor Zone 01 | 0 | 2025-09-10
MOC.CN.GF.Z1.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 01 | 0 | 2025-09-13
MOC.CN.GF.Z1.08.1400 | Wooden Doors installation - Ground Floor Zone 01 | 0 | 2025-09-18
MOC.CN.GF.Z1.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 01 | 0 | 2025-09-18
MOC.CN.GF.Z1.09.1765 | Cornice Installation - Ground Floor Zone 01 | 0 | 2025-09-20
MOC.CN.GF.Z1.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 01 | 0 | 2025-09-22
MOC.CN.GF.Z1.09.1710 | Metal Suspended Ceiling First Fix - Ground Floor Zone 01 | 0 | 2025-09-24
MOC.CN.GF.Z1.10.2780 | Elevator Finishes - Ground Floor Zone 01 | 0 | 2025-10-01
MOC.CN.GF.Z1.10.1775 | Signage works - Ground Floor Zone 01 | 0 | 2025-10-02
MOC.CN.GF.Z1.10.1785[R] | GLASS partiton - Ground Floor Zone 01 [Remaining] | 70 | 2025-10-04
MOC.CN.GF.Z1.09.1460 | Final painting coat - Ground Floor Zone 01 | 0 | 2025-10-05
MOC.CN.GF.Z1.09.1715 | Metal Suspended Ceiling Second Fix - Ground Floor Zone 01 | 0 | 2025-10-12
MOC.CN.GF.Z1.05.1220 | Metal Handles for stairs - Ground Floor Zone 01 | 0 | 2025-10-13
MOC.CN.GF.Z1.10.1795 | Curtain Installation - Ground Floor Zone 01 | 0 | 2025-10-16
MOC.CN.GF.Z1.18.01 | Final Touch Up - Ground Floor Zone 01 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.FIN.FLR Flooring |  | 28.39 | 2025-10-20
MOC.CN.GF.Z1.09.1640 | Raised Floor First Fix - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 01 | 100 | 19-Jun-25 A
MOC.CN.GF.Z1.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 01 [Remaining] | 40 | 2025-09-29
MOC.CN.GF.Z1.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 01 [Remaining] | 40 | 2025-10-04
MOC.CN.GF.Z1.09.1515 | Porcelain tiles for Flooring - Ground Floor Zone 01 | 0 | 2025-10-11
MOC.CN.GF.Z1.09.1595 | Carpet Installation - Ground Floor Zone 01 | 0 | 2025-10-15
MOC.CN.GF.Z1.09.1690 | Skirting Installation - Ground Floor Zone 01 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.MEP MEP |  | 45.15 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.MEC Mechanical |  | 76.98 | 2025-10-04
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.MEC.PL Plumbing |  | 32.09 | 2025-09-13
MOC.CN.GF.Z1.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 01 | 100 | 01-Apr-25 A
MOC.CN.GF.Z1.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 01 | 100 | 07-Apr-25 A
MOC.CN.GF.Z1.15.2420 | Water Supply pipes insulation - Ground Floor Zone 01 | 100 | 07-Apr-25 A
MOC.CN.GF.Z1.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 01 [Remaining] | 100 | 15-Jun-25 A
MOC.CN.GF.Z1.15.2220 | Stainless Steel water tanks - Ground Floor Zone 01 | 0 | 2025-08-18
MOC.CN.GF.Z1.15.2315 | Floor Drain Installation - Ground Floor Zone 01 | 0 | 2025-09-13
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.MEC.FF Fire Fightig |  | 82.15 | 2025-10-04
MOC.CN.GF.Z1.15.2405 | Liquefied-Petroleum Gas Pipes Installation & Testing - Ground Floor Zone 01 | 100 | 16-Feb-25 A
MOC.CN.GF.Z1.15.2410 | Liquefied-Petroleum Gas valves installation - Ground Floor Zone 01 | 100 | 16-Feb-25 A
MOC.CN.GF.Z1.15.2425 | Foam System - Pipes Installation & Testing - Ground Floor Zone 01 | 100 | 23-Mar-25 A
MOC.CN.GF.Z1.15.2415 | Liquefied-Petroleum Gas System installation - Ground Floor Zone 01 | 100 | 30-Apr-25 A
MOC.CN.GF.Z1.15.2430 | Foam System - Foam Tank installation - Ground Floor Zone 01 | 100 | 26-May-25 A
MOC.CN.GF.Z1.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 01 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 01 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z1.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 01 [Remaining] | 0 | 2025-07-29
MOC.CN.GF.Z1.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-09-11
MOC.CN.GF.Z1.15.1985 | Fire sprinklers installation - Ground Floor Zone 01 | 0 | 2025-09-15
MOC.CN.GF.Z1.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 01 | 0 | 2025-09-21
MOC.CN.GF.Z1.15.1980 | Fire extinguishers installation - Ground Floor Zone 01 | 0 | 2025-09-22
MOC.CN.GF.Z1.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 01 | 0 | 2025-09-25
MOC.CN.GF.Z1.15.2435 | Foam System - Sprinklers installation - Ground Floor Zone 01 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.MEC.HV HVAC |  | 73.86 | 2025-09-25
MOC.CN.GF.Z1.15.2290 | Kitchen filtration unit - Ground Floor Zone 01 | 100 | 30-Apr-25 A
MOC.CN.GF.Z1.15.2275 | Thermostat Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2320 | Air Handling pipes installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2380 | Duct Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2395 | HVAC Valves installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2385 | Duct Insulation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2390 | Duct Lining - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.15.2340 | Fan Coil Units Installation - Ground Floor Zone 01 | 100 | 18-Jun-25 A
MOC.CN.GF.Z1.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 01 | 100 | 14-Jul-25 A
MOC.CN.GF.Z1.15.2380[R] | Duct Installation - Ground Floor Zone 01 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z1.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 01 [Remaining] | 95 | 2025-07-24
MOC.CN.GF.Z1.15.2395[R] | HVAC Valves installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-07-24
MOC.CN.GF.Z1.15.2385[R] | Duct Insulation - Ground Floor Zone 01 [Remaining] | 95 | 2025-07-24
MOC.CN.GF.Z1.15.2390[R] | Duct Lining - Ground Floor Zone 01 [Remaining] | 95 | 2025-07-24
MOC.CN.GF.Z1.15.2375[R] | HVAC Pipes Insulation - Ground Floor Zone 01 [Remaining] | 0 | 2025-07-27
MOC.CN.GF.Z1.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-08-24
MOC.CN.GF.Z1.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 01 | 0 | 2025-09-04
MOC.CN.GF.Z1.15.2100 | Air Diffusers Installation - Ground Floor Zone 01 | 0 | 2025-09-24
MOC.CN.GF.Z1.15.2275[R] | Thermostat Installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-09-24
MOC.CN.GF.Z1.15.2325 | Air Handling units installation - Ground Floor Zone 01 | 0 | 2025-09-25
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL Electrical |  | 27.83 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.EP Electrical Power |  | 47.16 | 2025-10-20
MOC.CN.GF.Z1.16.2655 | Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2630 | Cables & Wiring Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2745 | Wiring Installation in floors - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 01 [Remaining] | 85 | 2025-07-22
MOC.CN.GF.Z1.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 01 [Remaining] | 40 | 2025-07-28
MOC.CN.GF.Z1.16.2745[R] | Wiring Installation in floors - Ground Floor Zone 01 [Remaining] | 40 | 2025-08-04
MOC.CN.GF.Z1.16.2625 | Earthing System installation - Ground Floor Zone 01 | 0 | 2025-08-20
MOC.CN.GF.Z1.16.2715 | Distribution board installation - Ground Floor Zone 01 | 0 | 2025-09-25
MOC.CN.GF.Z1.16.2495 | Sockets and Switches installation - Ground Floor Zone 01 | 0 | 2025-09-28
MOC.CN.GF.Z1.16.2490 | Lighting fixtures installation - Ground Floor Zone 01 | 0 | 2025-10-02
MOC.CN.GF.Z1.16.2750 | Floor Sockets Installation - Ground Floor Zone 01 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.AV Audio Visual |  | 40 | 2025-09-16
MOC.CN.GF.Z1.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 01 | 100 | 24-Apr-25 A
MOC.CN.GF.Z1.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2740[R] | Audiovisual system Wiring Installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-08-03
MOC.CN.GF.Z1.16.2515 | Audiovisual system installation - Ground Floor Zone 01 | 0 | 2025-09-16
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.LC Lighting Control |  | 1.52 | 2025-09-29
MOC.CN.GF.Z1.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z1.16.2660 | Lighting Control System installation - Ground Floor Zone 01 | 0 | 2025-09-28
MOC.CN.GF.Z1.16.2530 | UPS installation - Ground Floor Zone 01 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-24
MOC.CN.GF.Z1.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 01 [Remaining] | 0 | 2025-08-04
MOC.CN.GF.Z1.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 01 | 0 | 2025-09-24
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.SS Security System |  | 2.31 | 2025-09-27
MOC.CN.GF.Z1.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2695 | Security System Wiring Installation - Ground Floor Zone 01 | 0 | 2025-08-05
MOC.CN.GF.Z1.16.2640 | Security System Installation - Ground Floor Zone 01 | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-25
MOC.CN.GF.Z1.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 01 | 0 | 2025-08-05
MOC.CN.GF.Z1.16.2645 | IPTV System installation - Ground Floor Zone 01 | 0 | 2025-09-25
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.39 | 2025-09-28
MOC.CN.GF.Z1.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 01 | 100 | 31-May-25 A
MOC.CN.GF.Z1.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 01 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z1.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 01 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.PA Public Address System |  | 33.33 | 2025-09-27
MOC.CN.GF.Z1.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 01 | 0 | 2025-08-05
MOC.CN.GF.Z1.16.2525 | Public Address System installation - Ground Floor Zone 01 | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.GF.Z1.MEP.EL.CBS Central Battery |  | 95 | 2025-07-22
MOC.CN.GF.Z1.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 01 | 100 | 05-May-25 A
MOC.CN.GF.Z1.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 01 | 90 | 2025-07-22
MOC.REV.R06.U0200725.CON.GF.Z2 Zone 02 |  | 57.58 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z2.FIN Finishes |  | 69.33 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z2.FIN.C&W Ceiling & Walls |  | 73.13 | 2025-10-18
MOC.CN.GF.Z2.04.1175 | Masonary works - Ground Floor Zone 02 | 100 | 11-Feb-25 A
MOC.CN.GF.Z2.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 02 | 100 | 25-Feb-25 A
MOC.CN.GF.Z2.09.1740 | Plaster First Stage - Ground Floor Zone 02 | 100 | 01-Apr-25 A
MOC.CN.GF.Z2.09.1745 | Plaster Second Stage - Ground Floor Zone 02 | 100 | 08-Apr-25 A
MOC.CN.GF.Z2.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 02 | 100 | 20-Apr-25 A
MOC.CN.GF.Z2.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 02 | 100 | 21-Apr-25 A
MOC.CN.GF.Z2.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1455 | First and Second painting coats - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.10.1785 | GLASS partiton - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 02 | 100 | 21-Jun-25 A
MOC.CN.GF.Z2.09.1700[R] | Gypsum Board Ceiling First Fix - Ground Floor Zone 02 [Remaining] | 100 | 29-Jun-25 A
MOC.CN.GF.Z2.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 02 [Remaining] | 100 | 06-Jul-25 A
MOC.CN.GF.Z2.09.1670[R] | Acoustic Ceiling First Fix - Ground Floor Zone 02 [Remaining] | 100 | 07-Jul-25 A
MOC.CN.GF.Z2.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 02 | 10 | 2025-08-28
MOC.CN.GF.Z2.09.1455[R] | First and Second painting coats - Ground Floor Zone 02 [Remaining] | 40 | 2025-09-04
MOC.CN.GF.Z2.08.1430 | Doors Frame installation - Ground Floor Zone 02 | 0 | 2025-09-06
MOC.CN.GF.Z2.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 02 | 90 | 2025-09-09
MOC.CN.GF.Z2.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 02 | 80 | 2025-09-11
MOC.CN.GF.Z2.08.1400 | Wooden Doors installation - Ground Floor Zone 02 | 0 | 2025-09-13
MOC.CN.GF.Z2.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 02 | 0 | 2025-09-18
MOC.CN.GF.Z2.09.1765 | Cornice Installation - Ground Floor Zone 02 | 0 | 2025-09-21
MOC.CN.GF.Z2.10.1785[R] | GLASS partiton - Ground Floor Zone 02 [Remaining] | 85 | 2025-09-25
MOC.CN.GF.Z2.10.1775 | Signage works - Ground Floor Zone 02 | 0 | 2025-09-27
MOC.CN.GF.Z2.10.2780 | Elevator Finishes - Ground Floor Zone 02 | 0 | 2025-09-30
MOC.CN.GF.Z2.09.1460 | Final painting coat - Ground Floor Zone 02 | 0 | 2025-10-06
MOC.CN.GF.Z2.05.1220 | Metal Handles for stairs - Ground Floor Zone 02 | 0 | 2025-10-14
MOC.CN.GF.Z2.10.1795 | Curtain Installation - Ground Floor Zone 02 | 0 | 2025-10-18
MOC.CN.GF.Z2.18.01 | Final Touch Up - Ground Floor Zone 02 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z2.FIN.FLR Flooring |  | 57.38 | 2025-10-15
MOC.CN.GF.Z2.09.1640 | Raised Floor First Fix - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 02 | 100 | 18-Jun-25 A
MOC.CN.GF.Z2.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 02 [Remaining] | 100 | 22-Jun-25 A
MOC.CN.GF.Z2.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 02 [Remaining] | 100 | 25-Jun-25 A
MOC.CN.GF.Z2.09.1595 | Carpet Installation - Ground Floor Zone 02 | 0 | 2025-10-11
MOC.CN.GF.Z2.09.1690 | Skirting Installation - Ground Floor Zone 02 | 0 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z2.MEP MEP |  | 49.67 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.MEC Mechanical |  | 65.78 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.MEC.PL Plumbing |  | 68.75 | 2025-10-02
MOC.CN.GF.Z2.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 02 | 100 | 26-Mar-25 A
MOC.CN.GF.Z2.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 02 | 100 | 07-Apr-25 A
MOC.CN.GF.Z2.15.2420 | Water Supply pipes insulation - Ground Floor Zone 02 | 100 | 07-Apr-25 A
MOC.CN.GF.Z2.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 02 [Remaining] | 0 | 2025-07-22
MOC.CN.GF.Z2.15.2315 | Floor Drain Installation - Ground Floor Zone 02 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.MEC.FF Fire Fightig |  | 57.47 | 2025-10-01
MOC.CN.GF.Z2.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 02 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z2.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 02 [Remaining] | 0 | 2025-07-27
MOC.CN.GF.Z2.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 02 [Remaining] | 0 | 2025-09-11
MOC.CN.GF.Z2.15.1980 | Fire extinguishers installation - Ground Floor Zone 02 | 0 | 2025-09-21
MOC.CN.GF.Z2.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 02 | 0 | 2025-09-24
MOC.CN.GF.Z2.15.1985 | Fire sprinklers installation - Ground Floor Zone 02 | 0 | 2025-09-29
MOC.CN.GF.Z2.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 02 | 0 | 2025-10-01
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.MEC.HV HVAC |  | 67.98 | 2025-09-27
MOC.CN.GF.Z2.15.2275 | Thermostat Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2320 | Air Handling pipes installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2380 | Duct Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2395 | HVAC Valves installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2385 | Duct Insulation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2390 | Duct Lining - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.15.2340 | Fan Coil Units Installation - Ground Floor Zone 02 | 100 | 17-Jun-25 A
MOC.CN.GF.Z2.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 02 | 100 | 13-Jul-25 A
MOC.CN.GF.Z2.15.2380[R] | Duct Installation - Ground Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z2.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z2.15.2385[R] | Duct Insulation - Ground Floor Zone 02 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z2.15.2375[R] | HVAC Pipes Insulation - Ground Floor Zone 02 [Remaining] | 0 | 2025-07-26
MOC.CN.GF.Z2.15.2395[R] | HVAC Valves installation - Ground Floor Zone 02 [Remaining] | 20 | 2025-07-27
MOC.CN.GF.Z2.15.2390[R] | Duct Lining - Ground Floor Zone 02 [Remaining] | 0 | 2025-08-02
MOC.CN.GF.Z2.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 02 [Remaining] | 0 | 2025-08-17
MOC.CN.GF.Z2.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 02 | 0 | 2025-09-03
MOC.CN.GF.Z2.15.2275[R] | Thermostat Installation - Ground Floor Zone 02 [Remaining] | 0 | 2025-09-17
MOC.CN.GF.Z2.15.2100 | Air Diffusers Installation - Ground Floor Zone 02 | 0 | 2025-09-24
MOC.CN.GF.Z2.15.2325 | Air Handling units installation - Ground Floor Zone 02 | 0 | 2025-09-27
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL Electrical |  | 44.12 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.EP Electrical Power |  | 47.99 | 2025-10-15
MOC.CN.GF.Z2.16.2655 | Conduits and boxes installation - Ground Floor Zone 02 | 100 | 04-May-25 A
MOC.CN.GF.Z2.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 02 | 100 | 05-May-25 A
MOC.CN.GF.Z2.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2630 | Cables & Wiring Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2745 | Wiring Installation in floors - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 02 [Remaining] | 100 | 18-Jun-25 A
MOC.CN.GF.Z2.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 02 [Remaining] | 45 | 2025-07-26
MOC.CN.GF.Z2.16.2745[R] | Wiring Installation in floors - Ground Floor Zone 02 [Remaining] | 80 | 2025-07-28
MOC.CN.GF.Z2.16.2625 | Earthing System installation - Ground Floor Zone 02 | 0 | 2025-08-13
MOC.CN.GF.Z2.16.2715 | Distribution board installation - Ground Floor Zone 02 | 0 | 2025-09-16
MOC.CN.GF.Z2.16.2495 | Sockets and Switches installation - Ground Floor Zone 02 | 0 | 2025-09-24
MOC.CN.GF.Z2.16.2490 | Lighting fixtures installation - Ground Floor Zone 02 | 0 | 2025-09-30
MOC.CN.GF.Z2.16.2750 | Floor Sockets Installation - Ground Floor Zone 02 | 0 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.AV Audio Visual |  | 33.33 | 2025-09-22
MOC.CN.GF.Z2.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 02 | 100 | 05-May-25 A
MOC.CN.GF.Z2.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 02 | 0 | 2025-08-05
MOC.CN.GF.Z2.16.2515 | Audiovisual system installation - Ground Floor Zone 02 | 0 | 2025-09-22
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.LC Lighting Control |  | 71.47 | 2025-09-29
MOC.CN.GF.Z2.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 02 | 100 | 05-May-25 A
MOC.CN.GF.Z2.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 02 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z2.16.2660 | Lighting Control System installation - Ground Floor Zone 02 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-25
MOC.CN.GF.Z2.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 02 [Remaining] | 0 | 2025-08-06
MOC.CN.GF.Z2.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 02 | 0 | 2025-09-25
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.SS Security System |  | 2.31 | 2025-09-18
MOC.CN.GF.Z2.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2695 | Security System Wiring Installation - Ground Floor Zone 02 | 0 | 2025-07-31
MOC.CN.GF.Z2.16.2640 | Security System Installation - Ground Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-18
MOC.CN.GF.Z2.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 02 | 0 | 2025-07-31
MOC.CN.GF.Z2.16.2645 | IPTV System installation - Ground Floor Zone 02 | 0 | 2025-09-18
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.84 | 2025-09-28
MOC.CN.GF.Z2.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 02 [Remaining] | 90 | 2025-08-07
MOC.CN.GF.Z2.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 02 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.PA Public Address System |  | 33.33 | 2025-09-28
MOC.CN.GF.Z2.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 02 | 0 | 2025-08-05
MOC.CN.GF.Z2.16.2525 | Public Address System installation - Ground Floor Zone 02 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z2.MEP.EL.CBS Central Battery |  | 96.5 | 2025-07-21
MOC.CN.GF.Z2.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 02 | 100 | 06-May-25 A
MOC.CN.GF.Z2.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 02 | 100 | 31-May-25 A
MOC.CN.GF.Z2.16.2690[R] | Central Battery System Wiring Installation - Ground Floor Zone 02 [Remaining] | 90 | 2025-07-21
MOC.REV.R06.U0200725.CON.GF.Z3 Zone 03 |  | 55.91 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z3.FIN Finishes |  | 49.34 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z3.FIN.C&W Ceiling & Walls |  | 50.58 | 2025-10-22
MOC.CN.GF.Z3.04.1175 | Masonary works - Ground Floor Zone 03 | 100 | 11-Feb-25 A
MOC.CN.GF.Z3.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 03 | 100 | 25-Feb-25 A
MOC.CN.GF.Z3.09.1740 | Plaster First Stage - Ground Floor Zone 03 | 100 | 01-Apr-25 A
MOC.CN.GF.Z3.09.1745 | Plaster Second Stage - Ground Floor Zone 03 | 100 | 10-Apr-25 A
MOC.CN.GF.Z3.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 03 | 100 | 23-Apr-25 A
MOC.CN.GF.Z3.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 03 | 100 | 30-Apr-25 A
MOC.CN.GF.Z3.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.09.1455 | First and Second painting coats - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.10.1785 | GLASS partiton - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 03 | 100 | 15-Jun-25 A
MOC.CN.GF.Z3.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 03 | 100 | 23-Jun-25 A
MOC.CN.GF.Z3.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 03 [Remaining] | 40 | 2025-08-12
MOC.CN.GF.Z3.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 03 | 90 | 2025-08-17
MOC.CN.GF.Z3.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 03 | 10 | 2025-08-31
MOC.CN.GF.Z3.08.1430 | Doors Frame installation - Ground Floor Zone 03 | 0 | 2025-09-06
MOC.CN.GF.Z3.09.1455[R] | First and Second painting coats - Ground Floor Zone 03 [Remaining] | 40 | 2025-09-07
MOC.CN.GF.Z3.08.1400 | Wooden Doors installation - Ground Floor Zone 03 | 0 | 2025-09-13
MOC.CN.GF.Z3.10.1785[R] | GLASS partiton - Ground Floor Zone 03 [Remaining] | 70 | 2025-09-15
MOC.CN.GF.Z3.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 03 | 25 | 2025-09-18
MOC.CN.GF.Z3.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 03 | 0 | 2025-09-20
MOC.CN.GF.Z3.09.1765 | Cornice Installation - Ground Floor Zone 03 | 0 | 2025-09-24
MOC.CN.GF.Z3.10.1775 | Signage works - Ground Floor Zone 03 | 0 | 2025-09-27
MOC.CN.GF.Z3.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 03 | 0 | 2025-09-29
MOC.CN.GF.Z3.10.2780 | Elevator Finishes - Ground Floor Zone 03 | 0 | 2025-10-02
MOC.CN.GF.Z3.09.1460 | Final painting coat - Ground Floor Zone 03 | 0 | 2025-10-12
MOC.CN.GF.Z3.10.1795 | Curtain Installation - Ground Floor Zone 03 | 0 | 2025-10-14
MOC.CN.GF.Z3.05.1220 | Metal Handles for stairs - Ground Floor Zone 03 | 0 | 2025-10-20
MOC.CN.GF.Z3.18.01 | Final Touch Up - Ground Floor Zone 03 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z3.FIN.FLR Flooring |  | 45.91 | 2025-10-20
MOC.CN.GF.Z3.09.1640 | Raised Floor First Fix - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 03 [Remaining] | 100 | 12-Jul-25 A
MOC.CN.GF.Z3.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 03 [Remaining] | 100 | 12-Jul-25 A
MOC.CN.GF.Z3.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 03 | 0 | 2025-09-22
MOC.CN.GF.Z3.09.1595 | Carpet Installation - Ground Floor Zone 03 | 0 | 2025-10-15
MOC.CN.GF.Z3.09.1515 | Porcelain tiles for Flooring - Ground Floor Zone 03 | 0 | 2025-10-15
MOC.CN.GF.Z3.09.1695 | Rubber roll flooring - Ground Floor Zone 03 | 0 | 2025-10-18
MOC.CN.GF.Z3.09.1690 | Skirting Installation - Ground Floor Zone 03 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z3.MEP MEP |  | 58.33 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.MEC Mechanical |  | 65.7 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.MEC.PL Plumbing |  | 68.75 | 2025-09-28
MOC.CN.GF.Z3.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 03 | 100 | 27-Mar-25 A
MOC.CN.GF.Z3.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 03 | 100 | 07-Apr-25 A
MOC.CN.GF.Z3.15.2420 | Water Supply pipes insulation - Ground Floor Zone 03 | 100 | 07-Apr-25 A
MOC.CN.GF.Z3.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-29
MOC.CN.GF.Z3.15.2315 | Floor Drain Installation - Ground Floor Zone 03 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.MEC.FF Fire Fightig |  | 57.09 | 2025-10-07
MOC.CN.GF.Z3.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 03 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 03 [Remaining] | 95 | 2025-07-21
MOC.CN.GF.Z3.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-30
MOC.CN.GF.Z3.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-09-18
MOC.CN.GF.Z3.15.1980 | Fire extinguishers installation - Ground Floor Zone 03 | 0 | 2025-09-24
MOC.CN.GF.Z3.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 03 | 0 | 2025-09-28
MOC.CN.GF.Z3.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.CN.GF.Z3.15.1985 | Fire sprinklers installation - Ground Floor Zone 03 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.MEC.HV HVAC |  | 70.88 | 2025-10-06
MOC.CN.GF.Z3.15.2275 | Thermostat Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2320 | Air Handling pipes installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2380 | Duct Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2395 | HVAC Valves installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2385 | Duct Insulation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2390 | Duct Lining - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2340 | Fan Coil Units Installation - Ground Floor Zone 03 | 100 | 30-Jun-25 A
MOC.CN.GF.Z3.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 03 | 100 | 13-Jul-25 A
MOC.CN.GF.Z3.15.2380[R] | Duct Installation - Ground Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z3.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 03 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z3.15.2385[R] | Duct Insulation - Ground Floor Zone 03 [Remaining] | 90 | 2025-07-23
MOC.CN.GF.Z3.15.2390[R] | Duct Lining - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-26
MOC.CN.GF.Z3.15.2375[R] | HVAC Pipes Insulation - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-28
MOC.CN.GF.Z3.15.2395[R] | HVAC Valves installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-29
MOC.CN.GF.Z3.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-08-14
MOC.CN.GF.Z3.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 03 | 0 | 2025-09-03
MOC.CN.GF.Z3.15.2275[R] | Thermostat Installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-09-17
MOC.CN.GF.Z3.15.2325 | Air Handling units installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.CN.GF.Z3.15.2100 | Air Diffusers Installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.MEC.BMS BMS |  | 65 | 2025-10-14
MOC.CN.GF.Z3.15.2125 | BMS - First fix - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2130 | BMS - Second Fix - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.15.2125[R] | BMS - First fix - Ground Floor Zone 03 [Remaining] | 90 | 2025-08-07
MOC.CN.GF.Z3.15.2130[R] | BMS - Second Fix - Ground Floor Zone 03 [Remaining] | 10 | 2025-08-28
MOC.CN.GF.Z3.15.2135 | BMS installation - Ground Floor Zone 03 | 0 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL Electrical |  | 44.93 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.EP Electrical Power |  | 48.98 | 2025-10-18
MOC.CN.GF.Z3.16.2655 | Conduits and boxes installation - Ground Floor Zone 03 | 100 | 05-May-25 A
MOC.CN.GF.Z3.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2630 | Cables & Wiring Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2745 | Wiring Installation in floors - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 03 [Remaining] | 80 | 2025-07-22
MOC.CN.GF.Z3.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 03 [Remaining] | 45 | 2025-07-27
MOC.CN.GF.Z3.16.2745[R] | Wiring Installation in floors - Ground Floor Zone 03 [Remaining] | 70 | 2025-07-29
MOC.CN.GF.Z3.16.2625 | Earthing System installation - Ground Floor Zone 03 | 0 | 2025-08-14
MOC.CN.GF.Z3.16.2715 | Distribution board installation - Ground Floor Zone 03 | 0 | 2025-09-25
MOC.CN.GF.Z3.16.2495 | Sockets and Switches installation - Ground Floor Zone 03 | 0 | 2025-10-02
MOC.CN.GF.Z3.16.2490 | Lighting fixtures installation - Ground Floor Zone 03 | 0 | 2025-10-07
MOC.CN.GF.Z3.16.2750 | Floor Sockets Installation - Ground Floor Zone 03 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-06
MOC.CN.GF.Z3.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 03 | 100 | 24-Apr-25 A
MOC.CN.GF.Z3.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 03 | 0 | 2025-08-05
MOC.CN.GF.Z3.16.2515 | Audiovisual system installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.LC Lighting Control |  | 71.47 | 2025-10-06
MOC.CN.GF.Z3.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 03 | 100 | 04-May-25 A
MOC.CN.GF.Z3.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z3.16.2660 | Lighting Control System installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-10-06
MOC.CN.GF.Z3.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-08-02
MOC.CN.GF.Z3.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.SS Security System |  | 2.31 | 2025-10-06
MOC.CN.GF.Z3.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2695 | Security System Wiring Installation - Ground Floor Zone 03 | 0 | 2025-08-05
MOC.CN.GF.Z3.16.2640 | Security System Installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-10-06
MOC.CN.GF.Z3.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 03 | 0 | 2025-08-05
MOC.CN.GF.Z3.16.2645 | IPTV System installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.84 | 2025-10-06
MOC.CN.GF.Z3.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 03 | 100 | 02-Apr-25 A
MOC.CN.GF.Z3.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 03 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z3.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.PA Public Address System |  | 55 | 2025-10-06
MOC.CN.GF.Z3.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 03 | 100 | 31-May-25 A
MOC.CN.GF.Z3.16.2730[R] | Public Address System Wiring Installation - Ground Floor Zone 03 [Remaining] | 0 | 2025-07-26
MOC.CN.GF.Z3.16.2525 | Public Address System installation - Ground Floor Zone 03 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z3.MEP.EL.CBS Central Battery |  | 95 | 2025-07-22
MOC.CN.GF.Z3.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 03 | 100 | 06-May-25 A
MOC.CN.GF.Z3.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 03 | 90 | 2025-07-22
MOC.REV.R06.U0200725.CON.GF.Z4 Zone 04 |  | 56.81 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z4.FIN Finishes |  | 65.36 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z4.FIN.C&W Ceiling & Walls |  | 65.62 | 2025-10-22
MOC.CN.GF.Z4.04.1175 | Masonary works - Ground Floor Zone 04 | 100 | 11-Feb-25 A
MOC.CN.GF.Z4.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 04 | 100 | 26-Feb-25 A
MOC.CN.GF.Z4.09.1740 | Plaster First Stage - Ground Floor Zone 04 | 100 | 01-Apr-25 A
MOC.CN.GF.Z4.09.1745 | Plaster Second Stage - Ground Floor Zone 04 | 100 | 10-Apr-25 A
MOC.CN.GF.Z4.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 04 | 100 | 19-Apr-25 A
MOC.CN.GF.Z4.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 04 | 100 | 20-Apr-25 A
MOC.CN.GF.Z4.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1455 | First and Second painting coats - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.10.1785 | GLASS partiton - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 04 | 100 | 15-Jun-25 A
MOC.CN.GF.Z4.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 04 [Remaining] | 100 | 18-Jun-25 A
MOC.CN.GF.Z4.09.1700[R] | Gypsum Board Ceiling First Fix - Ground Floor Zone 04 [Remaining] | 100 | 19-Jun-25 A
MOC.CN.GF.Z4.09.1670[R] | Acoustic Ceiling First Fix - Ground Floor Zone 04 [Remaining] | 100 | 30-Jun-25 A
MOC.CN.GF.Z4.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 04 | 10 | 2025-08-28
MOC.CN.GF.Z4.09.1455[R] | First and Second painting coats - Ground Floor Zone 04 [Remaining] | 40 | 2025-09-06
MOC.CN.GF.Z4.08.1430 | Doors Frame installation - Ground Floor Zone 04 | 0 | 2025-09-06
MOC.CN.GF.Z4.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 04 | 75 | 2025-09-09
MOC.CN.GF.Z4.10.1785[R] | GLASS partiton - Ground Floor Zone 04 [Remaining] | 90 | 2025-09-13
MOC.CN.GF.Z4.08.1400 | Wooden Doors installation - Ground Floor Zone 04 | 0 | 2025-09-13
MOC.CN.GF.Z4.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 04 | 25 | 2025-09-20
MOC.CN.GF.Z4.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 04 | 0 | 2025-09-20
MOC.CN.GF.Z4.10.2780 | Elevator Finishes - Ground Floor Zone 04 | 0 | 2025-10-01
MOC.CN.GF.Z4.10.1775 | Signage works - Ground Floor Zone 04 | 0 | 2025-10-02
MOC.CN.GF.Z4.09.1460 | Final painting coat - Ground Floor Zone 04 | 0 | 2025-10-05
MOC.CN.GF.Z4.05.1220 | Metal Handles for stairs - Ground Floor Zone 04 | 0 | 2025-10-13
MOC.CN.GF.Z4.09.1765 | Cornice Installation - Ground Floor Zone 04 | 0 | 2025-10-16
MOC.CN.GF.Z4.10.1795 | Curtain Installation - Ground Floor Zone 04 | 0 | 2025-10-16
MOC.CN.GF.Z4.18.01 | Final Touch Up - Ground Floor Zone 04 | 0 | 2025-10-22
MOC.REV.R06.U0200725.CON.GF.Z4.FIN.FLR Flooring |  | 64.89 | 2025-10-14
MOC.CN.GF.Z4.09.1640 | Raised Floor First Fix - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1525 | Marble tiles works - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 04 [Remaining] | 100 | 16-Jun-25 A
MOC.CN.GF.Z4.09.1525[R] | Marble tiles works - Ground Floor Zone 04 [Remaining] | 80 | 2025-09-08
MOC.CN.GF.Z4.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 04 | 0 | 2025-09-15
MOC.CN.GF.Z4.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 04 [Remaining] | 100 | 18-Sep-25 A
MOC.CN.GF.Z4.09.1515 | Porcelain tiles for Flooring - Ground Floor Zone 04 | 0 | 2025-10-07
MOC.CN.GF.Z4.09.1595 | Carpet Installation - Ground Floor Zone 04 | 0 | 2025-10-09
MOC.CN.GF.Z4.09.1690 | Skirting Installation - Ground Floor Zone 04 | 0 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z4.MEP MEP |  | 49.94 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.MEC Mechanical |  | 70.4 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.MEC.PL Plumbing |  | 73.42 | 2025-10-06
MOC.CN.GF.Z4.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 04 | 100 | 25-Mar-25 A
MOC.CN.GF.Z4.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 04 | 100 | 07-Apr-25 A
MOC.CN.GF.Z4.15.2420 | Water Supply pipes insulation - Ground Floor Zone 04 | 100 | 07-Apr-25 A
MOC.CN.GF.Z4.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 04 [Remaining] | 70 | 2025-07-21
MOC.CN.GF.Z4.15.2315 | Floor Drain Installation - Ground Floor Zone 04 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.MEC.FF Fire Fightig |  | 55.21 | 2025-09-29
MOC.CN.GF.Z4.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 04 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 04 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z4.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 04 [Remaining] | 0 | 2025-07-29
MOC.CN.GF.Z4.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 04 [Remaining] | 0 | 2025-09-15
MOC.CN.GF.Z4.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 04 | 0 | 2025-09-15
MOC.CN.GF.Z4.15.1980 | Fire extinguishers installation - Ground Floor Zone 04 | 0 | 2025-09-22
MOC.CN.GF.Z4.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.CN.GF.Z4.15.1985 | Fire sprinklers installation - Ground Floor Zone 04 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.MEC.HV HVAC |  | 75.22 | 2025-09-28
MOC.CN.GF.Z4.15.2275 | Thermostat Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2320 | Air Handling pipes installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2380 | Duct Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2395 | HVAC Valves installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2385 | Duct Insulation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2390 | Duct Lining - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.15.2340 | Fan Coil Units Installation - Ground Floor Zone 04 | 100 | 30-Jun-25 A
MOC.CN.GF.Z4.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 04 | 100 | 13-Jul-25 A
MOC.CN.GF.Z4.15.2380[R] | Duct Installation - Ground Floor Zone 04 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z4.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 04 [Remaining] | 90 | 2025-07-23
MOC.CN.GF.Z4.15.2385[R] | Duct Insulation - Ground Floor Zone 04 [Remaining] | 65 | 2025-07-26
MOC.CN.GF.Z4.15.2390[R] | Duct Lining - Ground Floor Zone 04 [Remaining] | 65 | 2025-07-29
MOC.CN.GF.Z4.15.2395[R] | HVAC Valves installation - Ground Floor Zone 04 [Remaining] | 0 | 2025-07-30
MOC.CN.GF.Z4.15.2375[R] | HVAC Pipes Insulation - Ground Floor Zone 04 [Remaining] | 0 | 2025-08-02
MOC.CN.GF.Z4.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 04 [Remaining] | 0 | 2025-08-17
MOC.CN.GF.Z4.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 04 | 0 | 2025-08-28
MOC.CN.GF.Z4.15.2275[R] | Thermostat Installation - Ground Floor Zone 04 [Remaining] | 0 | 2025-09-17
MOC.CN.GF.Z4.15.2325 | Air Handling units installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.CN.GF.Z4.15.2100 | Air Diffusers Installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL Electrical |  | 43.77 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.EP Electrical Power |  | 53.66 | 2025-10-14
MOC.CN.GF.Z4.16.2655 | Conduits and boxes installation - Ground Floor Zone 04 | 100 | 05-May-25 A
MOC.CN.GF.Z4.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 04 | 100 | 05-May-25 A
MOC.CN.GF.Z4.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2630 | Cables & Wiring Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2745 | Wiring Installation in floors - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 04 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z4.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 04 [Remaining] | 45 | 2025-07-27
MOC.CN.GF.Z4.16.2745[R] | Wiring Installation in floors - Ground Floor Zone 04 [Remaining] | 80 | 2025-07-29
MOC.CN.GF.Z4.16.2625 | Earthing System installation - Ground Floor Zone 04 | 0 | 2025-08-14
MOC.CN.GF.Z4.16.2715 | Distribution board installation - Ground Floor Zone 04 | 0 | 2025-09-17
MOC.CN.GF.Z4.16.2495 | Sockets and Switches installation - Ground Floor Zone 04 | 0 | 2025-09-25
MOC.CN.GF.Z4.16.2490 | Lighting fixtures installation - Ground Floor Zone 04 | 0 | 2025-09-30
MOC.CN.GF.Z4.16.2750 | Floor Sockets Installation - Ground Floor Zone 04 | 0 | 2025-10-14
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.AV Audio Visual |  | 36.67 | 2025-09-28
MOC.CN.GF.Z4.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 04 | 100 | 24-Apr-25 A
MOC.CN.GF.Z4.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 04 | 10 | 2025-08-04
MOC.CN.GF.Z4.16.2515 | Audiovisual system installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.LC Lighting Control |  | 71.47 | 2025-09-28
MOC.CN.GF.Z4.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 04 | 100 | 05-May-25 A
MOC.CN.GF.Z4.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 04 [Remaining] | 90 | 2025-07-22
MOC.CN.GF.Z4.16.2660 | Lighting Control System installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-28
MOC.CN.GF.Z4.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 04 | 100 | 06-May-25 A
MOC.CN.GF.Z4.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 04 [Remaining] | 0 | 2025-08-04
MOC.CN.GF.Z4.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.SS Security System |  | 2.31 | 2025-09-28
MOC.CN.GF.Z4.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 04 | 100 | 06-May-25 A
MOC.CN.GF.Z4.16.2695 | Security System Wiring Installation - Ground Floor Zone 04 | 0 | 2025-08-05
MOC.CN.GF.Z4.16.2640 | Security System Installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-28
MOC.CN.GF.Z4.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 04 | 100 | 06-May-25 A
MOC.CN.GF.Z4.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 04 | 0 | 2025-08-05
MOC.CN.GF.Z4.16.2645 | IPTV System installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.84 | 2025-09-28
MOC.CN.GF.Z4.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 04 | 100 | 02-Apr-25 A
MOC.CN.GF.Z4.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 04 | 100 | 31-May-25 A
MOC.CN.GF.Z4.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 04 [Remaining] | 90 | 2025-08-05
MOC.CN.GF.Z4.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.PA Public Address System |  | 33.33 | 2025-09-28
MOC.CN.GF.Z4.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 04 | 100 | 02-Apr-25 A
MOC.CN.GF.Z4.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 04 | 0 | 2025-08-05
MOC.CN.GF.Z4.16.2525 | Public Address System installation - Ground Floor Zone 04 | 0 | 2025-09-28
MOC.REV.R06.U0200725.CON.GF.Z4.MEP.EL.CBS Central Battery |  | 11.88 | 2025-10-13
MOC.CN.GF.Z4.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 04 | 100 | 02-Apr-25 A
MOC.CN.GF.Z4.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 04 | 90 | 2025-07-22
MOC.CN.GF.Z4.16.2635 | Central Battery System - Ground Floor Zone 04 | 0 | 2025-10-13
MOC.REV.R06.U0200725.CON.GF.Z5 Zone 05 |  | 47.69 | 2025-10-25
MOC.REV.R06.U0200725.CON.GF.Z5.FIN Finishes |  | 44.33 | 2025-10-25
MOC.REV.R06.U0200725.CON.GF.Z5.FIN.C&W Ceiling & Walls |  | 45.18 | 2025-10-25
MOC.CN.GF.Z5.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 05 | 100 | 27-Feb-25 A
MOC.CN.GF.Z5.04.1175 | Masonary works - Ground Floor Zone 05 | 100 | 31-Mar-25 A
MOC.CN.GF.Z5.09.1740 | Plaster First Stage - Ground Floor Zone 05 | 100 | 01-Apr-25 A
MOC.CN.GF.Z5.09.1745 | Plaster Second Stage - Ground Floor Zone 05 | 100 | 08-Apr-25 A
MOC.CN.GF.Z5.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 05 | 100 | 24-Apr-25 A
MOC.CN.GF.Z5.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 05 | 100 | 30-Apr-25 A
MOC.CN.GF.Z5.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.09.1455 | First and Second painting coats - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.10.1785 | GLASS partiton - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 05 | 100 | 24-Jun-25 A
MOC.CN.GF.Z5.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 05 [Remaining] | 10 | 2025-08-26
MOC.CN.GF.Z5.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 05 | 10 | 2025-09-02
MOC.CN.GF.Z5.09.1455[R] | First and Second painting coats - Ground Floor Zone 05 [Remaining] | 35 | 2025-09-06
MOC.CN.GF.Z5.08.1430 | Doors Frame installation - Ground Floor Zone 05 | 0 | 2025-09-09
MOC.CN.GF.Z5.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 05 | 0 | 2025-09-09
MOC.CN.GF.Z5.08.1400 | Wooden Doors installation - Ground Floor Zone 05 | 0 | 2025-09-16
MOC.CN.GF.Z5.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 05 | 0 | 2025-09-20
MOC.CN.GF.Z5.09.1725[R] | Wooden Cladding Second Fix - Ground Floor Zone 05 [Remaining] | 0 | 2025-09-20
MOC.CN.GF.Z5.10.1775 | Signage works - Ground Floor Zone 05 | 0 | 2025-09-21
MOC.CN.GF.Z5.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 05 | 0 | 2025-09-21
MOC.CN.GF.Z5.10.2780 | Elevator Finishes - Ground Floor Zone 05 | 0 | 2025-10-02
MOC.CN.GF.Z5.10.1785[R] | GLASS partiton - Ground Floor Zone 05 [Remaining] | 75 | 2025-10-04
MOC.CN.GF.Z5.09.1460 | Final painting coat - Ground Floor Zone 05 | 0 | 2025-10-08
MOC.CN.GF.Z5.05.1220 | Metal Handles for stairs - Ground Floor Zone 05 | 0 | 2025-10-16
MOC.CN.GF.Z5.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 05 | 20 | 2025-10-19
MOC.CN.GF.Z5.09.1765 | Cornice Installation - Ground Floor Zone 05 | 0 | 2025-10-20
MOC.CN.GF.Z5.10.1795 | Curtain Installation - Ground Floor Zone 05 | 0 | 2025-10-20
MOC.CN.GF.Z5.18.01 | Final Touch Up - Ground Floor Zone 05 | 0 | 2025-10-25
MOC.REV.R06.U0200725.CON.GF.Z5.FIN.FLR Flooring |  | 41.64 | 2025-10-18
MOC.CN.GF.Z5.09.1640 | Raised Floor First Fix - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 05 | 0 | 2025-09-17
MOC.CN.GF.Z5.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 05 [Remaining] | 40 | 2025-09-24
MOC.CN.GF.Z5.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 05 [Remaining] | 40 | 2025-10-01
MOC.CN.GF.Z5.09.1595 | Carpet Installation - Ground Floor Zone 05 | 0 | 2025-10-13
MOC.CN.GF.Z5.09.1690 | Skirting Installation - Ground Floor Zone 05 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z5.MEP MEP |  | 50.23 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.MEC Mechanical |  | 61.92 | 2025-09-30
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.MEC.PL Plumbing |  | 68.75 | 2025-09-25
MOC.CN.GF.Z5.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 05 | 100 | 05-Apr-25 A
MOC.CN.GF.Z5.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 05 | 100 | 07-Apr-25 A
MOC.CN.GF.Z5.15.2420 | Water Supply pipes insulation - Ground Floor Zone 05 | 100 | 07-Apr-25 A
MOC.CN.GF.Z5.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 05 [Remaining] | 0 | 2025-07-22
MOC.CN.GF.Z5.15.2315 | Floor Drain Installation - Ground Floor Zone 05 | 0 | 2025-09-25
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.MEC.FF Fire Fightig |  | 54.53 | 2025-09-30
MOC.CN.GF.Z5.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 05 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 05 [Remaining] | 80 | 2025-07-22
MOC.CN.GF.Z5.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 05 [Remaining] | 0 | 2025-07-28
MOC.CN.GF.Z5.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 05 [Remaining] | 0 | 2025-09-13
MOC.CN.GF.Z5.15.1980 | Fire extinguishers installation - Ground Floor Zone 05 | 0 | 2025-09-22
MOC.CN.GF.Z5.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 05 | 0 | 2025-09-28
MOC.CN.GF.Z5.15.1985 | Fire sprinklers installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.CN.GF.Z5.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 05 | 0 | 2025-09-30
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.MEC.HV HVAC |  | 63.96 | 2025-09-29
MOC.CN.GF.Z5.15.2275 | Thermostat Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2320 | Air Handling pipes installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2380 | Duct Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2395 | HVAC Valves installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2385 | Duct Insulation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2390 | Duct Lining - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.15.2380[R] | Duct Installation - Ground Floor Zone 05 [Remaining] | 70 | 2025-07-21
MOC.CN.GF.Z5.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 05 [Remaining] | 70 | 2025-07-23
MOC.CN.GF.Z5.15.2385[R] | Duct Insulation - Ground Floor Zone 05 [Remaining] | 30 | 2025-07-23
MOC.CN.GF.Z5.15.2375[R] | HVAC Pipes Insulation - Ground Floor Zone 05 [Remaining] | 0 | 2025-07-26
MOC.CN.GF.Z5.15.2390[R] | Duct Lining - Ground Floor Zone 05 [Remaining] | 30 | 2025-07-27
MOC.CN.GF.Z5.15.2395[R] | HVAC Valves installation - Ground Floor Zone 05 [Remaining] | 0 | 2025-07-27
MOC.CN.GF.Z5.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 05 | 0 | 2025-08-17
MOC.CN.GF.Z5.15.2340 | Fan Coil Units Installation - Ground Floor Zone 05 | 0 | 2025-08-19
MOC.CN.GF.Z5.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 05 [Remaining] | 0 | 2025-08-28
MOC.CN.GF.Z5.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 05 | 0 | 2025-09-10
MOC.CN.GF.Z5.15.2275[R] | Thermostat Installation - Ground Floor Zone 05 [Remaining] | 0 | 2025-09-21
MOC.CN.GF.Z5.15.2100 | Air Diffusers Installation - Ground Floor Zone 05 | 0 | 2025-09-28
MOC.CN.GF.Z5.15.2325 | Air Handling units installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL Electrical |  | 46.37 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.EP Electrical Power |  | 53.23 | 2025-10-15
MOC.CN.GF.Z5.16.2655 | Conduits and boxes installation - Ground Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.GF.Z5.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.GF.Z5.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2630 | Cables & Wiring Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2745 | Wiring Installation in floors - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 05 [Remaining] | 10 | 2025-07-27
MOC.CN.GF.Z5.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 05 [Remaining] | 40 | 2025-07-28
MOC.CN.GF.Z5.16.2745[R] | Wiring Installation in floors - Ground Floor Zone 05 [Remaining] | 70 | 2025-07-29
MOC.CN.GF.Z5.16.2625 | Earthing System installation - Ground Floor Zone 05 | 0 | 2025-08-14
MOC.CN.GF.Z5.16.2715 | Distribution board installation - Ground Floor Zone 05 | 0 | 2025-09-17
MOC.CN.GF.Z5.16.2495 | Sockets and Switches installation - Ground Floor Zone 05 | 0 | 2025-09-28
MOC.CN.GF.Z5.16.2490 | Lighting fixtures installation - Ground Floor Zone 05 | 0 | 2025-10-02
MOC.CN.GF.Z5.16.2750 | Floor Sockets Installation - Ground Floor Zone 05 | 0 | 2025-10-15
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.AV Audio Visual |  | 33.33 | 2025-09-29
MOC.CN.GF.Z5.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.GF.Z5.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 05 | 0 | 2025-08-05
MOC.CN.GF.Z5.16.2515 | Audiovisual system installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.LC Lighting Control |  | 70.92 | 2025-10-02
MOC.CN.GF.Z5.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 05 | 100 | 01-May-25 A
MOC.CN.GF.Z5.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 05 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z5.16.2660 | Lighting Control System installation - Ground Floor Zone 05 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-09-24
MOC.CN.GF.Z5.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 05 | 100 | 07-May-25 A
MOC.CN.GF.Z5.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 05 [Remaining] | 0 | 2025-07-31
MOC.CN.GF.Z5.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 05 | 0 | 2025-09-24
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.SS Security System |  | 2.31 | 2025-09-29
MOC.CN.GF.Z5.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 05 | 100 | 07-May-25 A
MOC.CN.GF.Z5.16.2695 | Security System Wiring Installation - Ground Floor Zone 05 | 0 | 2025-08-10
MOC.CN.GF.Z5.16.2640 | Security System Installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-09-29
MOC.CN.GF.Z5.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 05 | 100 | 07-May-25 A
MOC.CN.GF.Z5.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 05 | 0 | 2025-08-07
MOC.CN.GF.Z5.16.2645 | IPTV System installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.84 | 2025-09-29
MOC.CN.GF.Z5.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 05 | 100 | 02-Apr-25 A
MOC.CN.GF.Z5.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 05 | 100 | 31-May-25 A
MOC.CN.GF.Z5.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 05 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z5.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.PA Public Address System |  | 33.33 | 2025-09-29
MOC.CN.GF.Z5.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 05 | 100 | 02-Apr-25 A
MOC.CN.GF.Z5.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 05 | 0 | 2025-07-31
MOC.CN.GF.Z5.16.2525 | Public Address System installation - Ground Floor Zone 05 | 0 | 2025-09-29
MOC.REV.R06.U0200725.CON.GF.Z5.MEP.EL.CBS Central Battery |  | 90 | 2025-07-23
MOC.CN.GF.Z5.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 05 | 100 | 02-Apr-25 A
MOC.CN.GF.Z5.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 05 | 80 | 2025-07-23
MOC.REV.R06.U0200725.CON.GF.Z6 Zone 06 |  | 47.9 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z6.FIN Finishes |  | 46.81 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z6.FIN.C&W Ceiling & Walls |  | 50.49 | 2025-10-20
MOC.CN.GF.Z6.09.1750 | Gypsum Board Partitions First Fix - Ground Floor Zone 06 | 100 | 27-Feb-25 A
MOC.CN.GF.Z6.04.1175 | Masonary works - Ground Floor Zone 06 | 100 | 31-Mar-25 A
MOC.CN.GF.Z6.09.1740 | Plaster First Stage - Ground Floor Zone 06 | 100 | 01-Apr-25 A
MOC.CN.GF.Z6.09.1745 | Plaster Second Stage - Ground Floor Zone 06 | 100 | 10-Apr-25 A
MOC.CN.GF.Z6.09.1685 | Wooden Cladding First Fix - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.09.1755 | Gypsum Board Partitions Second Fix - Ground Floor Zone 06 | 100 | 30-Apr-25 A
MOC.CN.GF.Z6.09.1680 | Wooden Ceiling First Fix - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.09.1725 | Wooden Cladding Second Fix - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.09.1455 | First and Second painting coats - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.10.1785 | GLASS partiton - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.09.1735 | Acoustic wall panel Installation - Ground Floor Zone 06 | 100 | 15-Jun-25 A
MOC.CN.GF.Z6.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Zone 06 | 25 | 2025-08-09
MOC.CN.GF.Z6.08.1430 | Doors Frame installation - Ground Floor Zone 06 | 0 | 2025-08-27
MOC.CN.GF.Z6.09.1680[R] | Wooden Ceiling First Fix - Ground Floor Zone 06 [Remaining] | 20 | 2025-08-27
MOC.CN.GF.Z6.09.1670 | Acoustic Ceiling First Fix - Ground Floor Zone 06 | 0 | 2025-08-28
MOC.CN.GF.Z6.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Zone 06 | 5 | 2025-09-02
MOC.CN.GF.Z6.08.1400 | Wooden Doors installation - Ground Floor Zone 06 | 0 | 2025-09-03
MOC.CN.GF.Z6.09.1455[R] | First and Second painting coats - Ground Floor Zone 06 [Remaining] | 0 | 2025-09-08
MOC.CN.GF.Z6.09.1765 | Cornice Installation - Ground Floor Zone 06 | 0 | 2025-09-14
MOC.CN.GF.Z6.09.1725[R] | Wooden Cladding Second Fix - Ground Floor Zone 06 [Remaining] | 0 | 2025-09-15
MOC.CN.GF.Z6.10.2780 | Elevator Finishes - Ground Floor Zone 06 | 0 | 2025-09-22
MOC.CN.GF.Z6.10.1775 | Signage works - Ground Floor Zone 06 | 0 | 2025-09-25
MOC.CN.GF.Z6.09.1730 | Acoustic Ceiling Second Fix - Ground Floor Zone 06 | 0 | 2025-09-27
MOC.CN.GF.Z6.09.1720 | Wooden Ceiling Second Fix - Ground Floor Zone 06 | 0 | 2025-09-30
MOC.CN.GF.Z6.10.1785[R] | GLASS partiton - Ground Floor Zone 06 [Remaining] | 70 | 2025-10-07
MOC.CN.GF.Z6.09.1460 | Final painting coat - Ground Floor Zone 06 | 0 | 2025-10-12
MOC.CN.GF.Z6.10.1795 | Curtain Installation - Ground Floor Zone 06 | 0 | 2025-10-13
MOC.CN.GF.Z6.05.1220 | Metal Handles for stairs - Ground Floor Zone 06 | 0 | 2025-10-20
MOC.CN.GF.Z6.18.01 | Final Touch Up - Ground Floor Zone 06 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z6.FIN.FLR Flooring |  | 35.96 | 2025-10-20
MOC.CN.GF.Z6.09.1640 | Raised Floor First Fix - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.09.1645 | Raised Floor Final fix installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.09.1760 | Vinyl Installation - Ground Floor Zone 06 | 0 | 2025-09-04
MOC.CN.GF.Z6.09.1490 | Ceramic tiles for Flooring works - Ground Floor Zone 06 | 0 | 2025-09-29
MOC.CN.GF.Z6.09.1695 | Rubber roll flooring - Ground Floor Zone 06 | 0 | 2025-09-29
MOC.CN.GF.Z6.09.1640[R] | Raised Floor First Fix - Ground Floor Zone 06 [Remaining] | 20 | 2025-10-01
MOC.CN.GF.Z6.09.1645[R] | Raised Floor Final fix installation - Ground Floor Zone 06 [Remaining] | 20 | 2025-10-04
MOC.CN.GF.Z6.09.1595 | Carpet Installation - Ground Floor Zone 06 | 0 | 2025-10-15
MOC.CN.GF.Z6.09.1690 | Skirting Installation - Ground Floor Zone 06 | 0 | 2025-10-20
MOC.REV.R06.U0200725.CON.GF.Z6.MEP MEP |  | 48.71 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.MEC Mechanical |  | 62.21 | 2025-10-08
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.MEC.PL Plumbing |  | 72.76 | 2025-10-06
MOC.CN.GF.Z6.15.2305 | Water Supply pipes installation & Testing - Ground Floor Zone 06 | 100 | 24-Mar-25 A
MOC.CN.GF.Z6.15.1915 | Valves and accessories for Water Supply System - Ground Floor Zone 06 | 100 | 07-Apr-25 A
MOC.CN.GF.Z6.15.2420 | Water Supply pipes insulation - Ground Floor Zone 06 | 100 | 07-Apr-25 A
MOC.CN.GF.Z6.15.2295 | Drainage pipes installation & Testing - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Zone 06 [Remaining] | 60 | 2025-07-21
MOC.CN.GF.Z6.15.2315 | Floor Drain Installation - Ground Floor Zone 06 | 0 | 2025-10-06
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.MEC.FF Fire Fightig |  | 54.53 | 2025-10-08
MOC.CN.GF.Z6.15.1955 | Fire Fighting pipes installation & Testing - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.1970 | Fire Fighting valves and accessories - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.1975 | Fire-hose cabinets installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2245 | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2245[R] | NOVEC 1230 - Pipes Installation & Testing - Ground Floor Zone 06 [Remaining] | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.1955[R] | Fire Fighting pipes installation & Testing - Ground Floor Zone 06 [Remaining] | 80 | 2025-07-22
MOC.CN.GF.Z6.15.1970[R] | Fire Fighting valves and accessories - Ground Floor Zone 06 [Remaining] | 0 | 2025-07-28
MOC.CN.GF.Z6.15.1975[R] | Fire-hose cabinets installation - Ground Floor Zone 06 [Remaining] | 0 | 2025-09-15
MOC.CN.GF.Z6.15.2250 | NOVEC 1230 - Cylinders installation - Ground Floor Zone 06 | 0 | 2025-09-18
MOC.CN.GF.Z6.15.1980 | Fire extinguishers installation - Ground Floor Zone 06 | 0 | 2025-09-25
MOC.CN.GF.Z6.15.2255 | NOVEC 1230 - Nozzles installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.CN.GF.Z6.15.1985 | Fire sprinklers installation - Ground Floor Zone 06 | 0 | 2025-10-08
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.MEC.HV HVAC |  | 64.24 | 2025-10-07
MOC.CN.GF.Z6.15.2275 | Thermostat Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2320 | Air Handling pipes installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2380 | Duct Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2370 | HVAC Pipes Installation & Testing - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2385 | Duct Insulation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2390 | Duct Lining - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.15.2380[R] | Duct Installation - Ground Floor Zone 06 [Remaining] | 75 | 2025-07-21
MOC.CN.GF.Z6.15.2370[R] | HVAC Pipes Installation & Testing - Ground Floor Zone 06 [Remaining] | 0 | 2025-07-22
MOC.CN.GF.Z6.15.2385[R] | Duct Insulation - Ground Floor Zone 06 [Remaining] | 40 | 2025-07-23
MOC.CN.GF.Z6.15.2390[R] | Duct Lining - Ground Floor Zone 06 [Remaining] | 40 | 2025-07-26
MOC.CN.GF.Z6.15.2375 | HVAC Pipes Insulation - Ground Floor Zone 06 | 0 | 2025-07-31
MOC.CN.GF.Z6.15.2395 | HVAC Valves installation - Ground Floor Zone 06 | 0 | 2025-08-07
MOC.CN.GF.Z6.15.2280 | Variable Air Volume (VAV) - Ground Floor Zone 06 | 0 | 2025-08-14
MOC.CN.GF.Z6.15.2340 | Fan Coil Units Installation - Ground Floor Zone 06 | 0 | 2025-08-20
MOC.CN.GF.Z6.15.2320[R] | Air Handling pipes installation - Ground Floor Zone 06 [Remaining] | 0 | 2025-09-01
MOC.CN.GF.Z6.15.2275[R] | Thermostat Installation - Ground Floor Zone 06 [Remaining] | 0 | 2025-09-08
MOC.CN.GF.Z6.15.2755 | Air Handling Unit Valves Installation - Ground Floor Zone 06 | 0 | 2025-09-11
MOC.CN.GF.Z6.15.2325 | Air Handling units installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.CN.GF.Z6.15.2100 | Air Diffusers Installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL Electrical |  | 44.33 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.EP Electrical Power |  | 49.17 | 2025-10-18
MOC.CN.GF.Z6.16.2655 | Conduits and boxes installation - Ground Floor Zone 06 | 100 | 22-Apr-25 A
MOC.CN.GF.Z6.16.2460 | Installing electrical conduits and boxes in floors - Ground Floor Zone 06 | 100 | 22-Apr-25 A
MOC.CN.GF.Z6.16.2610 | Cable Trays & Trunks Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.16.2630 | Cables & Wiring Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.16.2610[R] | Cable Trays & Trunks Installation - Ground Floor Zone 06 [Remaining] | 0 | 2025-07-28
MOC.CN.GF.Z6.16.2630[R] | Cables & Wiring Installation - Ground Floor Zone 06 [Remaining] | 55 | 2025-07-31
MOC.CN.GF.Z6.16.2745 | Wiring Installation in floors - Ground Floor Zone 06 | 0 | 2025-08-17
MOC.CN.GF.Z6.16.2625 | Earthing System installation - Ground Floor Zone 06 | 0 | 2025-09-02
MOC.CN.GF.Z6.16.2715 | Distribution board installation - Ground Floor Zone 06 | 0 | 2025-09-27
MOC.CN.GF.Z6.16.2495 | Sockets and Switches installation - Ground Floor Zone 06 | 0 | 2025-10-04
MOC.CN.GF.Z6.16.2490 | Lighting fixtures installation - Ground Floor Zone 06 | 0 | 2025-10-08
MOC.CN.GF.Z6.16.2750 | Floor Sockets Installation - Ground Floor Zone 06 | 0 | 2025-10-18
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.AV Audio Visual |  | 33.33 | 2025-10-07
MOC.CN.GF.Z6.16.2735 | Audiovisual system Conduits and boxes installation - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.16.2740 | Audiovisual system Wiring Installation - Ground Floor Zone 06 | 0 | 2025-08-05
MOC.CN.GF.Z6.16.2515 | Audiovisual system installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.LC Lighting Control |  | 70.92 | 2025-10-02
MOC.CN.GF.Z6.16.2685 | Lighting Control Conduits and boxes installation - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.16.2710 | Lighting Control Wiring Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.16.2710[R] | Lighting Control Wiring Installation - Ground Floor Zone 06 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z6.16.2660 | Lighting Control System installation - Ground Floor Zone 06 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.T&D Telecommunication & Data System |  | 63.18 | 2025-10-04
MOC.CN.GF.Z6.16.2720 | Telecommunication & Data System Conduits and boxes installation - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.16.2200 | Telecommunication and Data Cables installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.16.2200[R] | Telecommunication and Data Cables installation - Ground Floor Zone 06 [Remaining] | 0 | 2025-08-02
MOC.CN.GF.Z6.16.2505 | Telecommunication and Data system installation - Ground Floor Zone 06 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.SS Security System |  | 2.31 | 2025-10-04
MOC.CN.GF.Z6.16.2670 | Security System Conduits and boxes installation - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.16.2695 | Security System Wiring Installation - Ground Floor Zone 06 | 0 | 2025-07-31
MOC.CN.GF.Z6.16.2640 | Security System Installation - Ground Floor Zone 06 | 0 | 2025-10-04
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.IPTV IPTV System |  | 33.33 | 2025-10-02
MOC.CN.GF.Z6.16.2675 | IPTV System Conduits and boxes installation - Ground Floor Zone 06 | 100 | 24-Apr-25 A
MOC.CN.GF.Z6.16.2700 | IPTV System Wiring Installation - Ground Floor Zone 06 | 0 | 2025-07-31
MOC.CN.GF.Z6.16.2645 | IPTV System installation - Ground Floor Zone 06 | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.FA FIRE ALARM AND VOICE EVACUATION SYSTEM |  | 58.84 | 2025-10-07
MOC.CN.GF.Z6.16.2680 | Fire Alarm & Voice Evacuation Conduits and boxes installation - Ground Floor Zone 06 | 100 | 02-Apr-25 A
MOC.CN.GF.Z6.16.2705 | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 06 | 100 | 31-May-25 A
MOC.CN.GF.Z6.16.2705[R] | Fire Alarm & Voice Evacuation Wiring Installation - Ground Floor Zone 06 [Remaining] | 90 | 2025-07-21
MOC.CN.GF.Z6.16.2650 | Fire Alarm & Voice Evacuation System Installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.PA Public Address System |  | 33.33 | 2025-10-07
MOC.CN.GF.Z6.16.2725 | Public Address System Conduits and boxes installation - Ground Floor Zone 06 | 100 | 02-Apr-25 A
MOC.CN.GF.Z6.16.2730 | Public Address System Wiring Installation - Ground Floor Zone 06 | 0 | 2025-08-05
MOC.CN.GF.Z6.16.2525 | Public Address System installation - Ground Floor Zone 06 | 0 | 2025-10-07
MOC.REV.R06.U0200725.CON.GF.Z6.MEP.EL.CBS Central Battery |  | 90 | 2025-07-23
MOC.CN.GF.Z6.16.2665 | Central Battery System Conduits and boxes installation - Ground Floor Zone 06 | 100 | 02-Apr-25 A
MOC.CN.GF.Z6.16.2690 | Central Battery System Wiring Installation - Ground Floor Zone 06 | 80 | 2025-07-23
MOC.REV.R06.U0200725.CON.GF.WT Wet Areas |  | 52.77 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.WT.FIN Finishes |  | 58.24 | 2025-09-14
MOC.REV.R06.U0200725.CON.GF.WT.FIN.C&W Ceiling & Walls |  | 64.78 | 2025-09-14
MOC.CN.GF.WT.04.1175 | Masonary works - Ground Floor Wet Areas | 100 | 10-Feb-25 A
MOC.CN.GF.WT.09.1740 | Plaster First Stage - Ground Floor Wet Areas | 100 | 02-Apr-25 A
MOC.CN.GF.WT.09.1745 | Plaster Second Stage - Ground Floor Wet Areas | 100 | 08-Apr-25 A
MOC.CN.GF.WT.09.1665 | Porcelain tiles for walls - Ground Floor Wet Areas | 100 | 19-May-25 A
MOC.CN.GF.WT.09.1455 | First and Second painting coats - Ground Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.GF.WT.09.1700 | Gypsum Board Ceiling First Fix - Ground Floor Wet Areas | 25 | 2025-07-30
MOC.CN.GF.WT.08.1430 | Doors Frame installation - Ground Floor Wet Areas | 0 | 2025-08-13
MOC.CN.GF.WT.09.1705 | Gypsum Board Ceiling Second Fix - Ground Floor Wet Areas | 0 | 2025-08-14
MOC.CN.GF.WT.09.1455[R] | First and Second painting coats - Ground Floor Wet Areas [Remaining] | 50 | 2025-08-21
MOC.CN.GF.WT.10.1790 | HPL partition installation - Ground Floor Wet Areas | 10 | 2025-08-28
MOC.CN.GF.WT.08.1400 | Wooden Doors installation - Ground Floor Wet Areas | 0 | 2025-08-30
MOC.CN.GF.WT.10.1775 | Signage works - Ground Floor Wet Areas | 0 | 2025-09-06
MOC.CN.GF.WT.09.1460 | Final painting coat - Ground Floor Wet Areas | 0 | 2025-09-14
MOC.REV.R06.U0200725.CON.GF.WT.FIN.FLR Flooring |  | 41.8 | 2025-09-10
MOC.CN.GF.WT.07.1330 | Water proofing for wet areas - Ground Floor Wet Areas | 100 | 23-Apr-25 A
MOC.CN.GF.Z1.07.1330 | Water proofing for wet areas - Ground Floor Zone 01 | 100 | 29-Apr-25 A
MOC.CN.GF.WT.09.1515 | Porcelain tiles for Flooring - Ground Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.GF.WT.09.1515[R] | Porcelain tiles for Flooring - Ground Floor Wet Areas [Remaining] | 75 | 2025-07-22
MOC.CN.GF.WT.10.1770 | Toilet Accessories and Fixtures Installation - Ground Floor Wet Areas | 0 | 2025-09-10
MOC.REV.R06.U0200725.CON.GF.WT.MEP MEP |  | 50.26 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.WT.MEP.PL Plumbing |  | 49.2 | 2025-10-02
MOC.CN.GF.WT.15.2305 | Water Supply pipes installation & Testing - Ground Floor Wet Areas | 100 | 05-Mar-25 A
MOC.CN.GF.WT.15.2420 | Water Supply pipes insulation - Ground Floor Wet Areas | 100 | 01-Apr-25 A
MOC.CN.GF.WT.15.1915 | Valves and accessories for Water Supply System - Ground Floor Wet Areas | 100 | 07-Apr-25 A
MOC.CN.GF.WT.15.2295 | Drainage pipes installation & Testing - Ground Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.GF.WT.15.1945 | Plumbing Fixtures Installations - Ground Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.GF.WT.15.2295[R] | Drainage pipes installation & Testing - Ground Floor Wet Areas [Remaining] | 50 | 2025-07-21
MOC.CN.GF.WT.15.1925 | Electrical water heater - Ground Floor Wet Areas | 70 | 2025-08-03
MOC.CN.GF.WT.15.2315 | Floor Drain Installation - Ground Floor Wet Areas | 0 | 2025-08-28
MOC.CN.GF.WT.15.1945[R] | Plumbing Fixtures Installations - Ground Floor Wet Areas [Remaining] | 0 | 2025-10-02
MOC.REV.R06.U0200725.CON.GF.WT.MEP.EL Electrical |  | 62.82 | 2025-09-06
MOC.REV.R06.U0200725.CON.GF.WT.MEP.EL.EP Electrical Power |  | 62.82 | 2025-09-06
MOC.CN.GF.WT.16.2655 | Conduits and boxes installation - Ground Floor Wet Areas | 100 | 21-Apr-25 A
MOC.CN.GF.WT.16.2630 | Cables & Wiring Installation - Ground Floor Wet Areas | 100 | 31-May-25 A
MOC.CN.GF.WT.16.2630[R] | Cables & Wiring Installation - Ground Floor Wet Areas [Remaining] | 30 | 2025-07-23
MOC.CN.GF.WT.16.2490 | Lighting fixtures installation - Ground Floor Wet Areas | 0 | 2025-09-06
MOC.REV.R06.U0200725.CON.RF Roof Floor |  | 92.23 | 2025-08-25
MOC.REV.R06.U0200725.CON.RF.FIN Finishes |  | 0
MOC.REV.R06.U0200725.CON.RF.MEP MEP |  | 92.23 | 2025-08-25
MOC.CN.RF..16.2535 | Generator installation - Roof Floor | 100 | 08-Apr-25 A
MOC.CN.RF..15.2375 | HVAC Pipes Insulation - Roof Floor | 0 | 2025-08-25
MOC.REV.R06.U0200725.CON.1 Long Lead Items Installation |  | 8.71 | 2025-10-27
MOC.CN.F1.Z5.10.1800 | Furniture - First Floor Zone 05 | 70 | 2025-10-05
MOC.CN.F1.Z6.10.1800 | Furniture - First Floor Zone 06 | 40 | 2025-10-09
MOC.CN.GF.Z2.10.1800 | Furniture - Ground Floor Zone 02 | 0 | 2025-10-14
MOC.CN.GF.Z3.10.1800 | Furniture - Ground Floor Zone 03 | 0 | 2025-10-14
MOC.CN.GF.Z4.10.1800 | Furniture - Ground Floor Zone 04 | 0 | 2025-10-14
MOC.CN.F1.Z1.10.1800 | Furniture - First Floor Zone 01 | 0 | 2025-10-14
MOC.CN.F1.Z2.10.1800 | Furniture - First Floor Zone 02 | 0 | 2025-10-14
MOC.CN.GF.Z1.10.1800 | Furniture - Ground Floor Zone 01 | 0 | 2025-10-15
MOC.CN.F1.Z4.10.1800 | Furniture - First Floor Zone 04 | 25 | 2025-10-16
MOC.CN.RF..10.1800 | Furniture - Roof Floor | 0 | 2025-10-21
MOC.CN.F1.Z3.10.1800 | Furniture - First Floor Zone 03 | 0 | 2025-10-21
MOC.CN.F2.Z3.10.1800 | Furniture - Second Floor Zone 03 | 0 | 2025-10-21
MOC.CN.F2.Z4.10.1800 | Furniture - Second Floor Zone 04 | 0 | 2025-10-21
MOC.CN.F2.Z6.10.1800 | Furniture - Second Floor Zone 06 | 0 | 2025-10-21
MOC.CN.GF.Z5.10.1800 | Furniture - Ground Floor Zone 05 | 0 | 2025-10-22
MOC.CN.F2.Z5.10.1800 | Furniture - Second Floor Zone 05 | 0 | 2025-10-22
MOC.CN.F2.Z2.10.1800 | Furniture - Second Floor Zone 02 | 0 | 2025-10-22
MOC.CN.F2.Z1.10.1800 | Furniture - Second Floor Zone 01 | 0 | 2025-10-23
MOC.CN.F2.Z6.09.1710 | Metal Suspended Ceiling First Fix - Second Floor Zone 06 | 0 | 2025-10-23
MOC.CN.GF.Z6.10.1800 | Furniture - Ground Floor Zone 06 | 0 | 2025-10-25
MOC.CN.F2.Z6.09.1715 | Metal Suspended Ceiling Second Fix - Second Floor Zone 06 | 0 | 2025-10-27
MOC.REV.R06.U0200725.POC Project Close Out |  | 0
MOC.REV.R06.U0200725.POC.T&C Final Touchup, Testing & Commissioning |  | 0
MOC.REV.R06.U0200725.POC.AS Built As Built Drawings |  | 0
MOC.REV.R06.U0200725.POC.AS Built.SUB Submittal |  | 0
MOC.REV.R06.U0200725.POC.AS Built.SUB.F01 First Floor |  | 0
MOC.REV.R06.U0200725.POC.AS Built.SUB.F02 Second Floor |  | 0
MOC.REV.R06.U0200725.POC.AS Built.SUB.GF Ground Floor |  | 0
MOC.REV.R06.U0200725.POC.AS Built.APP Approval |  | 0
MOC.REV.R06.U0200725.POC.AS Built.APP.F01 First Floor |  | 0
MOC.REV.R06.U0200725.POC.AS Built.APP.F02 Second Floor |  | 0
MOC.REV.R06.U0200725.POC.AS Built.APP.GF Ground Floor |  | 0
MOC.REV.R06.U0200725.POC.SNAG Snag List |  | 0
MOC.REV.R06.U0200725.POC.SNAG.F01 First Floor |  | 0
MOC.REV.R06.U0200725.POC.SNAG.F02 Second Floor |  | 0
MOC.REV.R06.U0200725.POC.SNAG.GF Ground Floor |  | 0
MOC.REV.R06.U0200725.POC.1 Civil Defence & UMA Handover |  | 0
MOC.REV.R06.U0200725.POC.TOC TOC |  | 0